## START HERE
PROPERTY MARKETPLACE — MASTER PROJECT ROADMAP & CHECKLIST
Your single source of truth for building the marketplace, from research to launch to mobile app.
HOW TO USE THIS WORKBOOK EVERY DAY
1. Open MASTER ROADMAP. | Look at the dashboard at the top: it tells you instantly how many tasks are done, in progress, blocked and remaining. These numbers update themselves.
2. Filter by Phase. | Click the filter arrow on the 'Phase No.' column and pick the phase you are working on. Do phases roughly in order — later phases depend on earlier ones.
3. Find your next task. | Filter Status = NOT STARTED and Priority = CRITICAL. Check the 'Dependency' column: if the dependency is not DONE, do that first.
4. Update Status as you go. | Click any Status cell and pick from the dropdown: NOT STARTED, IN PROGRESS, BLOCKED, REVIEW, DONE, DEFERRED. The dashboard and the PHASES sheet recalculate automatically.
5. Check DECISIONS LOG weekly. | Anything marked DECISION REQUIRED is waiting for you. The project cannot finish until these are answered. Write your answer in 'Final Decision' and set the date.
WHAT THE COLOUR TAGS MEAN
OBSERVED FROM RESEARCH | This comes from the attached research document — it was actually observed on a live competitor marketplace. Treat it as evidence.
PROPOSED | This is a recommendation, not an observation. It is a sensible default but you may change it.
DECISION REQUIRED | Nobody has decided this yet. It needs YOUR answer. See the DECISIONS LOG sheet.
USER REQUIREMENT | This came from your own instructions rather than from the research.
THE SEVEN QUESTIONS THIS WORKBOOK ANSWERS
1. What is already done? | MASTER ROADMAP dashboard + filter Status = DONE.
2. What should I work on next? | MASTER ROADMAP: filter Status = NOT STARTED, sort by Phase No., check Dependency.
3. What is blocked? | MASTER ROADMAP: filter Status = BLOCKED.
4. What depends on what? | MASTER ROADMAP 'Dependency' column, and the PHASES sheet 'Dependencies' column.
5. What belongs to the MVP? | MVP CHECKLIST sheet: filter MVP? = MVP.
6. What can wait? | MVP CHECKLIST: filter MVP? = FUTURE. Then see POST-LAUNCH ROADMAP for when.
7. What decisions are outstanding? | DECISIONS LOG: filter Decision Status = OPEN — DECISION REQUIRED.
THE SHEETS, IN THE ORDER YOU WILL NEED THEM
MASTER ROADMAP | All 213 tasks with dependencies, effort, deliverables and acceptance criteria. Your daily working sheet.
PHASES | The 24 phases at a glance, with progress bars that calculate themselves from MASTER ROADMAP.
MVP CHECKLIST | What must be built for launch, and what must NOT be built yet. Your defence against scope creep.
FEATURE CHECKLIST | Every feature broken down by who uses it and what it needs (frontend, backend, database, API).
WEBSITE PAGES | Every page to design and build, with its URL and whether it needs SEO.
USER FLOWS | Step-by-step journeys for buyers, sellers and admins, including what can go wrong at each step.
DATABASE | The proposed tables, what each is for, and which are MVP versus later.
API CHECKLIST | Every planned API endpoint. Do not build these yet — this is the plan.
UI/UX CHECKLIST | The design system and interface work, from tokens to accessibility.
SEO CHECKLIST | URL structure, metadata, sitemaps and indexation. Read this BEFORE building any page.
SECURITY CHECKLIST | Controls that protect users, data and the business model.
TESTING & QA | What to test and what 'passing' means for each item.
PERFORMANCE | Hard speed targets, in plain English, with how to measure each one.
DEVOPS & DEPLOYMENT | Environments, deployment, backups, monitoring and disaster recovery.
THIRD-PARTY SERVICES | External services you will need, when, and what they cost.
MONETIZATION ROADMAP | How the product makes money, and why none of it happens at launch.
LAUNCH CHECKLIST | The final gate. Every item must be DONE or consciously DEFERRED before going live.
POST-LAUNCH ROADMAP | What comes after launch, grouped into releases.
DECISIONS LOG | Every open decision. THE MOST IMPORTANT SHEET FOR YOU PERSONALLY.
GLOSSARY | Every technical term in plain English. Start here if a word is unfamiliar.
IMPORTANT RULES BUILT INTO THIS PLAN
Supply before demand. | Sellers and listings come before buyer features. An empty marketplace cannot be tested by buyers.
Measure before you monetise. | The lead loop is fully instrumented in Phase 10, but nothing is charged until after launch. You cannot price what you cannot measure.
URLs before pages. | The URL structure is decided in Phase 2, before any page is built. Retrofitting SEO-grade URLs later is effectively a rewrite.
Performance before launch. | Speed budgets are enforced in the build pipeline before going live, because performance debt compounds.
Nothing copied. | This is an ORIGINAL product. No competitor branding, wording, imagery, styling or content is used anywhere.
HONEST LIMITATIONS OF THIS PLAN
Effort estimates assume competent full-time development. | They are S (1-2 days), M (3-5 days), L (1-2 weeks), XL (2-4 weeks). If you are learning as you go, or working part-time, multiply accordingly. See DECISIONS LOG D-23.
Some source research is marked UNKNOWN. | The research document could not inspect the competitor's frontend code, backend or performance. Nothing here claims otherwise, and no invented technical details were used to fill gaps.
One research conflict is flagged, not hidden. | The research document is internally inconsistent about whether 'similar properties' belongs in the MVP. See DECISIONS LOG D-14.
This plan does not include business costs. | Marketing, legal fees, salaries and supply acquisition are outside this workbook's scope, but they will decide whether the project succeeds.

## MASTER ROADMAP
MASTER ROADMAP — complete task list, phase by phase
Filter by Phase No. to see one phase at a time. Check 'Dependency' before starting a task. Update 'Status' from the dropdown — the dashboard below and the PHASES sheet recalculate automatically.
PROGRESS DASHBOARD (these numbers update themselves)
Total tasks | 213 |  | DONE | 2 |  | NOT STARTED | 211
IN PROGRESS | 0 |  | BLOCKED | 0 |  | REVIEW | 0
DEFERRED | 0 |  | MVP tasks (Ph 0-20) | 196 |  | Future tasks (Ph 21-23) | 17
CRITICAL priority | 122 |  | Decisions required | 15 |  | OVERALL COMPLETION | 0.939%
Phase | Phase No. | Task ID | Task | Subtask | Description | Why It Is Needed | Dependency | Priority | Status | Owner | Estimated Effort | Deliverable | Acceptance Criteria | Notes | Source
Phase 0 — Research & Product Definition | 0 | 0.1 | Competitor & market research | Reverse-engineer a market leader | Study the publicly observable structure, UX, URL grammar, SEO model and monetisation of an established marketplace. | You cannot design an original product well without knowing what the category standard actually is. | None | CRITICAL | DONE | UNASSIGNED | XL · 2–4 weeks | Research specification document | Document exists, every claim carries a confidence rating, sources cited. | COMPLETE. See docs/99acres-reverse-engineering-and-marketplace-spec.md in this repository. | OBSERVED FROM RESEARCH
Phase 0 — Research & Product Definition | 0 | 0.2 | Define the business model | Confirm lead-generation model | Confirm the product makes money from seller-side visibility and leads, not from buyer fees or transactions. | Every downstream decision (data model, ranking, quotas) follows from this. Research confirms the incumbent monetises contact reveals. | 0.1 | CRITICAL | DONE | UNASSIGNED | S · 1–2 days | One-page business-model statement | Written statement: who pays, for what, at which moment. | Research confirms the monetisable event is the contact reveal, not the listing. | OBSERVED FROM RESEARCH
Phase 0 — Research & Product Definition | 0 | 0.3 | Choose launch scope | Pick cities and categories | Decide which cities and which property categories the first version covers. | A narrow launch is testable. A national launch across all categories is not. | 0.2 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Written scope statement | Named cities and categories, written down and agreed. | Research proposes 3 cities, residential Buy + Rent only. YOU MUST CONFIRM which cities. See DECISIONS LOG D-11/D-12. | DECISION REQUIRED
Phase 0 — Research & Product Definition | 0 | 0.4 | Define MVP boundary | Agree what is NOT in v1 | Write the explicit out-of-scope list so scope creep is visible when it happens. | Unbounded MVPs never ship. The deferred list is as important as the included list. | 0.3 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Signed-off MVP + out-of-scope list | Both lists written; each deferred item has a target future phase. | See MVP CHECKLIST sheet. Research §24 gives the starting boundary. | OBSERVED FROM RESEARCH
Phase 0 — Research & Product Definition | 0 | 0.5 | Define success metrics | Set measurable launch targets | Agree the numbers that mean the MVP worked. | Without targets you cannot tell success from activity. | 0.4 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Metrics table with targets | Each metric has a target number and a way to measure it. | Research §24 proposes: ≥2,000 listings, search→PDP ≥25%, PDP→contact ≥8%, OTP completion ≥70%. | PROPOSED
Phase 0 — Research & Product Definition | 0 | 0.6 | Legal and compliance review | Engage a lawyer early | Review data-protection obligations (India DPDP Act), listing liability, T&C, privacy policy, RERA advertising norms. | This is not an engineering decision and getting it wrong after launch is expensive. | 0.3 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Legal opinion + draft policies | Lawyer has reviewed the data model and the T&C draft. | Research §17.5 flags DPDP consent, retention, erasure; GST invoicing; RERA disclosure. Do not skip. | OBSERVED FROM RESEARCH
Phase 0 — Research & Product Definition | 0 | 0.7 | Brand and naming | Choose name, domain, identity | Pick a product name, secure the domain and social handles, define brand direction. | Needed before design, SEO and any public artefact. | 0.3 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Name + registered domain | Domain registered, name checked for trademark conflict. | MUST be original. Do not reuse any competitor branding, wording or visual identity. | DECISION REQUIRED
Phase 0 — Research & Product Definition | 0 | 0.8 | Supply acquisition plan | Plan how to get first listings | Decide how the first 2,000 listings arrive: manual outreach, agent partnerships, free posting drive. | An empty marketplace cannot be tested by buyers. Supply must exist before demand. | 0.3 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Written supply plan with owner | A named plan with a weekly listing target. | Research §23 sequencing: supply before demand. This is a business task, not an engineering task — it is the most common reason marketplaces fail. | OBSERVED FROM RESEARCH
Phase 1 — Project Foundation | 1 | 1.1 | Create code repository | Set up Git + GitHub | Create the repository, add README, LICENSE, .gitignore and CODEOWNERS. | Single source of truth for all code and history. | 0.7 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Repository with initial commit | Repo exists, you can clone and push. |  | PROPOSED
Phase 1 — Project Foundation | 1 | 1.2 | Branch strategy | Agree branching rules | Define main/develop/feature branch rules and who can merge. | Prevents broken code reaching production. | 1.1 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Written branching policy in README | Policy documented; main branch protected. | PROPOSED: trunk-based with short feature branches + required PR review. | PROPOSED
Phase 1 — Project Foundation | 1 | 1.3 | Choose frontend framework | Confirm Next.js + TypeScript | Confirm the frontend framework and language. | Server-side rendering is a hard requirement for the SEO model; retrofitting it later is a rewrite. | 0.4 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Recorded decision | Decision written in DECISIONS LOG with date. | Research §22 recommends Next.js (App Router) + React + TypeScript. See DECISIONS LOG D-01. | DECISION REQUIRED
Phase 1 — Project Foundation | 1 | 1.4 | Choose backend framework | Confirm backend language/framework | Confirm backend framework and whether it is a modular monolith. | Determines hiring, libraries and deployment for the whole project. | 0.4 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Recorded decision | Decision written in DECISIONS LOG with date. | Research §22 recommends NestJS (TypeScript) modular monolith; Spring Boot if the team is Java-strong. See D-02. | DECISION REQUIRED
Phase 1 — Project Foundation | 1 | 1.5 | Scaffold projects | Create frontend + backend skeletons | Create empty but runnable frontend and backend applications. | Gives a working baseline everything else builds on. | 1.3,1.4 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Two runnable apps | Both start locally with one command. |  | PROPOSED
Phase 1 — Project Foundation | 1 | 1.6 | Code quality tooling | ESLint, Prettier, TypeScript strict | Configure linting, formatting and strict type checking. | Catches a large class of bugs before they are written. | 1.5 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Lint + format config committed | Lint runs clean on the scaffold. |  | PROPOSED
Phase 1 — Project Foundation | 1 | 1.7 | Environment configuration | Set up .env handling | Define environment variables and a .env.example; never commit real secrets. | Secrets in Git are the single most common serious security mistake. | 1.5 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | .env.example + secret policy | No real secret exists in Git history. | See SECURITY CHECKLIST and DEVOPS sheets. | PROPOSED
Phase 1 — Project Foundation | 1 | 1.8 | Local development setup | Docker Compose for DB + cache | Run PostgreSQL and Redis locally with one command. | Everyone develops against the same versions. | 1.5 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | docker-compose.yml | `docker compose up` gives a working DB and cache. |  | PROPOSED
Phase 1 — Project Foundation | 1 | 1.9 | CI pipeline (basic) | GitHub Actions: lint, typecheck, test | Run checks automatically on every pull request. | Stops broken code merging while the codebase is still small. | 1.6 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Green CI on the scaffold | CI runs on PR and blocks merge on failure. | Performance and Lighthouse gates are added later in Phase 16. | PROPOSED
Phase 1 — Project Foundation | 1 | 1.10 | Project documentation | Start a living README/architecture doc | Document how to run, test and deploy the project. | You will not remember this in three months. | 1.5 | MEDIUM | NOT STARTED | UNASSIGNED | S · 1–2 days | README with setup steps | A new machine can run the project from the README alone. |  | PROPOSED
Phase 2 — Product Architecture | 2 | 2.1 | Define module boundaries | Agree the backend modules | Split the backend into modules: identity, location, listing, search, lead, moderation, content, billing. | Clear boundaries now make it cheap to split into services later, if ever needed. | 1.4 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Module map diagram | Every module has a written owner-of-data statement. | Research §21.3 gives the module table. Modules talk via events, never by reading each other's tables. | OBSERVED FROM RESEARCH
Phase 2 — Product Architecture | 2 | 2.2 | Define URL / route architecture | Design the public URL structure | Design every public route before building any page. | The research's single highest-leverage finding: URL structure IS the product architecture for SEO. | 0.3 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Route table (see WEBSITE PAGES sheet) | Every planned page has an agreed final URL pattern. | Research §16.5. Two surfaces: pretty SSR URLs (indexable) and /search?… (noindex). | OBSERVED FROM RESEARCH
Phase 2 — Product Architecture | 2 | 2.3 | Decide rendering strategy | SSR / SSG / ISR per route type | Decide which pages are server-rendered, statically generated or incrementally regenerated. | Directly determines SEO performance and hosting cost. | 2.2 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Rendering decision per route type | Each route type in WEBSITE PAGES has a rendering mode. | Research §18.4: SSR for all indexable routes; personalisation must never block first paint. | OBSERVED FROM RESEARCH
Phase 2 — Product Architecture | 2 | 2.4 | Choose database | Confirm PostgreSQL + PostGIS | Confirm the primary database and geospatial extension. | One engine covers search, geo and transactions for the whole first phase. | 1.4 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Recorded decision | Decision in DECISIONS LOG. | Research §22 recommends PostgreSQL 16 + PostGIS. See D-03. | DECISION REQUIRED
Phase 2 — Product Architecture | 2 | 2.5 | Decide search approach | Postgres now, OpenSearch later | Confirm that MVP search runs on PostgreSQL and a search cluster is deferred. | Avoids running a search cluster before there is data to justify it. | 2.4 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Recorded decision + trigger | Written trigger for when to migrate (listing count or latency). | Research §13.3: Postgres to ~100k listings, then OpenSearch. See D-04. | DECISION REQUIRED
Phase 2 — Product Architecture | 2 | 2.6 | Define the normalised filter object | One filter shape for both surfaces | Design a single canonical object that both the pretty URL and the query-param URL translate into. | Prevents the two surfaces drifting apart and returning different results. | 2.2 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Filter object schema | Both URL forms parse to an identical object in tests. | Research §6.2 — this is the core search design decision. | OBSERVED FROM RESEARCH
Phase 2 — Product Architecture | 2 | 2.7 | Define ID strategy | Public vs internal identifiers | Decide how entity IDs look publicly and internally. | Sequential public IDs leak business volume and allow enumeration. | 2.4 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | ID convention document | Public IDs are non-sequential and prefixed per entity type. | Research §11.1 observed typed prefixed IDs. PROPOSED: internal bigint + public prefixed short ID. | PROPOSED
Phase 2 — Product Architecture | 2 | 2.8 | Define event/outbox pattern | How modules communicate | Design the transactional outbox and domain events. | Keeps search index, notifications and analytics in sync without fragile dual writes. | 2.1 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Event catalogue + outbox design | Listing publish emits one event consumed by indexer and alerts. | Research §21.4. | OBSERVED FROM RESEARCH
Phase 2 — Product Architecture | 2 | 2.9 | Choose hosting and cloud | Pick where it runs | Decide hosting for frontend, backend, database and object storage. | Affects cost, deployment and every DevOps task. | 1.4 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Recorded decision + cost estimate | Decision in DECISIONS LOG with a monthly cost estimate. | Research §22: managed hosting first, Kubernetes only when justified. See D-07. | DECISION REQUIRED
Phase 2 — Product Architecture | 2 | 2.10 | Write architecture document | Consolidate all decisions | Write one document describing the whole system. | You are not an expert — this document is how you stay oriented. | 2.1-2.9 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Architecture document | A new developer can understand the system from it. |  | PROPOSED
Phase 3 — Design System & UI/UX | 3 | 3.1 | Define design tokens | Colour, type, spacing, radius scales | Define the design variables that every component uses. | Stops the UI drifting into inconsistency; makes dark mode and theming cheap. | 1.5 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Token file (CSS variables) | No component contains a raw colour or pixel value. | Research §14.4/§14.5. MUST be an original visual identity — do not copy competitor colours or fonts. | OBSERVED FROM RESEARCH
Phase 3 — Design System & UI/UX | 3 | 3.2 | Choose typography | Font family and type scale | Pick fonts, including Indic script coverage if localisation is ever planned. | Font choice is hard to change later and affects performance. | 3.1 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Type scale documented | Scale defined; tabular numerals enabled for prices. | Research §14.3 proposes a 1.250 scale and tabular numerals for price/area alignment. | PROPOSED
Phase 3 — Design System & UI/UX | 3 | 3.3 | Build base components | Button, input, select, chip, badge | Build the smallest reusable UI pieces. | Everything else is assembled from these. | 3.1 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Component library v1 | Each has all states: default, hover, focus, disabled, loading, error. | Research §14.6. | OBSERVED FROM RESEARCH
Phase 3 — Design System & UI/UX | 3 | 3.4 | Design the property card | The most important component | Design the card used in every result list. | It is the unit of comparison; card quality drives click-through. | 3.3 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Property card component | Fixed image ratio, one primary action, area basis always labelled. | Research §7.1. One filled primary button only — two competing buttons reduce clicks on both. | OBSERVED FROM RESEARCH
Phase 3 — Design System & UI/UX | 3 | 3.5 | Design search and filter UI | Search bar, filter panel, chips, sort | Design the search entry point and the filter experience for desktop and mobile. | Search is the product's main funnel. | 3.3 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Search + filter components | Mobile uses a full-screen sheet with a live result count on Apply. | Research §6.4/§15.3. Desktop = left rail apply-on-change; mobile = sheet apply-on-confirm. | OBSERVED FROM RESEARCH
Phase 3 — Design System & UI/UX | 3 | 3.6 | Design navigation | Header, footer, mobile bottom nav | Design site navigation for all breakpoints. | Orientation and the supply-side call to action live here. | 3.3 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Navigation components | Bottom nav on mobile; Post Property visually distinct from primary actions. | Research §14.9. | OBSERVED FROM RESEARCH
Phase 3 — Design System & UI/UX | 3 | 3.7 | Design system states | Empty, loading, error, skeleton | Design what every screen shows when there is no data, data is loading, or something failed. | Beginners skip these; they are half of the real user experience. | 3.3 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | State components | Zero-results screen offers a recovery action, never a dead end. | Research §4.2 empty-state rules: name the blocking filter, offer radius expansion, offer alert. | OBSERVED FROM RESEARCH
Phase 3 — Design System & UI/UX | 3 | 3.8 | Accessibility baseline | WCAG 2.1 AA | Define and check contrast, focus rings, keyboard order, touch targets. | Legal exposure, and it measurably improves usability for everyone. | 3.3 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Accessibility checklist passed | Visible focus ring everywhere; 44x44px minimum touch targets. | Research §14.11. Never remove focus outlines without a replacement. | OBSERVED FROM RESEARCH
Phase 3 — Design System & UI/UX | 3 | 3.9 | Responsive rules | Breakpoints and layout changes | Define what changes at each breakpoint. | Most traffic will be mobile. | 3.4,3.5 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Responsive specification | Every component has a defined behaviour at each breakpoint. | Research §15.2 gives the full breakpoint table. | OBSERVED FROM RESEARCH
Phase 3 — Design System & UI/UX | 3 | 3.10 | Motion and reduced motion | Animation rules | Define durations, easing, and honour prefers-reduced-motion. | Excess motion feels slow and harms accessibility. | 3.3 | MEDIUM | NOT STARTED | UNASSIGNED | S · 1–2 days | Motion tokens | No core-path animation exceeds 200ms; reduced-motion respected. | Research §14.10. | OBSERVED FROM RESEARCH
Phase 3 — Design System & UI/UX | 3 | 3.11 | Wireframe key screens | Home, results, PDP, posting, dashboard | Draw the main screens before building them. | Cheaper to change a drawing than a build. | 3.4-3.7 | HIGH | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Wireframes for all MVP screens | Every MVP page in WEBSITE PAGES has a wireframe. |  | PROPOSED
Phase 4 — Database & Backend Foundation | 4 | 4.1 | Design database schema v1 | Tables, columns, types | Write the first schema covering MVP entities only. | The data model constrains everything built on top of it. | 2.4 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Schema definition / migration files | All MVP tables in DATABASE sheet exist. | Research §12. Do not build future-phase tables yet. | OBSERVED FROM RESEARCH
Phase 4 — Database & Backend Foundation | 4 | 4.2 | Set up migrations | Versioned schema changes | Configure a migration tool so schema changes are versioned and reversible. | Manual schema edits in production cause outages and data loss. | 4.1 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Migration tooling working | Migrations run forward and roll back cleanly. |  | PROPOSED
Phase 4 — Database & Backend Foundation | 4 | 4.3 | Three area fields, not one | carpet / built-up / super area | Model the three Indian area measurements as separate fields. | Conflating them produces wrong price-per-sqft and destroys user trust. | 4.1 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Area fields in schema | All three fields exist plus an explicit area-unit field. | Research §12.3 — flagged as the most common data-integrity failure in this domain. | OBSERVED FROM RESEARCH
Phase 4 — Database & Backend Foundation | 4 | 4.4 | Listing state machine | Define lifecycle states | Implement DRAFT, UNDER_SCREENING, ACTIVE, REJECTED, EXPIRED, SOLD/RENTED, DELETED. | Lifecycle is a product feature, not an implementation detail. | 4.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | State machine + transitions | Illegal transitions are rejected by the database or service layer. | Research §8.1 observed these exact states on the incumbent. | OBSERVED FROM RESEARCH
Phase 4 — Database & Backend Foundation | 4 | 4.5 | Seed reference data | Property types, amenities | Load the fixed lookup lists. | Needed before any listing can be created. | 4.1 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Seed scripts | Reference tables populated and re-runnable. |  | PROPOSED
Phase 4 — Database & Backend Foundation | 4 | 4.6 | Core indexes | Add indexes for hot queries | Add the indexes the search and dashboard queries need. | Without them search degrades badly as data grows. | 4.1 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Index migration | Indexes from DATABASE sheet created. | Research §12.4 gives a starting index plan. Do not add every possible index — measure first. | OBSERVED FROM RESEARCH
Phase 4 — Database & Backend Foundation | 4 | 4.7 | Backend skeleton + health check | Module folders, config, /health | Create the backend module structure and a health endpoint. | Deployment and monitoring need a health check from day one. | 2.1 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Running API with /health | /health returns 200 with DB connectivity confirmed. |  | PROPOSED
Phase 4 — Database & Backend Foundation | 4 | 4.8 | Error handling and logging | Standard error shape | Define one error response format and structured logging. | Consistent errors make debugging and frontend handling far simpler. | 4.7 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Error middleware + logger | All errors return the same JSON shape with a request ID. |  | PROPOSED
Phase 4 — Database & Backend Foundation | 4 | 4.9 | API conventions | Naming, versioning, pagination | Agree REST conventions before writing endpoints. | Inconsistent APIs are painful to consume and document. | 4.7 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | API convention document | Documented and applied to the first endpoint. | See API CHECKLIST sheet. | PROPOSED
Phase 4 — Database & Backend Foundation | 4 | 4.10 | Object storage + presigned uploads | S3-compatible bucket | Set up media storage with direct-from-browser presigned uploads. | Keeps large image uploads off the application server. | 2.9 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Working upload to storage | A file uploads from the browser without passing through the API. | Research §22. Enforce content-type and size limits on the presigned URL. | OBSERVED FROM RESEARCH
Phase 4 — Database & Backend Foundation | 4 | 4.11 | Background job queue | Set up worker + queue | Configure the queue and a worker process. | Image processing, moderation, alerts and indexing must not block requests. | 4.7 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Queue + worker running | A test job is enqueued and processed. | Research §22 proposes BullMQ on Redis to avoid new infrastructure. | PROPOSED
Phase 5 — User Authentication | 5 | 5.1 | Choose OTP provider | Pick an SMS/OTP vendor | Select and contract an SMS provider that supports Indian DLT registration. | OTP is the primary login method; DLT template registration is legally required in India and takes time. | 0.6 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Signed provider + registered templates | Test OTP delivered to a real Indian number. | Research §22 names MSG91 / Twilio / AWS SNS as candidates. See DECISIONS LOG D-09. Start DLT registration EARLY — it has a lead time. | DECISION REQUIRED
Phase 5 — User Authentication | 5 | 5.2 | User + role model | Users with multiple roles | Implement users where one account can be both buyer and seller. | A person who buys today may sell next year; single-role accounts force duplicate accounts. | 4.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | User table + role array | One account can hold buyer and owner roles simultaneously. | Research §12.2. Incumbent enforces one account per phone+email. | OBSERVED FROM RESEARCH
Phase 5 — User Authentication | 5 | 5.3 | OTP request + verify | Send and check the code | Build the endpoints that send an OTP and verify it. | The entry point to every authenticated action. | 5.1,5.2 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Working OTP login | A new user can register and log in by phone only. |  | OBSERVED FROM RESEARCH
Phase 5 — User Authentication | 5 | 5.4 | OTP abuse protection | Rate limits and expiry | Limit OTP requests per number and per IP; expire and single-use every code. | Without limits, OTP endpoints are abused and your SMS bill becomes the attack. | 5.3 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Rate-limit rules live | Max attempts enforced; codes expire; reuse rejected. | Research §17.5 proposes max 5/hour/number with exponential backoff. | OBSERVED FROM RESEARCH
Phase 5 — User Authentication | 5 | 5.5 | Session tokens | JWT access + refresh rotation | Issue short-lived access tokens and rotating refresh tokens. | Balances security against making users log in constantly. | 5.3 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Token issue + refresh working | Access token expires; refresh rotates; reuse is detected. | Research §22. See DECISIONS LOG D-08. | PROPOSED
Phase 5 — User Authentication | 5 | 5.6 | Role-based authorization | Permission checks | Enforce what each role may do on the server, on every endpoint. | Client-side role checks are decoration; server checks are security. | 5.5 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Authorization middleware | A buyer token cannot edit a listing, proven by test. |  | PROPOSED
Phase 5 — User Authentication | 5 | 5.7 | Account management | Profile edit, phone change | Let users update name, email and phone with re-verification. | Basic expectation; phone change must invalidate sessions. | 5.5 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Profile screens + API | Phone change requires OTP and invalidates other sessions. | Research §17.5. | OBSERVED FROM RESEARCH
Phase 5 — User Authentication | 5 | 5.8 | Login/registration UI | Auth screens and modal | Build sign-in, registration and the inline auth prompt. | Must interrupt a buyer action without losing what they were doing. | 3.3,5.3 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Auth UI complete | After login, the interrupted action (e.g. save) completes automatically. | Research §9.1 — replaying the intended action after login is a real conversion factor. | OBSERVED FROM RESEARCH
Phase 5 — User Authentication | 5 | 5.9 | Account deletion / data rights | DPDP compliance | Let users request deletion and export of their data. | Legal requirement under India's data-protection law. | 0.6,5.7 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Deletion + export flow | A request is honoured within the policy window and logged. | Research §17.5. Soft-delete only where leads/payments reference the user. | OBSERVED FROM RESEARCH
Phase 6 — Location & Property Data | 6 | 6.1 | Design the location model | Hierarchical place tree | Build country → state → city → zone → locality → society as a self-referencing tree. | The research calls this the most important table in the system; search, SEO and stats all depend on it. | 4.1 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | LOCATION table + tree queries | Any locality resolves its full ancestor path in one query. | Research §12.2/§12.3. Incumbent uses numeric location IDs shared across all features. | OBSERVED FROM RESEARCH
Phase 6 — Location & Property Data | 6 | 6.2 | Source locality data | Acquire place data for launch cities | Obtain or compile locality names and coordinates for the launch cities. | Cannot be generated; this is a real data-acquisition task people underestimate. | 0.3,6.1 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Seeded gazetteer | All localities in the launch cities exist with coordinates. | DECISION REQUIRED: source (open data, commercial, manual). Research §20.4 flags boundary polygons as a genuine project. | DECISION REQUIRED
Phase 6 — Location & Property Data | 6 | 6.3 | Location aliases | Handle alternate names | Store alternate spellings (e.g. Bangalore/Bengaluru, Gurgaon/Gurugram). | Users type both; without aliases search silently fails. | 6.1 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Alias field + search support | Searching either spelling returns the same place. | Research §12.2 — specifically called out for the Indian market. | OBSERVED FROM RESEARCH
Phase 6 — Location & Property Data | 6 | 6.4 | Location slugs | URL-safe names | Generate and store stable slugs and full paths for every place. | SEO URLs are built from these; they must be stable. | 6.1,2.2 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Slug fields populated | Every active place has a unique, stable slug. |  | OBSERVED FROM RESEARCH
Phase 6 — Location & Property Data | 6 | 6.5 | Typeahead suggestion table | Denormalised search-as-you-type data | Build a separate lightweight table for autocomplete. | Never run autocomplete against the live property table — it will be slow. | 6.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | place_suggest table + index | Typeahead responds within the latency budget. | Research §13.3. Include result counts next to suggestions — it improves selection quality. | OBSERVED FROM RESEARCH
Phase 6 — Location & Property Data | 6 | 6.6 | Typeahead API + UI | Multi-entity autocomplete | Return grouped suggestions (city, locality, society) and render them as removable chips. | Users type cities, localities and society names interchangeably. | 6.5,3.5 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Working typeahead | Grouped results; debounced; in-flight requests cancelled. | Research §6.6. Debounce ~250ms and cancel stale requests to avoid flicker. | OBSERVED FROM RESEARCH
Phase 6 — Location & Property Data | 6 | 6.7 | PostGIS geometry | Coordinates and distance queries | Enable PostGIS and store point geometry for places and listings. | Needed for radius search, map bounds and 'near me'. | 4.1 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Geo columns + GIST indexes | A radius query returns correct results. | Research §13.3. Boundary polygons can come later, city by city. | OBSERVED FROM RESEARCH
Phase 6 — Location & Property Data | 6 | 6.8 | Property type taxonomy | Define categories | Define residential/commercial types and which fields each requires. | Field sets differ per type; this drives the posting form and filters. | 0.3 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Type registry | Each type maps to a required field set. | Research §8.2 recommends a declarative field registry rather than hardcoded forms. See D-12. | OBSERVED FROM RESEARCH
Phase 6 — Location & Property Data | 6 | 6.9 | Amenity taxonomy | Define amenity list and groups | Define amenities grouped by society/flat/safety/recreation. | Used in posting, filtering and display; changing it later is disruptive. | 6.8 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Amenity reference data | Amenities seeded with groups and filterability flags. | Research §12.2. | OBSERVED FROM RESEARCH
Phase 7 — Seller / Owner Property Posting | 7 | 7.1 | Design the posting wizard | Plan the step sequence | Design the multi-step form: basics, location, profile, media, pricing, description, contact, preview. | A long single-page form has very poor completion rates on mobile. | 3.11,6.8 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Wizard flow design | Every step and field mapped; see USER FLOWS sheet. | Research §8.1 observed a 6-step form on the incumbent; §8.2 proposes our version. | OBSERVED FROM RESEARCH
Phase 7 — Seller / Owner Property Posting | 7 | 7.2 | Draft autosave | Save from the first step | Create a server-side draft as soon as the user starts, and save each step. | Losing a half-finished form is the single biggest abandonment cause. | 7.1,5.5 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Draft persistence | Refreshing mid-form loses nothing; draft resumable from dashboard. | Research §8.2 flags this as a critical requirement. | OBSERVED FROM RESEARCH
Phase 7 — Seller / Owner Property Posting | 7 | 7.3 | Config-driven form fields | Declarative field registry | Drive the visible fields from (intent, segment, property type) configuration. | Hardcoded branching becomes unmaintainable once there are several property types. | 6.8,7.1 | HIGH | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Field registry + renderer | Adding a property type needs no new form code. | Research §8.2. | OBSERVED FROM RESEARCH
Phase 7 — Seller / Owner Property Posting | 7 | 7.4 | Location step | Map pin + locality validation | Let the seller pick locality and drag a map pin; validate the pin against the locality. | Wrong locations make search results wrong and erode trust fast. | 6.6,6.7 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Location step working | Pin outside the selected locality triggers a warning. | Research §8.2. | OBSERVED FROM RESEARCH
Phase 7 — Seller / Owner Property Posting | 7 | 7.5 | Photo upload | Multi-image upload pipeline | Client-side compression, presigned upload, progress, reorder, set primary. | Photos are the highest-impact listing field. | 4.10,7.1 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Working photo upload | Multiple photos upload, reorder and persist reliably on mobile. | Research §24 proposes a conservative cap of 30 for MVP (incumbent allows 50). | OBSERVED FROM RESEARCH
Phase 7 — Seller / Owner Property Posting | 7 | 7.6 | Image processing worker | Thumbnails, format conversion, EXIF strip | Generate sized variants, convert to modern formats, strip EXIF metadata. | EXIF can contain the home's GPS coordinates — a real privacy risk. | 4.11,7.5 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Processing pipeline | Variants generated; EXIF removed; originals retained securely. | Research §17.5 and §18.4. | OBSERVED FROM RESEARCH
Phase 7 — Seller / Owner Property Posting | 7 | 7.7 | Perceptual image hashing | Duplicate detection groundwork | Compute and store an image fingerprint on upload. | Duplicate listings are the top user complaint in this category; build the hook early. | 7.6 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | phash stored per image | Identical images across listings are detectable by query. | Research §12.2/§17.5 — 'build the hash pipeline early, tune later'. | OBSERVED FROM RESEARCH
Phase 7 — Seller / Owner Property Posting | 7 | 7.8 | Pricing step | Price, negotiable, deposits, charges | Capture sale price or rent plus deposit, maintenance and charges. | Price is the primary comparison field; incomplete pricing generates wasted leads. | 7.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Pricing step working | Rent listings capture deposit and maintenance separately. |  | OBSERVED FROM RESEARCH
Phase 7 — Seller / Owner Property Posting | 7 | 7.9 | Description sanitisation | Strip contact details from text | Detect and remove phone numbers, emails and URLs from free text, including obfuscated forms. | Protects the lead model and prevents off-platform scams. | 7.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Sanitisation active | Obfuscated numbers ('nine eight seven…') are caught in tests. | Research §17.4 — incumbent enforces this in both text and images. | OBSERVED FROM RESEARCH
Phase 7 — Seller / Owner Property Posting | 7 | 7.10 | Completeness score | Live listing quality score | Show a score with the value of each missing field. | The cheapest available lever on listing quality. | 7.3 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Score shown in wizard | Score updates live and names the next best field to add. | Research §8.2. | OBSERVED FROM RESEARCH
Phase 7 — Seller / Owner Property Posting | 7 | 7.11 | Preview step | Exact public rendering | Show the seller precisely what buyers will see. | Builds seller confidence and catches mistakes before publication. | 7.3,9.1 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Preview screen | Preview is visually identical to the live page. |  | OBSERVED FROM RESEARCH
Phase 7 — Seller / Owner Property Posting | 7 | 7.12 | Publish + free quota | Submit for screening, enforce limits | Publish into the screening state and enforce the free-listing quota. | Quota is the foundation of later monetisation. | 7.11,4.4 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Publish working | Quota enforced; over-quota attempt is blocked with a clear message. | Research §8.1 observed 1–2 free owner listings. Our quota value: DECISION REQUIRED. | DECISION REQUIRED
Phase 7 — Seller / Owner Property Posting | 7 | 7.13 | Edit / renew / delete | Manage an existing listing | Let sellers edit, renew before expiry and delete listings. | Stale listings are the category's biggest trust problem. | 7.12 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Listing management working | Edited listings re-enter screening where materially changed. |  | OBSERVED FROM RESEARCH
Phase 8 — Property Search & Filters | 8 | 8.1 | Search query builder | Translate filters to SQL | Build the service that turns the normalised filter object into a database query. | The core of the product; everything funnels through it. | 2.6,4.6 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Search service | All MVP filters combine correctly and return correct results. | Research §6.3 gives the full filter taxonomy. | OBSERVED FROM RESEARCH
Phase 8 — Property Search & Filters | 8 | 8.2 | Facet counts | Counts per filter option | Compute how many results each filter option would return. | Counts appear in titles, buttons and labels; wrong counts look broken. | 8.1 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Facet count service | Counts exclude the facet's own selection (standard faceted semantics). | Research §6.4 rule 3 — getting this wrong makes multi-select appear broken. | OBSERVED FROM RESEARCH
Phase 8 — Property Search & Filters | 8 | 8.3 | Sorting | Relevance, price, newest | Implement sort orders. | Users distrust results that ignore an explicit sort. | 8.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Sort working | Explicit sorts are pure — promoted listings never interleave. | Research §13.5 rule 2. | OBSERVED FROM RESEARCH
Phase 8 — Property Search & Filters | 8 | 8.4 | Relevance ranking v1 | Deterministic scoring | Score by match quality, freshness and listing completeness. | Machine learning needs traffic; start with rules you can explain. | 8.3 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Ranking function | Ranking is documented and reproducible. | Research §13.5 gives the formula. No paid boost exists yet in MVP. | OBSERVED FROM RESEARCH
Phase 8 — Property Search & Filters | 8 | 8.5 | Results page (SEO surface) | Server-rendered landing pages | Build the indexable results page at pretty URLs. | This is the main customer-acquisition channel. | 8.1,2.3,3.4 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Landing page route | Page renders server-side with correct H1, count and content. | Research §4.2/§16. | OBSERVED FROM RESEARCH
Phase 8 — Property Search & Filters | 8 | 8.6 | Results page (app surface) | Interactive filtered search | Build the /search interface with live filtering. | Different job from the SEO page: state, speed, no page reloads. | 8.5 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Interactive search | Filter change updates URL and results without losing scroll. | Research §6.4 rules 5 and 6. Must be noindex. | OBSERVED FROM RESEARCH
Phase 8 — Property Search & Filters | 8 | 8.7 | Filter state never lost | State preservation rules | Guarantee filters, scroll and results survive every interaction and error. | The incumbent's users specifically complain that filtering throws them back to home. | 8.6 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | State tests passing | No filter or sort action can navigate away or clear state, even on API error. | Research §18.2 — this is our clearest differentiation opportunity. | OBSERVED FROM RESEARCH
Phase 8 — Property Search & Filters | 8 | 8.8 | Applied filter chips | Removable chips in plain language | Show applied filters as chips with human-readable labels. | Users must see and undo what they applied. | 8.6 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Chips working | Chips read '₹40L–₹60L', not raw parameter values. | Research §6.4 rule 7. | OBSERVED FROM RESEARCH
Phase 8 — Property Search & Filters | 8 | 8.9 | Pagination (two kinds) | Path pages + infinite scroll | Path-based pages for crawlers, infinite scroll for the app surface. | The research found the incumbent deliberately runs both. | 8.5,8.6 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Both pagination modes | Crawlable /page/2 exists; app surface scrolls without breaking the footer. | Research §2.1/§6.1. | OBSERVED FROM RESEARCH
Phase 8 — Property Search & Filters | 8 | 8.10 | Non-linear range sliders | Budget and area controls | Make sliders denser where most inventory sits, with exact numeric inputs. | A linear 0–10cr slider makes the common 40–60L range untouchable. | 3.5,8.6 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Range controls | The dense band is selectable precisely; numeric entry also works. | Research §6.4 rule 8. | OBSERVED FROM RESEARCH
Phase 8 — Property Search & Filters | 8 | 8.11 | Zero-result recovery | Relaxation ladder | When nothing matches, widen budget, then radius, then config — and say so. | Property searches are over-constrained constantly. | 8.1,3.7 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Relaxation working | User is told what was relaxed and can undo it in one tap. | Research §13.6. | OBSERVED FROM RESEARCH
Phase 8 — Property Search & Filters | 8 | 8.12 | Search result caching | Cache counts and hot queries | Cache facet counts and popular queries in Redis. | Counts are expensive and change slowly. | 8.2 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Caching layer | Cached responses meet the search latency budget. | Research §18.4. | OBSERVED FROM RESEARCH
Phase 9 — Property Detail Page | 9 | 9.1 | PDP layout and sections | Build the detail page | Build the property page: gallery, header, details, amenities, location, seller. | Where the buying decision and the lead are made. | 3.4,4.1 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | PDP route | All MVP sections render server-side. | Research §7.2 gives the section order. | OBSERVED FROM RESEARCH
Phase 9 — Property Detail Page | 9 | 9.2 | Image gallery | Swipe, arrows, keyboard, lightbox | Build the gallery with full accessibility and lazy loading. | Photos are the most-used element on the page. | 3.3,9.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Gallery component | Keyboard and screen-reader accessible; only first image eager-loaded. | Research §14.6/§18.4. | OBSERVED FROM RESEARCH
Phase 9 — Property Detail Page | 9 | 9.3 | Sticky contact module | Always-reachable CTA | Sticky right rail on desktop, sticky bottom bar on mobile. | The user must never scroll into a state with no way to contact. | 9.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Sticky contact | Contact affordance visible at every scroll position. | Research §7.2. | OBSERVED FROM RESEARCH
Phase 9 — Property Detail Page | 9 | 9.4 | Key details grid | Structured specification block | Show type, status, floor, facing, age, furnishing, parking, areas. | These answer the questions that otherwise become wasted phone calls. | 9.1 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Details grid | Area basis (carpet/built-up/super) always labelled explicitly. | Research §12.3. | OBSERVED FROM RESEARCH
Phase 9 — Property Detail Page | 9 | 9.5 | Static location map | Show where the property is | Display a map with the property location and nearby landmarks. | Location is the primary decision factor. | 6.7,9.1 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Map on PDP | Map renders without blocking page load. | IN MVP (research §24 lists a map on the PDP). Interactive MAP SEARCH is a separate, deferred feature. | OBSERVED FROM RESEARCH
Phase 9 — Property Detail Page | 9 | 9.6 | Location privacy | Approximate pin for owner listings | Show an approximate circle rather than an exact pin until contact. | A safety consideration for residential owner listings. | 9.5 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Precision setting honoured | Owner listings render approximate location by default. | Research §6.5. | OBSERVED FROM RESEARCH
Phase 9 — Property Detail Page | 9 | 9.7 | Seller card | Who is advertising | Show seller type (owner/agent/builder), verification and member-since. | Posted-by is a top-three buyer filter and a trust signal. | 9.1 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Seller card | Seller type is unambiguous on every listing. | Research §7.1. | OBSERVED FROM RESEARCH
Phase 9 — Property Detail Page | 9 | 9.8 | Similar properties | Related listings block | Show comparable listings by locality, budget and configuration. | Keeps users on site after they reject a listing. | 8.1,9.1 | MEDIUM | NOT STARTED | UNASSIGNED | M · 3–5 days | Similar block | Loads asynchronously; never blocks first paint. | IN MVP per research §24 — but research §23 places it in a later phase. FLAGGED INCONSISTENCY: confirm. See D-14. | DECISION REQUIRED
Phase 9 — Property Detail Page | 9 | 9.9 | Save / shortlist | Favourite a property | Let users save listings, with optimistic UI. | The primary retention action for a months-long decision. | 5.8,9.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Save working | Unauthenticated save prompts login then completes automatically. | Research §9.1. | OBSERVED FROM RESEARCH
Phase 9 — Property Detail Page | 9 | 9.10 | Expired listing handling | 410 page with alternatives | When a listing is gone, serve a useful page rather than a dead end. | Leaving dead listings indexed is a slow SEO penalty and a bad experience. | 4.4,9.1 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Expired page | Returns HTTP 410 and shows similar active listings. | Research §16.5 rule 6. | OBSERVED FROM RESEARCH
Phase 10 — Leads / Enquiry / Contact Reveal | 10 | 10.1 | Inquiry data model | Model the lead explicitly | Build the INQUIRY entity with an explicit type (enquiry vs contact reveal). | This is the business. It must be a first-class, countable object from the start. | 4.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | INQUIRY table | Every lead type is recorded with source surface and timestamp. | Research §12.2 — the incumbent splits 'Queries' from 'Viewed Contact'. | OBSERVED FROM RESEARCH
Phase 10 — Leads / Enquiry / Contact Reveal | 10 | 10.2 | Enquiry form | Send a message to the seller | Let a buyer send a written enquiry. | The lower-friction half of the lead loop. | 10.1,9.3 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Enquiry working | Enquiry reaches the seller and appears in their inbox. |  | OBSERVED FROM RESEARCH
Phase 10 — Leads / Enquiry / Contact Reveal | 10 | 10.3 | OTP-gated contact reveal | Reveal phone after verification | Require OTP before showing seller contact details. | Verifies the buyer is real and creates the billable lead event. | 10.1,5.3 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Reveal flow working | Lead is recorded BEFORE the number is displayed. | Research §7.2 — this is the monetisable moment. | OBSERVED FROM RESEARCH
Phase 10 — Leads / Enquiry / Contact Reveal | 10 | 10.4 | Duplicate lead prevention | Deduplicate repeat reveals | Prevent the same user revealing the same listing repeatedly from creating new billable leads. | Revenue integrity: double-charging sellers destroys trust in your billing. | 10.3 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Dedupe key enforced | Repeat reveal within the window creates no new billable lead. | Research §12.2/§12.3. | OBSERVED FROM RESEARCH
Phase 10 — Leads / Enquiry / Contact Reveal | 10 | 10.5 | Reveal rate limiting | Cap reveals per user per day | Limit how many contacts one account can reveal daily. | Prevents scraping of seller contact details at scale. | 10.3 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Limits enforced | Limit is enforced server-side and logged. | Research §17.5. | OBSERVED FROM RESEARCH
Phase 10 — Leads / Enquiry / Contact Reveal | 10 | 10.6 | Seller lead inbox | Where sellers see their leads | Build the inbox showing buyer name, phone, email and interest. | Sellers' entire perceived value of the platform lives here. | 10.1,11.1 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Lead inbox | Leads are listed with status and are filterable by type. | Research §3.2 observed exactly these fields on the incumbent. | OBSERVED FROM RESEARCH
Phase 10 — Leads / Enquiry / Contact Reveal | 10 | 10.7 | Lead notifications | Alert the seller immediately | Notify sellers of new leads by SMS/email/push. | Response speed is the strongest determinant of lead conversion. | 10.6,4.11 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Notifications sending | Seller notified within a minute of a lead. |  | OBSERVED FROM RESEARCH
Phase 10 — Leads / Enquiry / Contact Reveal | 10 | 10.8 | Lead status tracking | Simple seller CRM | Let sellers mark leads new/contacted/qualified/closed/lost and add notes. | Turns a list into a working tool and drives repeat visits. | 10.6 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Status tracking | Status and notes persist per lead. | Research §12.2. | OBSERVED FROM RESEARCH
Phase 10 — Leads / Enquiry / Contact Reveal | 10 | 10.9 | Lead funnel analytics | Instrument the whole loop | Record every step: search, card click, PDP view, contact start, OTP, reveal. | You cannot price or improve what you do not measure. | 10.3,15.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Funnel events flowing | Every funnel step is queryable end to end. | Research §1.3 point 2 — instrument from day one even though nothing is charged yet. | OBSERVED FROM RESEARCH
Phase 10 — Leads / Enquiry / Contact Reveal | 10 | 10.10 | Contact detail protection | Prevent off-platform leakage | Ensure seller contact data is only released through the tracked reveal path. | Protects both the business model and user privacy. | 10.3 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | No contact leakage | Contact fields never appear in any API response before reveal. | Research §17.4. Verify API payloads, not just the UI. | OBSERVED FROM RESEARCH
Phase 11 — User Dashboard | 11 | 11.1 | Dashboard shell | Navigation and layout | Build the logged-in dashboard container. | Home base for both buyers and sellers. | 5.8,3.6 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Dashboard shell | Role-appropriate navigation renders. |  | PROPOSED
Phase 11 — User Dashboard | 11 | 11.2 | My listings | Seller listing management | List the seller's listings grouped by lifecycle state. | Sellers must see what is live, expiring, rejected or under review. | 4.4,11.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Listings view | All lifecycle states visible with a clear next action. | Research §3.2 observed these states on the incumbent. | OBSERVED FROM RESEARCH
Phase 11 — User Dashboard | 11 | 11.3 | Saved properties | Buyer shortlist | Show saved listings with removal and notes. | The buyer-side retention surface. | 9.9,11.1 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Saved view | Saved listings persist across devices when logged in. |  | OBSERVED FROM RESEARCH
Phase 11 — User Dashboard | 11 | 11.4 | Listing analytics | Views, saves, contacts per listing | Show sellers how their listing is performing. | Demonstrates value and creates the upsell conversation later. | 10.9,11.2 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Per-listing stats | Counts update daily and match the event data. | Research §3.2. | OBSERVED FROM RESEARCH
Phase 11 — User Dashboard | 11 | 11.5 | Notification preferences | Control what users receive | Let users choose channels and frequency. | Unwanted messages cause unsubscribes and complaints. | 10.7,11.1 | MEDIUM | NOT STARTED | UNASSIGNED | S · 1–2 days | Preference screen | Preferences are honoured by the notification service. |  | PROPOSED
Phase 12 — Admin Panel | 12 | 12.1 | Admin authentication | Separate, hardened admin access | Build admin login with stronger requirements than user login. | Admin accounts are the highest-value target on the platform. | 5.6 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Admin auth | Admin access requires a second factor and is IP-logged. | Research §17.5. See DECISIONS LOG for 2FA choice. | OBSERVED FROM RESEARCH
Phase 12 — Admin Panel | 12 | 12.2 | Admin listing management | View, edit, approve, reject | Let admins act on any listing. | Moderation cannot function without it. | 12.1,4.4 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Admin listing screens | Admin can approve, reject with reason, and unpublish. |  | OBSERVED FROM RESEARCH
Phase 12 — Admin Panel | 12 | 12.3 | Admin user management | View and act on accounts | Search users, view their listings and leads, suspend accounts. | Needed for abuse handling and support. | 12.1 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Admin user screens | Admin can suspend an account and see the effect immediately. |  | PROPOSED
Phase 12 — Admin Panel | 12 | 12.4 | Audit log | Record every admin action | Log who did what, to which record, and when — immutably. | Accountability, dispute resolution and a legal requirement in practice. | 12.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Audit log | Every admin state change writes an immutable log entry. | Research §17.5. | OBSERVED FROM RESEARCH
Phase 12 — Admin Panel | 12 | 12.5 | Admin dashboard | Operational overview | Show queue depth, new listings, reports and lead volume. | Daily operational awareness in one screen. | 12.2 | MEDIUM | NOT STARTED | UNASSIGNED | M · 3–5 days | Admin dashboard | Key operational counters visible and accurate. |  | PROPOSED
Phase 12 — Admin Panel | 12 | 12.6 | Location data admin | Manage the gazetteer | Let admins add and correct localities and societies. | Place data needs continuous correction; it is never finished. | 6.1,12.1 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Location admin | A new locality can be added and is immediately searchable. |  | PROPOSED
Phase 13 — Moderation & Trust | 13 | 13.1 | Moderation queue | Human review workflow | Build the queue where listings awaiting screening are reviewed. | The incumbent screens listings before publication; quality depends on it. | 12.2 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Moderation queue | Reviewer can approve or reject with a specific reason. | Research §8.1 observed the 'under screening' state. | OBSERVED FROM RESEARCH
Phase 13 — Moderation & Trust | 13 | 13.2 | Automated pre-checks | Machine checks before human review | Run duplicate detection, contact-info detection and price sanity automatically. | Humans should only see what machines cannot decide. | 13.1,7.7,7.9 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Auto-check pipeline | High-confidence listings auto-approve; the rest queue. | Research §8.2. | OBSERVED FROM RESEARCH
Phase 13 — Moderation & Trust | 13 | 13.3 | Rejection reasons | Specific, actionable feedback | Give sellers a precise reason and a path to fix and resubmit. | 'Rejected' with no reason generates support load and churn. | 13.1 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Reason catalogue | Every rejection carries a specific reason and a fix action. | Research §8.2. | OBSERVED FROM RESEARCH
Phase 13 — Moderation & Trust | 13 | 13.4 | Report listing | User abuse reporting | Let any user report a listing from the card and the detail page. | Your users are your largest moderation workforce. | 9.1,13.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Reporting working | Reports enter the moderation queue with an SLA timer. | Research §17.5. | OBSERVED FROM RESEARCH
Phase 13 — Moderation & Trust | 13 | 13.5 | Photo verification (tier 1) | Guided on-site photo capture | Let sellers verify by capturing live, geo-stamped photos at the property. | The trust badge that buyers value most. | 7.5,13.1 | HIGH | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Verification flow | Captured photo location matches the listing pin within tolerance. | Research §17.2 — tiered verification. MVP does TIER 1 ONLY. | OBSERVED FROM RESEARCH
Phase 13 — Moderation & Trust | 13 | 13.6 | Scope the trust badge honestly | Label exactly what is verified | State precisely what the badge proves — and what it does not. | The incumbent's own Terms limit their badge to existence and genuine photos, not ownership or price. Overclaiming creates liability. | 13.5 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Badge wording + tooltip | Badge scope is visible on hover/tap; never a bare 'Verified'. | Research §17.2 — the most transferable trust insight in the research. | OBSERVED FROM RESEARCH
Phase 13 — Moderation & Trust | 13 | 13.7 | Owner vs agent detection | Anti-gaming signals | Detect agents posing as owners using volume, phone reuse and image reuse. | 'Posted by owner' carries a trust premium that agents will try to claim. | 13.2 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Detection + appeal path | Reclassification is appealable with human review. | Research §17.3 — the incumbent visibly does this. | OBSERVED FROM RESEARCH
Phase 13 — Moderation & Trust | 13 | 13.8 | Stale listing expiry | Automatic expiry and renewal prompts | Expire listings after a set period unless the seller confirms availability. | Dead listings are the category's biggest trust problem and our stated differentiator. | 4.4,7.13 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Expiry job | Listings expire on schedule; sellers are prompted beforehand. | Research §20.5 point 2. | OBSERVED FROM RESEARCH
Phase 14 — SEO & Programmatic Pages | 14 | 14.1 | Implement SEO URL routes | Build the pretty-URL routes | Implement the route structure agreed in Phase 2. | The primary acquisition channel; must be right before any page is indexed. | 2.2,8.5 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Routes live | Every indexable page resolves at its final URL. | Research §16.5. Changing URLs after indexing costs ranking. | OBSERVED FROM RESEARCH
Phase 14 — SEO & Programmatic Pages | 14 | 14.2 | Canonical tags | One canonical URL per page | Set canonical tags so filtered variants point to their cleanest form. | Prevents duplicate-content dilution across thousands of filter combinations. | 14.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Canonicals correct | Each variant declares the intended canonical. | Research §16.5 rule 2 — where most property portals generate index bloat. | OBSERVED FROM RESEARCH
Phase 14 — SEO & Programmatic Pages | 14 | 14.3 | Index / noindex strategy | Decide what search engines may index | Allowlist which filter combinations are indexable; noindex everything else. | Uncontrolled indexation of every filter combination causes demotion. | 14.2 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Indexation rules | The /search app surface is noindex; allowlist enforced. | Research §16.5 rules 1–2. | OBSERVED FROM RESEARCH
Phase 14 — SEO & Programmatic Pages | 14 | 14.4 | Thin-content gating | Minimum inventory to be indexable | Only allow a landing page to be indexed above an inventory threshold. | Thousands of near-empty pages are an SEO liability, not an asset. | 14.3 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Gating rule live | Pages below threshold are noindex and link to their parent. | Research §16.5 rule 3 proposes ≥5 active listings. Threshold: DECISION REQUIRED. | DECISION REQUIRED
Phase 14 — SEO & Programmatic Pages | 14 | 14.5 | Dynamic titles and metadata | Templated titles with live counts | Generate titles including current inventory counts. | Observed on the incumbent; improves click-through and signals freshness. | 14.1,8.2 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Title templates | Counts come from cache; fallback never renders '0+'. | Research §16.2 — confirmed technique. | OBSERVED FROM RESEARCH
Phase 14 — SEO & Programmatic Pages | 14 | 14.6 | Structured data (JSON-LD) | Machine-readable page data | Add schema.org markup per page type. | Enables rich results and helps search engines understand the content. | 14.1 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | JSON-LD on all page types | Markup validates in Google's Rich Results Test. | Research §16.5 rule 4 lists the types per page. | OBSERVED FROM RESEARCH
Phase 14 — SEO & Programmatic Pages | 14 | 14.7 | Breadcrumbs | Visible + marked-up navigation | Add breadcrumbs mirroring the location hierarchy. | Helps users orient and search engines understand structure. | 14.1,6.1 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Breadcrumbs live | Visible on every page and marked up. | Research §16.5 rule 8. | OBSERVED FROM RESEARCH
Phase 14 — SEO & Programmatic Pages | 14 | 14.8 | XML sitemaps | Segmented sitemap index | Generate sitemaps split by content type, regenerated nightly. | How search engines discover pages at scale. | 14.3 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Sitemaps live | ≤50k URLs per file; accurate lastmod; expired listings removed. | Research §16.5 rule 5. | OBSERVED FROM RESEARCH
Phase 14 — SEO & Programmatic Pages | 14 | 14.9 | robots.txt | Crawler directives | Write robots.txt and reference the sitemap index. | Controls crawl budget. | 14.8 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | robots.txt live | Does not block anything present in the sitemap. |  | OBSERVED FROM RESEARCH
Phase 14 — SEO & Programmatic Pages | 14 | 14.10 | Internal linking clusters | Generated related links | Add nearby-locality, budget-band and config links to every landing page. | Distributes ranking authority into the long tail automatically. | 14.1,6.1 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Link clusters live | Generated from the gazetteer, not hand-written. | Research §16.5 rule 9. | OBSERVED FROM RESEARCH
Phase 14 — SEO & Programmatic Pages | 14 | 14.11 | Image SEO | Alt text and filenames | Generate meaningful alt text from listing attributes. | Image search is a real traffic source; also an accessibility requirement. | 9.2 | MEDIUM | NOT STARTED | UNASSIGNED | S · 1–2 days | Alt text generated | Alt reads '3 BHK living room, New Town' not 'image1'. | Research §14.11. | OBSERVED FROM RESEARCH
Phase 14 — SEO & Programmatic Pages | 14 | 14.12 | Search Console setup | Verify and monitor | Set up Google Search Console and monitor coverage and Core Web Vitals. | How you find out indexation is broken. | 14.8,19.5 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Search Console verified | Sitemaps submitted; coverage report reviewed weekly. |  | PROPOSED
Phase 14 — SEO & Programmatic Pages | 14 | 14.13 | Programmatic landing matrix | Generate pages at scale | Generate the city × type × budget × config page matrix from the gazetteer. | The research shows this is the incumbent's core acquisition machine. | 14.4,14.10 | HIGH | NOT STARTED | UNASSIGNED | XL · 2–4 weeks | Matrix generator | Pages generated and governed by the thin-content gate. | PHASE 14+ / POST-MVP scale-up. Generate the matrix, but govern it. Research §2.3/§16.5. | OBSERVED FROM RESEARCH
Phase 15 — Analytics & Tracking | 15 | 15.1 | Event tracking foundation | Define and capture events | Define the event schema and capture events server-side. | Owning your funnel data is non-negotiable for a lead business. | 4.7 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Event pipeline | Events captured with user, session and surface context. | Research §22 — start this alongside Phase 10, not after it. | OBSERVED FROM RESEARCH
Phase 15 — Analytics & Tracking | 15 | 15.2 | Funnel dashboards | Visualise the lead funnel | Build reporting for search → PDP → contact → reveal. | Tells you which step is leaking. | 15.1,10.9 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Funnel dashboard | Each MVP success metric is visible as a number. | Research §24 success criteria. | OBSERVED FROM RESEARCH
Phase 15 — Analytics & Tracking | 15 | 15.3 | Web analytics | Install analytics tooling | Add page-level analytics alongside the event pipeline. | Traffic sources and landing-page performance. | 15.1 | MEDIUM | NOT STARTED | UNASSIGNED | S · 1–2 days | Analytics live | Traffic by source and landing page is visible. | See DECISIONS LOG D-10. | DECISION REQUIRED
Phase 15 — Analytics & Tracking | 15 | 15.4 | Error monitoring | Capture and alert on errors | Install error tracking for frontend and backend. | You cannot fix errors you never hear about. | 1.9 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Error tracking live | Errors alert with stack trace and request context. | Research §18.4 — alert specifically on filter/sort errors. | OBSERVED FROM RESEARCH
Phase 15 — Analytics & Tracking | 15 | 15.5 | Search quality monitoring | Track zero-result and abandonment | Monitor searches returning nothing and searches abandoned. | Direct signal of catalogue gaps and filter problems. | 15.1,8.11 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Search quality report | Zero-result rate tracked by city and filter combination. |  | PROPOSED
Phase 15 — Analytics & Tracking | 15 | 15.6 | Real user performance monitoring | Field Core Web Vitals | Collect real-user performance data segmented by device and city. | Lab tests do not reflect users on mid-range phones. | 16.1 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | RUM live | Field LCP/CLS/INP visible at p75. | Research §18.4. | OBSERVED FROM RESEARCH
Phase 16 — Performance Optimization | 16 | 16.1 | Set performance budgets | Agree hard limits | Adopt the numeric budgets and wire them into CI. | Performance debt compounds; retrofitting speed is far more expensive. | 1.9 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Budgets in CI config | Build fails when a budget is breached. | Research §18.3 — see the PERFORMANCE sheet for exact numbers. | OBSERVED FROM RESEARCH
Phase 16 — Performance Optimization | 16 | 16.2 | Image optimisation | Modern formats and sizing | Serve AVIF/WebP with responsive sizes and correct lazy loading. | Images are the dominant byte cost in this product. | 7.6,9.2 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Image pipeline optimised | First card image eager with high priority; rest lazy. | Research §18.4. | OBSERVED FROM RESEARCH
Phase 16 — Performance Optimization | 16 | 16.3 | Prevent layout shift | Reserve space for all media | Set explicit aspect ratios on every image and media box. | Layout shift is the most irritating and most preventable defect. | 16.2 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | CLS within budget | CLS ≤ 0.05 on results and detail pages. | Research §18.3. | OBSERVED FROM RESEARCH
Phase 16 — Performance Optimization | 16 | 16.4 | JavaScript budget | Code splitting and deferral | Split by route; load heavy libraries only where used. | Every kilobyte costs time on mid-range Android phones. | 16.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | JS within budget | Search route JS ≤180KB gzip. | Research §18.4 — the map library is typically the largest dependency. | OBSERVED FROM RESEARCH
Phase 16 — Performance Optimization | 16 | 16.5 | Caching strategy | Edge, application and HTTP caching | Cache landing HTML at the edge; cache counts and hot data in Redis. | The cheapest performance win available. | 8.12 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Caching live | Cache hit rates measured; stale-while-revalidate configured. | Research §18.4. | OBSERVED FROM RESEARCH
Phase 16 — Performance Optimization | 16 | 16.6 | Database query tuning | Find and fix slow queries | Profile slow queries and add or correct indexes. | Search latency degrades non-linearly as data grows. | 8.1,4.6 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Query performance | Search API p95 ≤300ms at expected data volume. | Research §18.3. | OBSERVED FROM RESEARCH
Phase 16 — Performance Optimization | 16 | 16.7 | Synthetic performance tests | Lighthouse in CI | Run automated performance tests on representative routes. | Catches regressions before users do. | 16.1 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | CI performance gate | Five representative routes tested on every main-branch build. | Research §18.4. | OBSERVED FROM RESEARCH
Phase 17 — Security | 17 | 17.1 | Input validation everywhere | Validate on the server | Validate and sanitise every input server-side, never trusting the client. | Client-side validation is a convenience, not a control. | 4.8 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Validation layer | Every endpoint rejects malformed input with a clear error. | See SECURITY CHECKLIST sheet. | OBSERVED FROM RESEARCH
Phase 17 — Security | 17 | 17.2 | Authorization tests | Prove role boundaries | Test that each role cannot access what it should not. | Broken access control is the most common serious web vulnerability. | 5.6 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Authorization test suite | Cross-role access attempts fail in automated tests. |  | OBSERVED FROM RESEARCH
Phase 17 — Security | 17 | 17.3 | File upload security | Validate uploads | Enforce type, size and content checks; never trust filenames or declared types. | Uploads are a classic attack vector. | 4.10,7.5 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Upload controls | Non-image content is rejected even when renamed. | Research §17.5. | OBSERVED FROM RESEARCH
Phase 17 — Security | 17 | 17.4 | Rate limiting | Protect expensive endpoints | Rate-limit search, OTP, contact reveal and uploads per IP and per account. | Protects cost, data and availability. | 5.4,10.5 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Rate limits live | Limits enforced and observable in monitoring. | Research §17.5. | OBSERVED FROM RESEARCH
Phase 17 — Security | 17 | 17.5 | XSS protection | Escape all user content | Ensure user-supplied text can never execute as code. | Listing descriptions are user-supplied and rendered publicly. | 7.9 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | XSS controls | Script payloads in descriptions render as inert text. |  | OBSERVED FROM RESEARCH
Phase 17 — Security | 17 | 17.6 | SQL injection protection | Parameterised queries only | Use parameterised queries or an ORM everywhere; never string-concatenate SQL. | Still one of the most damaging vulnerabilities. | 4.1 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | No dynamic SQL | Code review confirms no concatenated SQL. |  | OBSERVED FROM RESEARCH
Phase 17 — Security | 17 | 17.7 | Security headers | CSP, HSTS and friends | Configure Content-Security-Policy, HSTS and related headers. | Cheap, high-value defence in depth. | 19.3 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Headers configured | Headers verified by an external scanner. | Research §17.5. | OBSERVED FROM RESEARCH
Phase 17 — Security | 17 | 17.8 | Secrets management | No secrets in code | Store secrets in a managed secret store with rotation. | Leaked credentials are among the most damaging incidents. | 1.7 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Secrets externalised | No secret in Git history; rotation documented. |  | OBSERVED FROM RESEARCH
Phase 17 — Security | 17 | 17.9 | PII protection | Protect personal data | Encrypt personal data at rest; restrict and log access to lead data. | Legal obligation and the highest-value data you hold. | 0.6,10.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | PII controls | Lead data access is least-privilege and fully audited. | Research §17.5. | OBSERVED FROM RESEARCH
Phase 17 — Security | 17 | 17.10 | Security review | Independent check before launch | Have someone other than the builder review the security posture. | You cannot review your own blind spots. | 17.1-17.9 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Security review report | All critical and high findings resolved before launch. |  | PROPOSED
Phase 18 — Testing & QA | 18 | 18.1 | Testing strategy | Decide what to test and how | Agree the mix of unit, integration and end-to-end tests. | Testing everything is impossible; testing nothing is fatal. | 1.9 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Test strategy document | Written strategy with coverage expectations. | See TESTING & QA sheet. | PROPOSED
Phase 18 — Testing & QA | 18 | 18.2 | Unit tests | Test business logic | Test pricing, quota, ranking, validation and state transitions. | These are where silent logic errors hide. | 18.1 | HIGH | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Unit test suite | Core business rules covered; suite runs in CI. |  | PROPOSED
Phase 18 — Testing & QA | 18 | 18.3 | API integration tests | Test endpoints against a real database | Test each endpoint with a real database and real auth. | Catches the integration errors unit tests cannot. | 18.1,4.7 | HIGH | NOT STARTED | UNASSIGNED | L · 1–2 weeks | API test suite | All MVP endpoints covered including failure cases. |  | PROPOSED
Phase 18 — Testing & QA | 18 | 18.4 | End-to-end tests | Test the critical journeys | Automate the journeys in the USER FLOWS sheet. | These are the flows that must never break. | 18.1,10.3 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | E2E suite | Search, post, contact and moderation journeys pass automatically. |  | PROPOSED
Phase 18 — Testing & QA | 18 | 18.5 | Search and filter tests | Prove filter correctness | Test filter combinations, counts, sort purity and state preservation. | The incumbent's most-complained-about area; our differentiator. | 8.7,18.1 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Search test suite | Filter change never loses state; counts verified correct. | Research §18.2. | OBSERVED FROM RESEARCH
Phase 18 — Testing & QA | 18 | 18.6 | Responsive and device testing | Test on real devices | Test on real mid-range Android and iOS devices, not just a resized browser. | Emulators hide real performance and touch problems. | 3.9 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Device test report | Key journeys verified on at least one real low/mid-range Android. | Research §18.3. | OBSERVED FROM RESEARCH
Phase 18 — Testing & QA | 18 | 18.7 | Accessibility testing | Automated + manual checks | Run automated checks and test keyboard and screen-reader journeys. | Automated tools catch only a fraction of real issues. | 3.8 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Accessibility report | Search and contact journeys completable by keyboard alone. | Research §14.11. | OBSERVED FROM RESEARCH
Phase 18 — Testing & QA | 18 | 18.8 | Cross-browser testing | Test the main browsers | Verify on Chrome, Safari, Firefox and Edge. | Safari in particular behaves differently. | 18.4 | HIGH | NOT STARTED | UNASSIGNED | S · 1–2 days | Browser matrix signed off | No blocking defect in any supported browser. |  | PROPOSED
Phase 18 — Testing & QA | 18 | 18.9 | Load testing | Test under realistic traffic | Simulate expected peak load against search and detail pages. | Finds the breaking point before users do. | 16.6 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Load test report | System holds latency budgets at projected peak. |  | PROPOSED
Phase 18 — Testing & QA | 18 | 18.10 | User acceptance testing | Real people, real tasks | Have real owners and buyers attempt the core tasks while you watch. | Reveals confusion no automated test can. | 18.4 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | UAT findings log | At least 5 external users complete posting and search unaided. | The posting flow target is ≤8 minutes on mobile (research §24). | OBSERVED FROM RESEARCH
Phase 19 — Deployment | 19 | 19.1 | Provision environments | Dev, staging, production | Create three isolated environments with separate data. | Never test on production data. | 2.9 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Three environments | Staging mirrors production configuration. |  | PROPOSED
Phase 19 — Deployment | 19 | 19.2 | Infrastructure as code | Reproducible infrastructure | Define infrastructure in code rather than clicking consoles. | Makes environments reproducible and recoverable. | 19.1 | HIGH | NOT STARTED | UNASSIGNED | L · 1–2 weeks | IaC repository | An environment can be rebuilt from code. | Research §22 proposes Terraform. Can be deferred if it delays launch — record the decision. | PROPOSED
Phase 19 — Deployment | 19 | 19.3 | Domain, DNS and SSL | Make the site reachable and secure | Configure the domain, DNS records and TLS certificates. | Required before anything is publicly usable. | 0.7,19.1 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Domain live over HTTPS | HTTPS works, HTTP redirects, certificate auto-renews. |  | PROPOSED
Phase 19 — Deployment | 19 | 19.4 | CDN configuration | Edge caching and protection | Configure the CDN for assets, HTML caching and basic protection. | Performance and resilience. | 19.3 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | CDN live | Static assets served from edge with correct cache headers. | Research §18.4. | OBSERVED FROM RESEARCH
Phase 19 — Deployment | 19 | 19.5 | Deployment pipeline | Automated deploys | Automate deployment to staging and production. | Manual deploys are where outages come from. | 1.9,19.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | CD pipeline | A merge to main deploys to staging automatically. |  | PROPOSED
Phase 19 — Deployment | 19 | 19.6 | Database migration process | Safe schema changes in production | Define how migrations run at deploy time, including rollback. | A failed migration can take the whole site down. | 4.2,19.5 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Migration process | Migrations run automatically and can be rolled back. |  | PROPOSED
Phase 19 — Deployment | 19 | 19.7 | Backups and restore drill | Prove you can recover | Configure automated backups and actually practise a restore. | An untested backup is not a backup. | 19.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Restore drill completed | A real restore to a clean environment has been performed. | Do not skip the drill. This is the item most often assumed and never verified. | PROPOSED
Phase 19 — Deployment | 19 | 19.8 | Monitoring and alerting | Know when something breaks | Set up uptime, latency and error-rate alerts with someone receiving them. | Alerts nobody receives are decoration. | 15.4,19.5 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Alerts configured | A simulated outage produces an alert to a real person. |  | PROPOSED
Phase 19 — Deployment | 19 | 19.9 | Logging | Centralised, searchable logs | Aggregate application logs with request IDs. | You cannot debug production without logs. | 4.8,19.1 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Log aggregation | A request can be traced end to end by its ID. |  | PROPOSED
Phase 19 — Deployment | 19 | 19.10 | Rollback procedure | Undo a bad deploy fast | Document and test how to revert to the previous version. | Speed of recovery matters more than avoiding every failure. | 19.5 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Rollback tested | A rollback has been performed successfully on staging. |  | PROPOSED
Phase 19 — Deployment | 19 | 19.11 | Disaster recovery plan | Plan for the worst case | Document recovery objectives and the steps to restore service. | Decide this calmly now, not during an incident. | 19.7 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | DR plan document | Written RTO/RPO with named steps and owners. |  | PROPOSED
Phase 20 — Production Launch | 20 | 20.1 | Legal pages live | Terms, privacy, disclaimers | Publish reviewed T&C, privacy policy, cookie notice and listing disclaimers. | Legally required before accepting user data. | 0.6 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Legal pages published | Reviewed by a lawyer and linked from every page. | Research §17.5 — include the honest verification-scope disclaimer. | OBSERVED FROM RESEARCH
Phase 20 — Production Launch | 20 | 20.2 | Seed launch inventory | Load the first listings | Reach the minimum listing count before opening to buyers. | An empty marketplace fails its first impression permanently. | 0.8,7.12 | CRITICAL | NOT STARTED | UNASSIGNED | XL · 2–4 weeks | Launch inventory live | Target listing count met across the launch cities. | Research §24 proposes ≥2,000 listings across 3 cities. | OBSERVED FROM RESEARCH
Phase 20 — Production Launch | 20 | 20.3 | Pre-launch checklist | Work through every item | Complete the LAUNCH CHECKLIST sheet. | Catches the small omissions that embarrass a launch. | 18.10,19.11 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Signed-off checklist | Every launch checklist item is DONE or consciously DEFERRED. | See LAUNCH CHECKLIST sheet. | USER REQUIREMENT
Phase 20 — Production Launch | 20 | 20.4 | Production smoke tests | Verify the live site | Run the critical journeys against production after deploy. | Staging passing does not prove production works. | 20.3 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Smoke test pass | Post, search, contact and OTP verified on production. |  | PROPOSED
Phase 20 — Production Launch | 20 | 20.5 | Soft launch | Limited release first | Open to a small audience before any public announcement. | Finds real-world problems at low reputational cost. | 20.4 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Soft launch completed | Issues from the limited release triaged and resolved. |  | PROPOSED
Phase 20 — Production Launch | 20 | 20.6 | Public launch | Open and announce | Remove restrictions and begin acquisition. | The point of everything above. | 20.5 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Site publicly live | Site is open, monitored and staffed for support. |  | PROPOSED
Phase 20 — Production Launch | 20 | 20.7 | Launch monitoring window | Watch closely for 72 hours | Have someone actively watching errors, performance and leads. | Launch problems appear in the first hours. | 20.6,19.8 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Monitoring log | 72-hour watch completed with issues logged. |  | PROPOSED
Phase 21 — Post-launch Improvements | 21 | 21.1 | Triage launch feedback | Collect and prioritise | Gather user feedback and support issues into one prioritised list. | Real users find what testing missed. | 20.7 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Prioritised issue list | Every reported issue triaged with a severity. |  | PROPOSED
Phase 21 — Post-launch Improvements | 21 | 21.2 | Fix critical defects | Immediate fixes | Fix anything blocking the core journeys. | Broken core journeys destroy early word of mouth. | 21.1 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Defects resolved | No open critical defect on a core journey. |  | PROPOSED
Phase 21 — Post-launch Improvements | 21 | 21.3 | Measure against targets | Compare to success metrics | Check actual numbers against the launch targets. | Tells you whether to optimise or to change direction. | 15.2,20.7 | CRITICAL | NOT STARTED | UNASSIGNED | S · 1–2 days | Metrics review | Each MVP success metric reported as met or missed. | Research §24. | OBSERVED FROM RESEARCH
Phase 21 — Post-launch Improvements | 21 | 21.4 | Improve listing quality | Act on duplicate and staleness data | Tune duplicate detection and expiry based on real data. | Our stated differentiator; needs real data to tune. | 13.2,13.8 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Quality metrics improved | Duplicate rate in results below target. | Research §24 target: <2%. | OBSERVED FROM RESEARCH
Phase 21 — Post-launch Improvements | 21 | 21.5 | Conversion optimisation | Fix the weakest funnel step | Improve whichever funnel step is furthest from target. | Focused effort beats broad tinkering. | 21.3 | HIGH | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Funnel improvement | Measurable improvement in the targeted step. |  | PROPOSED
Phase 21 — Post-launch Improvements | 21 | 21.6 | SEO indexation review | Check what actually got indexed | Review coverage, fix crawl errors and thin pages. | Indexation problems are invisible without checking. | 14.12 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Coverage report reviewed | Indexed page count matches intent; errors resolved. |  | PROPOSED
Phase 22 — Mobile App Preparation | 22 | 22.1 | Decide PWA vs native | Choose the mobile strategy | Decide whether to improve the web app or build native apps. | Native apps are two more codebases with release cycles; the decision is expensive either way. | 21.3 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Recorded decision | Decision recorded with the evidence behind it. | Research §20.3 suggests a PWA covers v1. See DECISIONS LOG D-15. Do not decide before launch data exists. | DECISION REQUIRED
Phase 22 — Mobile App Preparation | 22 | 22.2 | Progressive Web App | Installable web app | Add a manifest, service worker and offline shell. | Gets most app benefits without a second codebase. | 22.1 | HIGH | NOT STARTED | UNASSIGNED | L · 1–2 weeks | PWA installable | App installs to home screen and opens offline shell. | PROPOSED as the step before native. | PROPOSED
Phase 22 — Mobile App Preparation | 22 | 22.3 | Mobile push notifications | Web push for leads and alerts | Enable push for lead alerts and saved-search matches. | Lead response speed is the seller's core value. | 22.2,10.7 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Push working | Seller receives a push within a minute of a lead. |  | PROPOSED
Phase 22 — Mobile App Preparation | 22 | 22.4 | API readiness for mobile | Stabilise and version the API | Ensure the API is versioned and documented well enough for a separate client. | A native app is just another API consumer; the API must be ready first. | 4.9 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Versioned API + docs | API documented and versioned; breaking changes have a policy. |  | PROPOSED
Phase 22 — Mobile App Preparation | 22 | 22.5 | Mobile analytics plan | Define app-specific events | Plan how app usage will be measured. | App funnels differ from web funnels. | 15.1,22.1 | MEDIUM | NOT STARTED | UNASSIGNED | S · 1–2 days | Mobile event plan | Event schema extended for app surfaces. |  | PROPOSED
Phase 23 — Native Mobile App | 23 | 23.1 | Choose mobile technology | Native, React Native or Flutter | Choose the mobile implementation approach. | Determines cost, team and long-term maintenance. | 22.1 | CRITICAL | NOT STARTED | UNASSIGNED | M · 3–5 days | Recorded decision | Decision recorded with cost and team implications. | DECISION REQUIRED. Do not decide until 22.1 is settled with real data. | DECISION REQUIRED
Phase 23 — Native Mobile App | 23 | 23.2 | Mobile app design | Adapt the design system | Adapt components to platform conventions. | Web patterns transplanted directly feel wrong on mobile. | 23.1,3.1 | HIGH | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Mobile design system | Key screens designed for both platforms. |  | PROPOSED
Phase 23 — Native Mobile App | 23 | 23.3 | Build core app screens | Search, detail, save, contact | Build the buyer journey in the app. | The highest-volume app use case. | 23.2,22.4 | CRITICAL | NOT STARTED | UNASSIGNED | XL · 2–4 weeks | App buyer journey | Buyer can search, view and contact from the app. |  | PROPOSED
Phase 23 — Native Mobile App | 23 | 23.4 | In-app posting and verification | Seller flows with camera | Build posting and the guided photo-verification capture. | Verification genuinely needs a camera; this is the app's strongest justification. | 23.3,13.5 | HIGH | NOT STARTED | UNASSIGNED | XL · 2–4 weeks | App seller flows | Seller can post and verify from the app. | Research §17.2 — the incumbent's verification is app-based for this reason. | OBSERVED FROM RESEARCH
Phase 23 — Native Mobile App | 23 | 23.5 | App store release | Publish to stores | Prepare listings, screenshots, privacy declarations and submit. | Store review takes time and can reject; plan for iterations. | 23.3 | CRITICAL | NOT STARTED | UNASSIGNED | L · 1–2 weeks | Apps published | Both apps live and installable. |  | PROPOSED
Phase 23 — Native Mobile App | 23 | 23.6 | App release process | Versioning and staged rollout | Define how updates ship, including staged rollout and forced upgrade. | Mobile users do not all update; you must support older versions. | 23.5 | HIGH | NOT STARTED | UNASSIGNED | M · 3–5 days | Release process | Staged rollout and minimum-version enforcement working. |  | PROPOSED

## PHASES
PHASES — the whole project at a glance
Progress is calculated automatically from the MASTER ROADMAP sheet. Do the phases roughly in order: later phases depend on earlier ones.
Phase No. | Phase Name | Objective | Main Deliverables | Dependencies | Estimated Duration | Status | Completion %
0 | Phase 0 — Research & Product Definition | Understand the market and decide exactly what to build. | Research spec; business-model statement; launch scope; MVP boundary; success metrics; legal review; supply plan | None | 2–3 weeks | IN PROGRESS | 25%
1 | Phase 1 — Project Foundation | Get a working, version-controlled, automatically-checked codebase. | Repository; branch policy; scaffolds; linting; CI; local Docker setup | Phase 0 | 1–2 weeks | NOT STARTED | 0%
2 | Phase 2 — Product Architecture | Decide the shape of the system before building any of it. | Module map; URL architecture; rendering strategy; filter object; ID strategy; architecture document | Phase 1 | 1–2 weeks | NOT STARTED | 0%
3 | Phase 3 — Design System & UI/UX | Build an original, consistent, accessible visual language. | Design tokens; component library; property card; search UI; states; responsive rules; wireframes | Phase 1 | 3–4 weeks | NOT STARTED | 0%
4 | Phase 4 — Database & Backend Foundation | Create the data model and the backend skeleton. | Schema v1; migrations; seed data; indexes; API conventions; object storage; job queue | Phase 2 | 2–3 weeks | NOT STARTED | 0%
5 | Phase 5 — User Authentication | Let people register and log in securely by phone. | OTP login; sessions; roles; authorization; profile; account deletion | Phase 4 | 2 weeks | NOT STARTED | 0%
6 | Phase 6 — Location & Property Data | Build the place hierarchy everything else depends on. | Gazetteer; aliases; slugs; typeahead; PostGIS; property-type and amenity taxonomies | Phase 4 | 2–3 weeks | NOT STARTED | 0%
7 | Phase 7 — Seller / Owner Property Posting | Let an owner list a property from a phone in under 8 minutes. | Posting wizard; autosave; media pipeline; sanitisation; completeness score; publish + quota | Phases 5, 6 | 3–4 weeks | NOT STARTED | 0%
8 | Phase 8 — Property Search & Filters | Let buyers find what they want, fast, without losing state. | Search service; facets; sorting; ranking; both result surfaces; pagination; zero-result recovery | Phases 6, 7 | 3–4 weeks | NOT STARTED | 0%
9 | Phase 9 — Property Detail Page | Answer the buyer's questions and lead them to contact. | PDP; gallery; sticky contact; details; static map; seller card; save | Phases 3, 8 | 2–3 weeks | NOT STARTED | 0%
10 | Phase 10 — Leads / Enquiry / Contact Reveal | Close the loop: deliver a measured lead to the seller. | Inquiry model; enquiry form; OTP reveal; dedupe; rate limits; lead inbox; notifications; funnel events | Phases 5, 9 | 2–3 weeks | NOT STARTED | 0%
11 | Phase 11 — User Dashboard | Give both sides a home base. | Dashboard shell; my listings; saved properties; listing analytics; notification preferences | Phases 7, 10 | 1–2 weeks | NOT STARTED | 0%
12 | Phase 12 — Admin Panel | Give operators the tools to run the marketplace. | Admin auth; listing and user management; audit log; admin dashboard; location admin | Phase 5 | 2 weeks | NOT STARTED | 0%
13 | Phase 13 — Moderation & Trust | Keep listing quality high and users safe. | Moderation queue; automated pre-checks; rejection reasons; reporting; verification tier 1; expiry | Phase 12 | 2–3 weeks | NOT STARTED | 0%
14 | Phase 14 — SEO & Programmatic Pages | Turn the URL architecture into an acquisition channel. | SEO routes; canonicals; indexation rules; thin-content gate; metadata; JSON-LD; sitemaps; internal links | Phases 8, 9 | 2–3 weeks (MVP) + ongoing | NOT STARTED | 0%
15 | Phase 15 — Analytics & Tracking | Know what is happening and why. | Event pipeline; funnel dashboards; web analytics; error monitoring; search-quality and performance monitoring | Phase 10 | 1–2 weeks | NOT STARTED | 0%
16 | Phase 16 — Performance Optimization | Be measurably faster than the incumbent. | Budgets in CI; image and JS optimisation; caching; query tuning; synthetic tests | Phases 8, 9 | 2 weeks | NOT STARTED | 0%
17 | Phase 17 — Security | Protect users, data and the business model. | Validation; authorization tests; upload security; rate limits; XSS/SQLi; headers; secrets; PII; review | Phases 5, 10 | 2 weeks | NOT STARTED | 0%
18 | Phase 18 — Testing & QA | Prove it works before real users find out it does not. | Test strategy; unit/API/E2E suites; search tests; device, accessibility, browser, load and user testing | Phases 10, 13 | 3 weeks | NOT STARTED | 0%
19 | Phase 19 — Deployment | Make it possible to ship safely and recover quickly. | Environments; IaC; domain/DNS/SSL; CDN; CD pipeline; migrations; backups; monitoring; rollback; DR | Phase 4 | 2 weeks | NOT STARTED | 0%
20 | Phase 20 — Production Launch | Go live with enough inventory to be useful. | Legal pages; launch inventory; launch checklist; smoke tests; soft launch; public launch; watch window | Phases 18, 19 | 2 weeks + inventory build | NOT STARTED | 0%
21 | Phase 21 — Post-launch Improvements | Fix what reality exposed and improve the weakest step. | Feedback triage; defect fixes; metric review; quality tuning; conversion work; indexation review | Phase 20 | Ongoing | NOT STARTED | 0%
22 | Phase 22 — Mobile App Preparation | Decide and prepare for mobile, based on real data. | PWA vs native decision; PWA; push; API versioning; mobile analytics plan | Phase 21 | 2–4 weeks | NOT STARTED | 0%
23 | Phase 23 — Native Mobile App | Build native apps only if the data justifies them. | Technology decision; mobile design; buyer journey; posting + verification; store release; release process | Phase 22 | 8–12 weeks | NOT STARTED | 0%

## MVP CHECKLIST
MVP CHECKLIST — what to build now, and what NOT to build yet
Filter MVP? = MVP for launch scope. Filter MVP? = FUTURE to see what is deliberately deferred and when it returns. This sheet is your defence against scope creep.
Feature | Category | MVP? | Priority | Reason | Dependencies | Status | Future Phase | Source
Intent tabs (Buy / Rent) | Search | MVP | CRITICAL | Buy and Rent are different products with different filters and economics; separating them is foundational. | Phase 6 | NOT STARTED | — | OBSERVED FROM RESEARCH
Multi-select location typeahead | Search | MVP | CRITICAL | Real users search several localities at once; the entire funnel starts here. | Gazetteer (6.1) | NOT STARTED | — | OBSERVED FROM RESEARCH
Faceted filters (budget, BHK, type, area, furnishing, status, posted-by, verified) | Search | MVP | CRITICAL | Core of the product. Research §6.3 defines the full set. | Phase 8 | NOT STARTED | — | OBSERVED FROM RESEARCH
Sorting (relevance, price up/down, newest) | Search | MVP | CRITICAL | Users distrust results that ignore an explicit sort. | Phase 8 | NOT STARTED | — | OBSERVED FROM RESEARCH
Filter state never lost on change or error | Search | MVP | CRITICAL | The incumbent's most-complained-about failure. This is our differentiator. | Phase 8 | NOT STARTED | — | OBSERVED FROM RESEARCH
Result cards | Property | MVP | CRITICAL | The unit of comparison; drives click-through. | Phase 3 | NOT STARTED | — | OBSERVED FROM RESEARCH
SEO landing pages with path pagination | SEO | MVP | CRITICAL | Primary acquisition channel; cannot be retrofitted. | Phase 14 | NOT STARTED | — | OBSERVED FROM RESEARCH
Property detail page | Property | MVP | CRITICAL | Where the decision and the lead happen. | Phase 9 | NOT STARTED | — | OBSERVED FROM RESEARCH
Image gallery | Property | MVP | CRITICAL | Photos are the most-used element on the page. | Phase 9 | NOT STARTED | — | OBSERVED FROM RESEARCH
Static location map on the detail page | Property | MVP | HIGH | Location is the primary decision factor. NOTE: this is a static map, NOT interactive map search. | Phase 6, 9 | NOT STARTED | — | OBSERVED FROM RESEARCH
Save / shortlist | Buyer | MVP | CRITICAL | Primary retention action in a months-long decision. | Phase 9 | NOT STARTED | — | OBSERVED FROM RESEARCH
Enquiry form | Leads | MVP | CRITICAL | Lower-friction half of the lead loop. | Phase 10 | NOT STARTED | — | OBSERVED FROM RESEARCH
OTP-gated contact reveal | Leads | MVP | CRITICAL | The monetisable event. Must be instrumented from day one. | Phase 5, 10 | NOT STARTED | — | OBSERVED FROM RESEARCH
Similar properties | Buyer | MVP | MEDIUM | Research §24 lists this in MVP; research §23 places it in a later phase. CONFLICT — see DECISIONS LOG D-14. | Phase 8, 9 | NOT STARTED | Possibly v1.1 | DECISION REQUIRED
Responsive web / PWA-ready | Frontend | MVP | CRITICAL | Majority of traffic will be mobile. | Phase 3 | NOT STARTED | — | OBSERVED FROM RESEARCH
OTP registration with role | Authentication | MVP | CRITICAL | Entry point to every authenticated action. | Phase 5 | NOT STARTED | — | OBSERVED FROM RESEARCH
Posting wizard with autosave | Seller/Owner | MVP | CRITICAL | Supply must exist before demand can be tested. | Phase 7 | NOT STARTED | — | OBSERVED FROM RESEARCH
Photo upload (cap ~30) | Seller/Owner | MVP | CRITICAL | Photos are the highest-impact listing field. Research proposes a conservative cap. | Phase 7 | NOT STARTED | — | OBSERVED FROM RESEARCH
Draft / preview / publish | Seller/Owner | MVP | CRITICAL | Preview builds seller confidence and catches errors. | Phase 7 | NOT STARTED | — | OBSERVED FROM RESEARCH
Listing lifecycle states | Property | MVP | CRITICAL | Lifecycle is a product feature, not an implementation detail. | Phase 4 | NOT STARTED | — | OBSERVED FROM RESEARCH
Seller dashboard (listings, leads, basic analytics) | Seller/Owner | MVP | CRITICAL | Where the seller's perceived value lives. | Phase 11 | NOT STARTED | — | OBSERVED FROM RESEARCH
Edit / renew / delete listing | Seller/Owner | MVP | HIGH | Stale listings are the category's biggest trust problem. | Phase 7 | NOT STARTED | — | OBSERVED FROM RESEARCH
Free listing quota enforcement | Billing/Monetization | MVP | CRITICAL | Foundation for all later monetisation. | Phase 7 | NOT STARTED | — | OBSERVED FROM RESEARCH
Moderation queue + automated pre-checks | Moderation | MVP | CRITICAL | Listing quality is the product. | Phase 13 | NOT STARTED | — | OBSERVED FROM RESEARCH
Duplicate detection (image hash + text) | Moderation | MVP | CRITICAL | Duplicates are the top user complaint in this category. | Phase 7, 13 | NOT STARTED | — | OBSERVED FROM RESEARCH
Contact-info detection and sanitisation | Moderation | MVP | CRITICAL | Protects the lead model and prevents off-platform scams. | Phase 7 | NOT STARTED | — | OBSERVED FROM RESEARCH
Report listing | Moderation | MVP | CRITICAL | Users are your largest moderation workforce. | Phase 13 | NOT STARTED | — | OBSERVED FROM RESEARCH
Photo verification tier 1 | Moderation | MVP | HIGH | The trust badge buyers value most. Tier 1 only in MVP. | Phase 13 | NOT STARTED | Tiers 2–5 later | OBSERVED FROM RESEARCH
Admin console | Admin | MVP | CRITICAL | Moderation cannot function without it. | Phase 12 | NOT STARTED | — | OBSERVED FROM RESEARCH
Audit log | Admin | MVP | CRITICAL | Accountability and dispute resolution. | Phase 12 | NOT STARTED | — | OBSERVED FROM RESEARCH
Event analytics / lead funnel | Analytics | MVP | CRITICAL | You cannot price or improve what you do not measure. | Phase 15 | NOT STARTED | — | OBSERVED FROM RESEARCH
Error monitoring | Analytics | MVP | CRITICAL | You cannot fix errors you never hear about. | Phase 15 | NOT STARTED | — | OBSERVED FROM RESEARCH
Enforced performance budgets | Performance | MVP | CRITICAL | Performance debt compounds; enforce before launch. | Phase 16 | NOT STARTED | — | OBSERVED FROM RESEARCH
JSON-LD, sitemaps, canonicals | SEO | MVP | CRITICAL | Basic technical SEO; cheap now, expensive later. | Phase 14 | NOT STARTED | — | OBSERVED FROM RESEARCH
Legal pages (T&C, privacy) | Content | MVP | CRITICAL | Legally required before accepting user data. | Phase 0, 20 | NOT STARTED | — | OBSERVED FROM RESEARCH
Interactive map search (pan / bounding box) | Search | FUTURE | HIGH | Valuable but expensive; the map library is usually the largest frontend dependency. | Phase 8 | NOT STARTED | v1.1 | OBSERVED FROM RESEARCH
Saved-search alerts | Buyer | FUTURE | HIGH | Best retention mechanism, but needs inventory volume to be useful. | Phase 8, 10 | NOT STARTED | v1.1 | OBSERVED FROM RESEARCH
Comparison view | Buyer | FUTURE | MEDIUM | Buyers build spreadsheets manually today — a real differentiator, but not launch-critical. | Phase 9 | NOT STARTED | v1.1 | OBSERVED FROM RESEARCH
Locality reviews & ratings | Content | FUTURE | MEDIUM | Needs a user base first. An empty review section actively damages trust. | Phase 6 | NOT STARTED | v2.0 | OBSERVED FROM RESEARCH
Price trends / appreciation data | Content | FUTURE | MEDIUM | Needs years of history plus statistical rigour. Thin-sample trends destroy credibility. | Phase 6 | NOT STARTED | v2.0 | OBSERVED FROM RESEARCH
Projects (new construction) | Property | FUTURE | MEDIUM | A full second data model: configurations, floor plans, payment plans. | Phase 6 | NOT STARTED | v1.5 | OBSERVED FROM RESEARCH
Builder profiles & microsites | Builder | FUTURE | MEDIUM | High advertising value, but requires the project model first. | Projects | NOT STARTED | v1.5 | OBSERVED FROM RESEARCH
Agent profiles & bulk tools | Agent/Dealer | FUTURE | HIGH | Agents are the paying cohort — but only once monetisation exists. | Phase 11 | NOT STARTED | v1.4 | OBSERVED FROM RESEARCH
Payments & subscriptions | Billing/Monetization | FUTURE | HIGH | Do not monetise before proving lead quality. Charging on thin liquidity kills marketplaces. | Phase 10, 15 | NOT STARTED | v1.3 | OBSERVED FROM RESEARCH
Featured / promoted listings | Billing/Monetization | FUTURE | MEDIUM | Requires payments and a bounded, labelled boost design. | Payments | NOT STARTED | v1.3 | OBSERVED FROM RESEARCH
Phone number masking | Leads | FUTURE | HIGH | Strong differentiator (not evidenced at the incumbent) but needs telephony integration and per-minute cost. | Phase 10 | NOT STARTED | v1.2 | OBSERVED FROM RESEARCH
Home loan marketplace / EMI tools | Content | FUTURE | MEDIUM | Highest-value adjacent lead type; EMI calculator is cheap and could come earlier. | Phase 9 | NOT STARTED | v2.2 | OBSERVED FROM RESEARCH
Native mobile apps | Frontend | FUTURE | MEDIUM | Two more codebases and release cycles. A PWA covers v1. | Phase 22 | NOT STARTED | v3.0 | OBSERVED FROM RESEARCH
Multi-language | Frontend | FUTURE | LOW | Significant complexity across content, SEO and UI. | Phase 3 | NOT STARTED | v3.0 | OBSERVED FROM RESEARCH
Commercial property category | Property | FUTURE | MEDIUM | Adds a full field schema, filter set and landing-page family. | Phase 6 | NOT STARTED | v1.4 | OBSERVED FROM RESEARCH
PG / co-living category | Property | FUTURE | MEDIUM | Different field set (gender, meals, sharing) and different economics. | Phase 6 | NOT STARTED | v1.4 | OBSERVED FROM RESEARCH
Plots / land category | Property | FUTURE | MEDIUM | Different field set (dimensions, boundary wall) and no BHK concept. | Phase 6 | NOT STARTED | v1.4 | OBSERVED FROM RESEARCH
Advanced recommendations / personalisation | Buyer | FUTURE | LOW | Needs traffic before it can learn anything useful. | Phase 15 | NOT STARTED | v2.1 | OBSERVED FROM RESEARCH
Learning-to-rank relevance | Search | FUTURE | LOW | Needs click and contact data at volume. | Phase 15 | NOT STARTED | v2.1 | OBSERVED FROM RESEARCH
OpenSearch / dedicated search cluster | Search | FUTURE | MEDIUM | Defer until measured need: ~100k listings or facet latency over budget. | Phase 8 | NOT STARTED | v2.0 | OBSERVED FROM RESEARCH
Locality boundary polygons | Search | FUTURE | MEDIUM | A genuine data-acquisition project. Start with centroid + radius. | Phase 6 | NOT STARTED | v2.0 | OBSERVED FROM RESEARCH
RERA registry cross-verification | Moderation | FUTURE | MEDIUM | Each Indian state has a separate registry, many without APIs. | Phase 13 | NOT STARTED | v1.5 | OBSERVED FROM RESEARCH
Rent agreements / tenant verification | Content | FUTURE | LOW | Adjacent service revenue; converts events into recurring income. | Payments | NOT STARTED | v2.2 | OBSERVED FROM RESEARCH
Community Q&A / editorial engine | Content | FUTURE | LOW | Long-tail SEO value but high ongoing editorial cost. | Phase 14 | NOT STARTED | v2.0 | OBSERVED FROM RESEARCH

## FEATURE CHECKLIST
FEATURE CHECKLIST — every feature, and what it needs to be built
Grouped by who uses it. 'Frontend / Backend / Database / API / Third-party' tell you which parts of the system each feature touches.
Feature | User Type | Description | MVP/Future | Frontend | Backend | Database | API | Third-party service | Dependency | Status | Source
Browse by intent (Buy/Rent) | Buyer | Switch the whole search context between buying and renting. | MVP | Yes | Yes | PROPERTY | GET /search | — | Phase 6 | NOT STARTED | OBSERVED FROM RESEARCH
Location typeahead | Buyer | Search-as-you-type across cities, localities and societies. | MVP | Yes | Yes | LOCATION, PLACE_SUGGEST | GET /places/suggest | — | Gazetteer | NOT STARTED | OBSERVED FROM RESEARCH
Faceted search | Buyer | Filter results across many dimensions with live counts. | MVP | Yes | Yes | PROPERTY, LOCATION | GET /search, GET /search/facets | — | Phase 8 | NOT STARTED | OBSERVED FROM RESEARCH
Sort results | Buyer | Order results by relevance, price or recency. | MVP | Yes | Yes | PROPERTY | GET /search | — | Phase 8 | NOT STARTED | OBSERVED FROM RESEARCH
Infinite scroll results | Buyer | Load more results as the user scrolls on the app surface. | MVP | Yes | Yes | PROPERTY | GET /search?page= | — | Phase 8 | NOT STARTED | OBSERVED FROM RESEARCH
Crawlable paginated pages | Buyer | Path-based result pages that search engines can index. | MVP | Yes | Yes | PROPERTY | SSR route | — | Phase 14 | NOT STARTED | OBSERVED FROM RESEARCH
Property detail view | Buyer | Full listing information on one page. | MVP | Yes | Yes | PROPERTY, PROPERTY_MEDIA, AMENITY | GET /properties/{id} | — | Phase 9 | NOT STARTED | OBSERVED FROM RESEARCH
Image gallery | Buyer | Browse listing photos including full-screen view. | MVP | Yes | No | PROPERTY_MEDIA | included in PDP | CDN | Phase 9 | NOT STARTED | OBSERVED FROM RESEARCH
Static location map | Buyer | See where the property is on a map. | MVP | Yes | No | PROPERTY (geo) | included in PDP | Maps provider | D-06 | NOT STARTED | OBSERVED FROM RESEARCH
Save / shortlist | Buyer | Keep a list of properties to revisit. | MVP | Yes | Yes | FAVORITE | POST/DELETE /favorites | — | Phase 5, 9 | NOT STARTED | OBSERVED FROM RESEARCH
Send enquiry | Buyer | Message the seller about a listing. | MVP | Yes | Yes | INQUIRY | POST /inquiries | — | Phase 10 | NOT STARTED | OBSERVED FROM RESEARCH
Reveal seller phone | Buyer | See the seller's number after OTP verification. | MVP | Yes | Yes | INQUIRY, USER | POST /inquiries/reveal | SMS/OTP | Phase 5, 10 | NOT STARTED | OBSERVED FROM RESEARCH
Similar properties | Buyer | See comparable listings on the detail page. | MVP | Yes | Yes | PROPERTY | GET /properties/{id}/similar | — | D-14 | NOT STARTED | DECISION REQUIRED
Zero-result recovery | Buyer | Get useful alternatives when nothing matches. | MVP | Yes | Yes | PROPERTY | GET /search | — | Phase 8 | NOT STARTED | OBSERVED FROM RESEARCH
Saved searches & alerts | Buyer | Be notified when new matching listings appear. | FUTURE | Yes | Yes | SAVED_SEARCH | CRUD /saved-searches | Email/Push | v1.1 | NOT STARTED | OBSERVED FROM RESEARCH
Interactive map search | Buyer | Search by panning and zooming a map. | FUTURE | Yes | Yes | PROPERTY (PostGIS) | GET /search/map | Maps provider | v1.1 | NOT STARTED | OBSERVED FROM RESEARCH
Compare properties | Buyer | Side-by-side comparison of shortlisted listings. | FUTURE | Yes | Yes | FAVORITE, PROPERTY | GET /compare | — | v1.1 | NOT STARTED | OBSERVED FROM RESEARCH
Register / log in by phone | Authentication | Create an account and sign in using an OTP. | MVP | Yes | Yes | USER, OTP_CHALLENGE | POST /auth/otp, /auth/verify | SMS provider | Phase 5 | NOT STARTED | OBSERVED FROM RESEARCH
Session management | Authentication | Stay logged in securely across visits. | MVP | Yes | Yes | USER, SESSION | POST /auth/refresh | — | Phase 5 | NOT STARTED | OBSERVED FROM RESEARCH
Role-based permissions | Authentication | Control what each type of user may do. | MVP | Yes | Yes | USER | all endpoints | — | Phase 5 | NOT STARTED | OBSERVED FROM RESEARCH
Profile management | Authentication | Update name, email and phone. | MVP | Yes | Yes | USER | PATCH /me | SMS provider | Phase 5 | NOT STARTED | OBSERVED FROM RESEARCH
Account deletion / data export | Authentication | Exercise data-protection rights. | MVP | Yes | Yes | USER | POST /me/delete | — | Legal | NOT STARTED | OBSERVED FROM RESEARCH
Post a property | Seller/Owner | Create a listing through a guided multi-step form. | MVP | Yes | Yes | PROPERTY | POST/PATCH /listings | — | Phase 7 | NOT STARTED | OBSERVED FROM RESEARCH
Draft autosave | Seller/Owner | Never lose a partially completed listing. | MVP | Yes | Yes | PROPERTY (DRAFT) | PATCH /listings/{id} | — | Phase 7 | NOT STARTED | OBSERVED FROM RESEARCH
Upload photos | Seller/Owner | Add, reorder and remove listing photos. | MVP | Yes | Yes | PROPERTY_MEDIA | POST /media/presign | Object storage | Phase 4, 7 | NOT STARTED | OBSERVED FROM RESEARCH
Preview listing | Seller/Owner | See exactly what buyers will see before publishing. | MVP | Yes | No | PROPERTY | GET /listings/{id}/preview | — | Phase 7, 9 | NOT STARTED | OBSERVED FROM RESEARCH
Publish listing | Seller/Owner | Submit the listing for screening and publication. | MVP | Yes | Yes | PROPERTY | POST /listings/{id}/publish | — | Phase 7 | NOT STARTED | OBSERVED FROM RESEARCH
Listing quota | Seller/Owner | Limit how many free listings an account may have. | MVP | Yes | Yes | USER, QUOTA_LEDGER | enforced on publish | — | Phase 7 | NOT STARTED | OBSERVED FROM RESEARCH
Manage listings | Seller/Owner | Edit, renew, mark sold or delete listings. | MVP | Yes | Yes | PROPERTY | PATCH/DELETE /listings/{id} | — | Phase 11 | NOT STARTED | OBSERVED FROM RESEARCH
Lead inbox | Seller/Owner | See everyone who enquired or revealed contact. | MVP | Yes | Yes | INQUIRY | GET /leads | — | Phase 10 | NOT STARTED | OBSERVED FROM RESEARCH
Lead status tracking | Seller/Owner | Mark leads as contacted, qualified, closed or lost. | MVP | Yes | Yes | INQUIRY | PATCH /leads/{id} | — | Phase 10 | NOT STARTED | OBSERVED FROM RESEARCH
Lead notifications | Seller/Owner | Be alerted immediately when a lead arrives. | MVP | No | Yes | INQUIRY, NOTIFICATION | worker job | SMS/Email/Push | Phase 10 | NOT STARTED | OBSERVED FROM RESEARCH
Listing performance stats | Seller/Owner | See views, saves and contacts per listing. | MVP | Yes | Yes | SEARCH_EVENT, INQUIRY | GET /listings/{id}/stats | — | Phase 15 | NOT STARTED | OBSERVED FROM RESEARCH
Photo verification | Seller/Owner | Verify a listing with guided on-site photo capture. | MVP | Yes | Yes | VERIFICATION_REQUEST | POST /verification | Object storage | Phase 13 | NOT STARTED | OBSERVED FROM RESEARCH
Agent public profile | Agent/Dealer | A public page listing an agent's properties and areas served. | FUTURE | Yes | Yes | AGENT_PROFILE | GET /agents/{id} | — | v1.4 | NOT STARTED | OBSERVED FROM RESEARCH
Bulk listing upload | Agent/Dealer | Upload many listings by file or feed. | FUTURE | Yes | Yes | PROPERTY | POST /listings/bulk | — | v1.4 | NOT STARTED | OBSERVED FROM RESEARCH
Agent lead CRM | Agent/Dealer | Assign, track and export leads across a team. | FUTURE | Yes | Yes | INQUIRY | GET /leads (extended) | — | v1.4 | NOT STARTED | OBSERVED FROM RESEARCH
Builder profile | Builder | A page for a developer and their projects. | FUTURE | Yes | Yes | BUILDER_PROFILE | GET /builders/{id} | — | v1.5 | NOT STARTED | OBSERVED FROM RESEARCH
Project listing & configurations | Builder | New-construction projects with unit configurations and floor plans. | FUTURE | Yes | Yes | PROJECT, PROJECT_CONFIGURATION | CRUD /projects | — | v1.5 | NOT STARTED | OBSERVED FROM RESEARCH
Brochure / payment plan hosting | Builder | Host downloadable project documents behind a lead form. | FUTURE | Yes | Yes | PROJECT | GET /projects/{id}/brochure | Object storage | v1.5 | NOT STARTED | OBSERVED FROM RESEARCH
Moderation queue | Admin | Review listings awaiting approval. | MVP | Yes | Yes | MODERATION_TASK, PROPERTY | GET /admin/moderation | — | Phase 12, 13 | NOT STARTED | OBSERVED FROM RESEARCH
Automated pre-checks | Admin | Machine screening before human review. | MVP | No | Yes | PROPERTY, PROPERTY_MEDIA | worker job | — | Phase 13 | NOT STARTED | OBSERVED FROM RESEARCH
Approve / reject with reason | Admin | Decide on a listing and tell the seller why. | MVP | Yes | Yes | PROPERTY, MODERATION_TASK | POST /admin/moderation/{id} | — | Phase 13 | NOT STARTED | OBSERVED FROM RESEARCH
Handle reported listings | Admin | Act on user abuse reports within an SLA. | MVP | Yes | Yes | REPORT | GET /admin/reports | — | Phase 13 | NOT STARTED | OBSERVED FROM RESEARCH
User management | Admin | Search, inspect and suspend accounts. | MVP | Yes | Yes | USER | GET/PATCH /admin/users | — | Phase 12 | NOT STARTED | OBSERVED FROM RESEARCH
Audit log | Admin | Immutable record of every administrative action. | MVP | Yes | Yes | AUDIT_LOG | GET /admin/audit | — | Phase 12 | NOT STARTED | OBSERVED FROM RESEARCH
Location data admin | Admin | Add and correct localities and societies. | MVP | Yes | Yes | LOCATION | CRUD /admin/locations | — | Phase 12 | NOT STARTED | OBSERVED FROM RESEARCH
SEO landing page generation | SEO | Generate city/type/budget landing pages from the gazetteer. | MVP (basic) | Yes | Yes | LOCATION, PROPERTY | SSR routes | — | Phase 14 | NOT STARTED | OBSERVED FROM RESEARCH
Thin-content gating | SEO | Keep near-empty pages out of the search index. | MVP | Yes | Yes | LOCATION (counts) | SSR routes | — | Phase 14 | NOT STARTED | OBSERVED FROM RESEARCH
Structured data (JSON-LD) | SEO | Machine-readable markup for rich search results. | MVP | Yes | No | PROPERTY | SSR routes | — | Phase 14 | NOT STARTED | OBSERVED FROM RESEARCH
XML sitemaps | SEO | Tell search engines which pages exist. | MVP | No | Yes | PROPERTY, LOCATION | GET /sitemap*.xml | — | Phase 14 | NOT STARTED | OBSERVED FROM RESEARCH
Programmatic landing matrix at scale | SEO | Generate the full combinatorial page matrix. | FUTURE | Yes | Yes | LOCATION, PROPERTY | generator job | — | v2.0 | NOT STARTED | OBSERVED FROM RESEARCH
Event tracking | Analytics | Record every meaningful user action. | MVP | Yes | Yes | SEARCH_EVENT | POST /events | Analytics | Phase 15 | NOT STARTED | OBSERVED FROM RESEARCH
Lead funnel reporting | Analytics | See where users drop out of the funnel. | MVP | Yes | Yes | SEARCH_EVENT, INQUIRY | internal dashboard | Analytics | Phase 15 | NOT STARTED | OBSERVED FROM RESEARCH
Error monitoring | Analytics | Capture and alert on application errors. | MVP | Yes | Yes | — | — | Error tracking | Phase 15 | NOT STARTED | OBSERVED FROM RESEARCH
Real user performance monitoring | Analytics | Measure real-world speed by device and city. | MVP | Yes | No | — | POST /rum | Analytics | Phase 16 | NOT STARTED | OBSERVED FROM RESEARCH
Transactional email | Notifications | Send receipts, alerts and account emails. | MVP | No | Yes | NOTIFICATION | worker job | Email provider | Phase 10 | NOT STARTED | OBSERVED FROM RESEARCH
SMS notifications | Notifications | Send OTP and lead alerts by SMS. | MVP | No | Yes | NOTIFICATION | worker job | SMS provider | Phase 5, 10 | NOT STARTED | OBSERVED FROM RESEARCH
Web push notifications | Notifications | Push lead alerts to installed devices. | FUTURE | Yes | Yes | NOTIFICATION | worker job | Push service | v1.2 | NOT STARTED | OBSERVED FROM RESEARCH
Notification preferences | Notifications | Let users control what they receive. | MVP | Yes | Yes | USER | PATCH /me/preferences | — | Phase 11 | NOT STARTED | OBSERVED FROM RESEARCH
Free listings | Billing/Monetization | Every seller gets a limited number of free listings. | MVP | Yes | Yes | QUOTA_LEDGER | enforced on publish | — | Phase 7 | NOT STARTED | OBSERVED FROM RESEARCH
Seller subscription plans | Billing/Monetization | Paid plans with higher quotas and features. | FUTURE | Yes | Yes | PLAN, SUBSCRIPTION | CRUD /subscriptions | Payment gateway | v1.3 | NOT STARTED | OBSERVED FROM RESEARCH
Payments & invoicing | Billing/Monetization | Take payment and issue GST-compliant invoices. | FUTURE | Yes | Yes | PAYMENT | POST /payments | Payment gateway | v1.3 | NOT STARTED | OBSERVED FROM RESEARCH
Featured listing placement | Billing/Monetization | Paid, clearly-labelled, bounded ranking boost. | FUTURE | Yes | Yes | PROMOTION | POST /promotions | Payment gateway | v1.3 | NOT STARTED | OBSERVED FROM RESEARCH
Legal & policy pages | Content | Terms, privacy, disclaimers and contact information. | MVP | Yes | No | — | static | — | Phase 20 | NOT STARTED | OBSERVED FROM RESEARCH
Help / FAQ content | Content | Answer common user questions and reduce support load. | MVP (basic) | Yes | No | — | static | — | Phase 20 | NOT STARTED | OBSERVED FROM RESEARCH
Locality reviews | Content | Resident ratings on environment, connectivity and safety. | FUTURE | Yes | Yes | REVIEW | CRUD /reviews | — | v2.0 | NOT STARTED | OBSERVED FROM RESEARCH
Price trends | Content | Rate-per-area trends and appreciation by locality. | FUTURE | Yes | Yes | LOCALITY_STATS, PRICE_HISTORY | GET /trends | — | v2.0 | NOT STARTED | OBSERVED FROM RESEARCH
EMI calculator | Content | Estimate monthly loan payments. | FUTURE | Yes | No | — | client-side | — | v2.2 | NOT STARTED | OBSERVED FROM RESEARCH

## WEBSITE PAGES
WEBSITE PAGES — every page to design and build
URL patterns follow the SEO architecture proposed in the research. Decide these URLs in Phase 2, BEFORE building any page — changing them after launch costs search ranking.
Page name | URL pattern | Purpose | User type | SEO required? | Dynamic/Static | Required components | API/data required | Mobile required? | Status | Source
Homepage | / | Route the visitor into a typed intent plus a place, as fast as possible. | All | Yes | Dynamic (SSR + cached) | Header, intent tabs, hero search, quick chips, recommended rail, budget tiles, locality cards, owner CTA, SEO footer | Suggest API, popular localities, recommended listings | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Search results — SEO landing | /{intent}/{city}[/{locality}][/{filter-slug}] | Indexable landing page for a specific search intent; the main acquisition channel. | Buyer/Tenant | Yes | Dynamic (SSR + ISR) | Breadcrumb, H1 with count, filter rail, sort, chips, result cards, pagination, SEO copy, internal links, FAQ | Search API, facet counts, internal link clusters | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Search results — paginated | /{intent}/{city}/.../page/{n} | Crawlable deep pages so inventory beyond page 1 can be indexed. | Buyer/Tenant | Yes | Dynamic (SSR) | Same as landing page plus prev/next links | Search API with offset | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Search — interactive app surface | /search?… | Fast, stateful filtering without page reloads. Deliberately NOT indexed. | Buyer/Tenant | No (noindex) | Dynamic (client + API) | Filter panel/sheet, chips, sort, infinite scroll, result count | Search API, facet API | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Property detail | /property/{slug}-p{id} | Answer every buyer question and convert to a lead. | Buyer/Tenant | Yes | Dynamic (SSR) | Breadcrumb, gallery, header, sticky contact, details grid, amenities, map, seller card, similar, FAQ, JSON-LD | Property API, similar API, locality summary | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Property expired | /property/{slug}-p{id} (HTTP 410) | Handle a removed listing without a dead end or an SEO penalty. | Buyer/Tenant | Yes (410) | Dynamic (SSR) | Explanation, similar active listings, search CTA | Similar listings API | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Locality hub | /localities/{city}/{locality} | Capture research-intent traffic and link into listings. | Buyer/Tenant | Yes | Dynamic (SSR + ISR) | Locality summary, listing rails by intent, nearby localities, map, stats | Locality API, listing counts | Yes | NOT STARTED | OBSERVED FROM RESEARCH
City hub | /localities/{city} | Top-level geographic entry point and crawl distribution. | Buyer/Tenant | Yes | Dynamic (SSR + ISR) | Locality grid, popular searches, listing counts | Locality API | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Login / Register | /login, /register | Let users authenticate by phone OTP. | All | No (noindex) | Dynamic | Phone input, OTP input, role select, resend timer | Auth API | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Post property wizard | /post-property | Let a seller create a listing in under 8 minutes on a phone. | Seller/Owner/Agent | No (noindex) | Dynamic | Stepper, config-driven fields, map pin, uploader, completeness score, preview | Listings API, media presign, places API | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Post property landing | /post-property-free | Marketing page that converts owners into sellers. | Seller/Owner | Yes | Static/ISR | Value proposition, steps explainer, CTA, FAQ | None | Yes | NOT STARTED | PROPOSED
Listing preview | /post-property/{id}/preview | Show the seller exactly what buyers will see. | Seller/Owner | No (noindex) | Dynamic | Full PDP rendering in preview mode, edit and publish actions | Listings API | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Dashboard home | /dashboard | Home base after login for both sides. | All (auth) | No (noindex) | Dynamic | Role-aware summary cards, quick actions | User API, counts | Yes | NOT STARTED | PROPOSED
My listings | /dashboard/listings | Manage listings across every lifecycle state. | Seller/Owner/Agent | No (noindex) | Dynamic | State tabs, listing rows, actions, empty states | Listings API | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Lead inbox | /dashboard/leads | See and work every lead received. | Seller/Owner/Agent | No (noindex) | Dynamic | Lead list, type filter, status controls, notes, detail drawer | Leads API | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Listing analytics | /dashboard/listings/{id}/stats | Show sellers how their listing performs. | Seller/Owner/Agent | No (noindex) | Dynamic | Stat tiles, trend chart, comparison to locality average | Stats API | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Saved properties | /dashboard/saved | The buyer's shortlist. | Buyer/Tenant | No (noindex) | Dynamic | Saved cards, remove, notes, empty state | Favorites API | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Profile & settings | /dashboard/profile | Manage account details and preferences. | All (auth) | No (noindex) | Dynamic | Profile form, phone change with OTP, notification preferences, delete account | User API | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Admin — moderation queue | /admin/moderation | Review listings awaiting approval. | Admin | No (noindex) | Dynamic | Queue list, listing preview, approve/reject with reason, auto-check results | Admin API | No | NOT STARTED | OBSERVED FROM RESEARCH
Admin — listings | /admin/listings | Find and act on any listing. | Admin | No (noindex) | Dynamic | Search, filters, bulk actions, detail view | Admin API | No | NOT STARTED | PROPOSED
Admin — users | /admin/users | Inspect and manage accounts. | Admin | No (noindex) | Dynamic | User search, detail, suspend, listings and leads view | Admin API | No | NOT STARTED | PROPOSED
Admin — reports | /admin/reports | Handle user abuse reports within SLA. | Admin | No (noindex) | Dynamic | Report queue, SLA timer, resolution actions | Admin API | No | NOT STARTED | OBSERVED FROM RESEARCH
Admin — locations | /admin/locations | Maintain the place hierarchy. | Admin | No (noindex) | Dynamic | Tree browser, add/edit locality, merge duplicates | Admin API | No | NOT STARTED | PROPOSED
Admin — audit log | /admin/audit | Review every administrative action. | Admin | No (noindex) | Dynamic | Filterable immutable log | Admin API | No | NOT STARTED | OBSERVED FROM RESEARCH
Admin — dashboard | /admin | Operational overview in one screen. | Admin | No (noindex) | Dynamic | Queue depth, new listings, reports, lead volume | Admin API | No | NOT STARTED | PROPOSED
Terms & Conditions | /terms | Legal terms of use, including verification scope disclaimer. | All | Yes | Static | Legal content, last-updated date | None | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Privacy Policy | /privacy | Explain what data is collected and users' rights. | All | Yes | Static | Legal content, contact for data requests | None | Yes | NOT STARTED | OBSERVED FROM RESEARCH
About / Contact | /about, /contact | Establish legitimacy and provide a support channel. | All | Yes | Static | Company info, contact form, support details | Contact form API | Yes | NOT STARTED | PROPOSED
Help / FAQ | /help[/{slug}] | Answer common questions and reduce support load. | All | Yes | Static/ISR | FAQ accordion, search, categories, FAQPage JSON-LD | None (MVP) | Yes | NOT STARTED | OBSERVED FROM RESEARCH
404 Not Found | (any unmatched) | Recover a lost user rather than losing them. | All | No | Static | Explanation, search box, popular links | None | Yes | NOT STARTED | PROPOSED
500 Error | (server error) | Fail gracefully and keep the brand intact. | All | No | Static | Apology, retry, support link | None | Yes | NOT STARTED | PROPOSED
Sitemap index | /sitemap.xml + children | Tell search engines which pages exist. | Crawler | Yes | Dynamic (generated) | XML only | Sitemap generator | No | NOT STARTED | OBSERVED FROM RESEARCH
robots.txt | /robots.txt | Control crawler access and point to sitemaps. | Crawler | Yes | Static/Dynamic | Text only | None | No | NOT STARTED | OBSERVED FROM RESEARCH
Map search | /search/map?bbox=… | Search by panning a map. DEFERRED to v1.1. | Buyer/Tenant | No (noindex) | Dynamic | Map, clustered markers, mini-cards, list toggle | Map search API | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Project detail | /project/{slug}-j{id} | New-construction project page. DEFERRED to v1.5. | Buyer/Tenant | Yes | Dynamic (SSR) | Overview, configurations, floor plans, brochure gate, amenities, RERA | Projects API | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Builder profile | /builder/{slug}-b{id} | Developer page with their projects. DEFERRED to v1.5. | Buyer/Tenant | Yes | Dynamic (SSR) | Profile, project list, track record | Builders API | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Agent profile | /agent/{slug}-a{id} | Agent page with listings and areas served. DEFERRED to v1.4. | Buyer/Tenant | Yes | Dynamic (SSR) | Profile, listings, areas, reviews | Agents API | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Price trends | /price-trends/{city}[/{locality}] | Rate and appreciation data. DEFERRED to v2.0. | Buyer/Tenant | Yes | Dynamic (ISR, monthly) | Trend charts, locality leaderboard, comparison | Stats API | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Locality reviews | /reviews/{city}[/{locality}] | Resident ratings and reviews. DEFERRED to v2.0. | Buyer/Tenant | Yes | Dynamic (SSR) | Rating summary, review list, write-review form | Reviews API | Yes | NOT STARTED | OBSERVED FROM RESEARCH
Pricing / plans | /pricing | Self-serve seller plans. DEFERRED to v1.3. | Seller/Agent/Builder | Yes | Static/ISR | Plan comparison, FAQ, checkout CTA | Plans API | Yes | NOT STARTED | OBSERVED FROM RESEARCH
EMI calculator | /home-loan/emi-calculator | High-intent finance tool and SEO asset. DEFERRED to v2.2. | Buyer | Yes | Static + client JS | Calculator, results, related content | None | Yes | NOT STARTED | OBSERVED FROM RESEARCH

## USER FLOWS
USER FLOWS — step-by-step journeys, including what can go wrong
Fifteen complete journeys for buyers, sellers and admins. The 'Possible Error' column is the most valuable part: these are the failures to design for and test.
Flow | Step No. | Actor | Action | Screen | System Response | Next Step | Possible Error | Status
A. Buyer searches for a property | 1 | Buyer | Opens the site | Homepage | Homepage renders server-side with the search widget ready | Step 2 | Slow first load — must stay within the LCP budget | NOT STARTED
A. Buyer searches for a property | 2 | Buyer | Chooses the Buy or Rent tab | Homepage | Search form reconfigures for the chosen intent | Step 3 | Wrong filter set shown if intent not applied | NOT STARTED
A. Buyer searches for a property | 3 | Buyer | Types a city or locality name | Homepage | Typeahead returns grouped suggestions with result counts | Step 4 | No suggestions if the gazetteer lacks the place; stale results if requests are not cancelled | NOT STARTED
A. Buyer searches for a property | 4 | Buyer | Selects one or more places | Homepage | Each selection becomes a removable chip | Step 5 | Duplicate chips if not de-duplicated | NOT STARTED
A. Buyer searches for a property | 5 | Buyer | Presses Search | Homepage | Navigates to the SEO landing URL for that intent and place | Step 6 | Unknown place cannot resolve to a URL | NOT STARTED
A. Buyer searches for a property | 6 | System | Renders results | Search results | Server-rendered results with count in H1 and title | Flow B | Zero results — must show the recovery ladder, never a blank page | NOT STARTED
B. Buyer filters results | 1 | Buyer | Opens filters | Search results (desktop rail / mobile sheet) | Filter panel opens showing option counts | Step 2 | Counts wrong if facet semantics are incorrect | NOT STARTED
B. Buyer filters results | 2 | Buyer | Sets a budget range | Filter panel | Result count preview updates live | Step 3 | Linear slider makes the common range unselectable | NOT STARTED
B. Buyer filters results | 3 | Buyer | Selects BHK and property type | Filter panel | Counts for other facets recalculate | Step 4 | Zero-count options hidden instead of disabled — looks broken | NOT STARTED
B. Buyer filters results | 4 | Buyer | Applies filters | Filter panel | URL updates; results refresh; chips appear | Step 5 | CRITICAL: must never navigate away, reset scroll or clear state | NOT STARTED
B. Buyer filters results | 5 | Buyer | Changes sort order | Search results | Results reorder; explicit sort is respected exactly | Step 6 | Promoted listings interleaving into an explicit sort destroys trust | NOT STARTED
B. Buyer filters results | 6 | Buyer | Removes a filter chip | Search results | That filter is removed and results refresh | Flow C | Back button behaviour inconsistent if history is mismanaged | NOT STARTED
C. Buyer opens a property | 1 | Buyer | Clicks a result card | Search results | Navigates to the property detail URL | Step 2 | Losing search context on back navigation | NOT STARTED
C. Buyer opens a property | 2 | System | Renders the detail page | Property detail | Server-rendered page with gallery and sticky contact | Step 3 | Layout shift if image boxes are not reserved | NOT STARTED
C. Buyer opens a property | 3 | Buyer | Browses photos | Property detail | Gallery advances; full-screen available | Step 4 | Slow gallery if all images load eagerly | NOT STARTED
C. Buyer opens a property | 4 | Buyer | Reads details and amenities | Property detail | Specification grid with explicit area basis | Step 5 | Ambiguous area basis misleads on price per sqft | NOT STARTED
C. Buyer opens a property | 5 | Buyer | Views the location map | Property detail | Map renders with approximate pin for owner listings | Flow D or E | Map blocking first paint; exact address exposed prematurely | NOT STARTED
D. Buyer saves a property | 1 | Buyer | Taps the save icon | Property detail or card | Icon fills immediately (optimistic update) | Step 2 | Optimistic update not reverted if the request fails | NOT STARTED
D. Buyer saves a property | 2 | System | Checks authentication | — | If logged out, opens the auth sheet | Step 3 | Losing the user's place in the page | NOT STARTED
D. Buyer saves a property | 3 | Buyer | Completes login if prompted | Auth sheet | Login succeeds | Step 4 | User abandons if returned to the homepage instead of the listing | NOT STARTED
D. Buyer saves a property | 4 | System | Replays the save | Property detail | Property is saved and confirmed by a toast | Step 5 | Save silently dropped after login — a common and costly bug | NOT STARTED
D. Buyer saves a property | 5 | Buyer | Opens saved list later | Saved properties | Saved listings appear, including on other devices | End | Saved items lost if stored only in the browser | NOT STARTED
E. Buyer contacts the seller | 1 | Buyer | Presses Contact or View Number | Property detail | Contact form opens | Step 2 | CTA not reachable if the sticky bar is missing | NOT STARTED
E. Buyer contacts the seller | 2 | Buyer | Enters name and phone | Contact form | Input validated | Step 3 | Weak validation lets junk leads through | NOT STARTED
E. Buyer contacts the seller | 3 | Buyer | Requests the OTP | Contact form | OTP sent to the phone | Step 4 | SMS delay or failure; must offer resend with a timer | NOT STARTED
E. Buyer contacts the seller | 4 | Buyer | Enters the OTP | Contact form | Code verified | Step 5 | Wrong code; expired code; too many attempts | NOT STARTED
E. Buyer contacts the seller | 5 | System | Records the lead | — | Inquiry saved BEFORE the number is shown; deduplicated | Step 6 | Revealing before recording loses the lead if the write fails | NOT STARTED
E. Buyer contacts the seller | 6 | System | Reveals contact details | Property detail | Seller's number shown; seller notified | End | Rate limit exceeded — explain clearly rather than failing silently | NOT STARTED
F. Buyer completes OTP verification | 1 | Buyer | Triggers an action needing verification | Any | OTP challenge created with expiry | Step 2 | Too many requests from one number | NOT STARTED
F. Buyer completes OTP verification | 2 | System | Sends the code | — | SMS dispatched via provider | Step 3 | Provider outage; DLT template not approved | NOT STARTED
F. Buyer completes OTP verification | 3 | Buyer | Enters the code | OTP input | Code checked against the challenge | Step 4 | Expired or already-used code | NOT STARTED
F. Buyer completes OTP verification | 4 | System | Issues a session | — | Tokens issued; the original action resumes | End | Action not resumed after verification | NOT STARTED
G. Seller registers | 1 | Seller | Chooses Post Property | Homepage / nav | Prompted to sign in or register | Step 2 | Entry point not obvious enough | NOT STARTED
G. Seller registers | 2 | Seller | Enters phone number | Register | OTP sent | Step 3 | Number already registered — must sign in instead | NOT STARTED
G. Seller registers | 3 | Seller | Enters the OTP | Register | Phone verified | Step 4 | Code expired | NOT STARTED
G. Seller registers | 4 | Seller | Selects role (Owner / Agent / Builder) | Register | Role stored on the account | Flow H | Agents self-selecting as owners — see the detection task | NOT STARTED
H. Seller posts a property | 1 | Seller | Starts the wizard | Post property — Basics | Draft created server-side immediately | Step 2 | Draft not created — refresh loses everything | NOT STARTED
H. Seller posts a property | 2 | Seller | Chooses intent, segment and type | Basics | Field set for later steps is configured | Step 3 | Wrong field set shown for the chosen type | NOT STARTED
H. Seller posts a property | 3 | Seller | Enters location and drags the pin | Location | Pin validated against the locality boundary | Step 4 | Pin far from the selected locality; locality missing from the gazetteer | NOT STARTED
H. Seller posts a property | 4 | Seller | Fills configuration and areas | Property profile | Areas captured separately by basis | Step 5 | Carpet and super area conflated — corrupts price per sqft | NOT STARTED
H. Seller posts a property | 5 | Seller | Selects amenities | Property profile | Amenities saved | Flow I | Overlong amenity list causing drop-off | NOT STARTED
I. Seller saves a draft | 1 | Seller | Leaves the form mid-way | Any wizard step | Progress autosaved to the draft | Step 2 | Autosave failing silently | NOT STARTED
I. Seller saves a draft | 2 | Seller | Returns later | Dashboard — My listings | Draft listed with a Resume action | Step 3 | Draft not visible in the dashboard | NOT STARTED
I. Seller saves a draft | 3 | Seller | Resumes the draft | Wizard | Reopens at the last completed step with data intact | Flow J | Reopening at step 1 and losing entered data | NOT STARTED
J. Seller uploads photos | 1 | Seller | Selects photos | Media step | Images compressed in the browser | Step 2 | Very large files failing on mobile data | NOT STARTED
J. Seller uploads photos | 2 | Seller | Uploads | Media step | Direct presigned upload with per-file progress | Step 3 | Upload failure with no retry; unsupported format | NOT STARTED
J. Seller uploads photos | 3 | System | Processes images | — | Variants generated, EXIF stripped, fingerprint computed | Step 4 | Processing backlog delaying publication | NOT STARTED
J. Seller uploads photos | 4 | Seller | Reorders and sets the main photo | Media step | Order saved | Flow K | Order not persisting | NOT STARTED
J. Seller uploads photos | 5 | System | Screens the images | — | Contact details or watermarks detected and flagged | Flow K | False positives blocking genuine photos | NOT STARTED
K. Seller previews the listing | 1 | Seller | Presses Preview | Wizard | Full public rendering shown | Step 2 | Preview differing from the live page | NOT STARTED
K. Seller previews the listing | 2 | Seller | Reviews the completeness score | Preview | Score shown with the highest-value missing fields | Step 3 | Score not explaining what to improve | NOT STARTED
K. Seller previews the listing | 3 | Seller | Edits or continues | Preview | Returns to the relevant step or proceeds | Flow L | Edits lost when returning to preview | NOT STARTED
L. Seller publishes the listing | 1 | Seller | Presses Publish | Preview | Quota checked | Step 2 | Over quota — must explain the limit and the options clearly | NOT STARTED
L. Seller publishes the listing | 2 | System | Moves to screening | — | Status set to UNDER_SCREENING; moderation task created | Step 3 | Seller not told that review is pending | NOT STARTED
L. Seller publishes the listing | 3 | System | Runs automated checks | — | Duplicate, contact-info and price-sanity checks run | Step 4 | False positive rejecting a genuine listing | NOT STARTED
L. Seller publishes the listing | 4 | Admin | Reviews if flagged | Admin moderation | Approved or rejected with a specific reason | Step 5 | Slow review leaving sellers waiting | NOT STARTED
L. Seller publishes the listing | 5 | System | Publishes | — | Status ACTIVE; indexed for search; sitemap updated | End | Listing live but not appearing in search — indexing lag | NOT STARTED
M. Seller manages a listing | 1 | Seller | Opens My Listings | Dashboard | Listings grouped by lifecycle state | Step 2 | States unclear to a non-technical seller | NOT STARTED
M. Seller manages a listing | 2 | Seller | Edits a listing | Edit form | Material changes re-enter screening | Step 3 | Price changes bypassing review | NOT STARTED
M. Seller manages a listing | 3 | Seller | Marks it sold or rented | My listings | Listing closed and removed from search | Step 4 | Sold listings staying live — the top trust complaint | NOT STARTED
M. Seller manages a listing | 4 | Seller | Renews before expiry | My listings | Expiry extended; freshness updated | End | No renewal reminder sent before expiry | NOT STARTED
N. Admin reviews a listing | 1 | Admin | Opens the moderation queue | Admin moderation | Pending listings listed oldest first | Step 2 | Queue growing faster than review capacity | NOT STARTED
N. Admin reviews a listing | 2 | Admin | Opens a listing | Admin moderation | Listing shown with automated check results | Step 3 | Check results not surfaced to the reviewer | NOT STARTED
N. Admin reviews a listing | 3 | Admin | Approves or rejects | Admin moderation | Decision applied and logged to the audit trail | Step 4 | Decision made without a recorded reason | NOT STARTED
N. Admin reviews a listing | 4 | System | Notifies the seller | — | Seller told the outcome and, if rejected, exactly why | End | Generic rejection message causing support load | NOT STARTED
O. Admin handles a reported listing | 1 | Buyer | Reports a listing | Property detail or card | Report created with a reason and an SLA timer | Step 2 | Report form too hidden to be used | NOT STARTED
O. Admin handles a reported listing | 2 | System | Triages | — | Auto-flags repeat-reported listings for priority review | Step 3 | High-volume reports overwhelming the queue | NOT STARTED
O. Admin handles a reported listing | 3 | Admin | Investigates | Admin reports | Listing, seller history and prior reports shown together | Step 4 | Deciding without seller context | NOT STARTED
O. Admin handles a reported listing | 4 | Admin | Acts | Admin reports | Listing removed, seller warned, or report dismissed | Step 5 | Action not logged in the audit trail | NOT STARTED
O. Admin handles a reported listing | 5 | System | Closes the loop | — | Reporter informed; seller informed if action was taken | End | Reporter never hearing back, so stops reporting | NOT STARTED

## DATABASE
DATABASE — proposed tables and what each one is for
An ORIGINAL conceptual schema derived from the observed functionality. Build only the MVP tables first. 'PostGIS?' marks tables needing map/location capability.
Table | Purpose | Important Fields | Relationships | Indexes | PostGIS? | MVP/Future | Status | Source
USER | Every person on the platform: buyer, seller, agent, builder or admin. | id, public_id, phone (unique, verified_at), email, name, roles[], status, preferred_city_id, created_at, deleted_at | 1:1 AGENT_PROFILE / BUILDER_PROFILE; 1:N PROPERTY, INQUIRY, FAVORITE | phone (unique), email (unique), status | No | MVP | NOT STARTED | OBSERVED FROM RESEARCH
AGENT_PROFILE | Extra details for users acting as agents. | user_id, agency_name, slug, rera_agent_id, verified_status, areas_served[], rating, response_rate | 1:1 USER | user_id (unique), slug (unique) | No | FUTURE (v1.4) | NOT STARTED | OBSERVED FROM RESEARCH
BUILDER_PROFILE | Extra details for developer accounts. | user_id, name, slug, logo_media_id, established_year, rera_ids[], verified_status | 1:1 USER; 1:N PROJECT | user_id (unique), slug (unique) | No | FUTURE (v1.5) | NOT STARTED | OBSERVED FROM RESEARCH
LOCATION | The place hierarchy: country, state, city, zone, locality, society. The most important table in the system. | id, public_id, parent_id, type, name, slug, full_slug, centroid, boundary, pincode, aliases[], listing_count, is_active | Self-referencing tree; 1:N PROPERTY | parent_id+type+is_active, slug, GIST(centroid), GIST(boundary) | YES | MVP | NOT STARTED | OBSERVED FROM RESEARCH
PROPERTY | A listing. The central fact table. | id, public_id, slug, owner_user_id, posted_by, intent, segment, property_type_id, location_id, geo, geo_precision, bedrooms, bathrooms, carpet_area, builtup_area, super_area, area_unit, price, status, is_verified, completeness_score, published_at, expires_at | N:1 USER, LOCATION, PROPERTY_TYPE; 1:N PROPERTY_MEDIA, INQUIRY, PRICE_HISTORY; M:N AMENITY | (status,intent,segment,location_id,price) WHERE ACTIVE; GIST(geo); (published_at DESC); (owner_user_id,status) | YES | MVP | NOT STARTED | OBSERVED FROM RESEARCH
PROPERTY_MEDIA | Photos, videos and floor plans for a listing. One table with a kind discriminator. | id, property_id, kind, storage_key, cdn_url, width, height, sort_order, is_primary, phash, moderation_status | N:1 PROPERTY | (property_id, sort_order), phash | No | MVP | NOT STARTED | OBSERVED FROM RESEARCH
PROPERTY_TYPE | Reference list of property types and the fields each requires. | id, code, name, segment, required_fields[], is_active | 1:N PROPERTY | code (unique) | No | MVP | NOT STARTED | OBSERVED FROM RESEARCH
AMENITY | Reference list of amenities, grouped and filterable. | id, code, name, category, applies_to_segments[], is_filterable, sort_order | M:N PROPERTY via PROPERTY_AMENITY | code (unique) | No | MVP | NOT STARTED | OBSERVED FROM RESEARCH
PROPERTY_AMENITY | Join table linking listings to amenities, with an optional value. | property_id, amenity_id, value | N:N join | (property_id), (amenity_id) | No | MVP | NOT STARTED | OBSERVED FROM RESEARCH
INQUIRY | A lead. The monetisable event — model it explicitly from day one. | id, property_id, from_user_id, to_user_id, type (QUERY/CONTACT_VIEW/CALLBACK/VISIT), contact_snapshot, source_surface, is_billable, dedupe_key, seller_status, seller_notes, created_at | N:1 PROPERTY, USER (from and to) | (to_user_id, created_at DESC), dedupe_key (UNIQUE) | No | MVP | NOT STARTED | OBSERVED FROM RESEARCH
FAVORITE | A buyer's saved listing. | user_id, property_id, created_at, note | N:N USER-PROPERTY | PK (user_id, property_id), (property_id) | No | MVP | NOT STARTED | OBSERVED FROM RESEARCH
SAVED_SEARCH | A stored search with optional alerts. Stores the filter object, not the URL. | id, user_id, name, filter_json, canonical_url, alert_frequency, last_run_at, last_seen_max_id | N:1 USER | (user_id), (alert_frequency, last_run_at) | No | FUTURE (v1.1) | NOT STARTED | OBSERVED FROM RESEARCH
SEARCH_EVENT | Append-only analytics of what people searched and clicked. | id, user_id/anon_id, filter_json, result_count, surface, latency_ms, clicked_property_ids[], executed_at | N:1 USER (nullable) | (executed_at), (user_id) | No | MVP | NOT STARTED | OBSERVED FROM RESEARCH
OTP_CHALLENGE | Short-lived one-time codes for phone verification. | id, phone, code_hash, purpose, attempts, expires_at, consumed_at | N:1 USER (nullable) | (phone, expires_at) | No | MVP | NOT STARTED | OBSERVED FROM RESEARCH
SESSION | Refresh-token records so sessions can be revoked. | id, user_id, refresh_token_hash, device, ip, expires_at, revoked_at | N:1 USER | (user_id), refresh_token_hash (unique) | No | MVP | NOT STARTED | OBSERVED FROM RESEARCH
MODERATION_TASK | An item awaiting human review. | id, property_id, reason, auto_check_results, assigned_to, status, decision, decision_reason, created_at, resolved_at | N:1 PROPERTY, USER | (status, created_at), (property_id) | No | MVP | NOT STARTED | OBSERVED FROM RESEARCH
REPORT | A user-submitted abuse report. | id, property_id, reporter_user_id, reason_code, details, status, sla_due_at, resolved_at | N:1 PROPERTY, USER | (status, sla_due_at), (property_id) | No | MVP | NOT STARTED | OBSERVED FROM RESEARCH
VERIFICATION_REQUEST | A request to verify a listing, with captured evidence. | id, property_id, method, captured_geo, captured_at, evidence_media_ids[], status, reviewed_by | N:1 PROPERTY | (property_id), (status) | YES (captured_geo) | MVP | NOT STARTED | OBSERVED FROM RESEARCH
AUDIT_LOG | Immutable record of administrative and sensitive actions. | id, actor_user_id, action, entity_type, entity_id, before, after, ip, created_at | N:1 USER | (entity_type, entity_id), (actor_user_id, created_at) | No | MVP | NOT STARTED | OBSERVED FROM RESEARCH
NOTIFICATION | Queued and sent notifications across channels. | id, user_id, channel, template, payload, status, sent_at, read_at | N:1 USER | (user_id, created_at DESC), (status) | No | MVP | NOT STARTED | OBSERVED FROM RESEARCH
PRICE_HISTORY | Every price change on a listing, for 'price reduced' badges. | id, property_id, old_price, new_price, change_pct, changed_at | N:1 PROPERTY | (property_id, changed_at DESC) | No | MVP (cheap, enables a high-converting badge) | NOT STARTED | OBSERVED FROM RESEARCH
PROJECT | A new-construction development. | id, public_id, builder_user_id, name, slug, location_id, geo, status, possession_date, rera_ids[], price_min, price_max | N:1 BUILDER_PROFILE, LOCATION; 1:N PROJECT_CONFIGURATION | (location_id, status), slug (unique), GIST(geo) | YES | FUTURE (v1.5) | NOT STARTED | OBSERVED FROM RESEARCH
PROJECT_CONFIGURATION | A unit type within a project (e.g. 3 BHK, 1450 sqft). | id, project_id, property_type_id, bedrooms, carpet_area, super_area, price_min, price_max, floor_plan_media_id | N:1 PROJECT | (project_id) | No | FUTURE (v1.5) | NOT STARTED | OBSERVED FROM RESEARCH
REVIEW | A resident review of a locality, society, project, agent or builder. | id, author_user_id, subject_type, subject_id, overall_rating, ratings{environment,lifestyle,connectivity,safety}, body, resident_status, status | N:1 USER; polymorphic subject | (subject_type, subject_id, status) | No | FUTURE (v2.0) | NOT STARTED | OBSERVED FROM RESEARCH
LOCALITY_STATS | Monthly price statistics per locality and property type. | id, location_id, property_type_id, transaction_type, period_month, median_price_per_unit_area, p25, p75, sample_size, yoy_change_pct | N:1 LOCATION | (location_id, property_type_id, transaction_type, period_month DESC) | No | FUTURE (v2.0) — enforce a minimum sample_size before publishing | NOT STARTED | OBSERVED FROM RESEARCH
PLAN | A purchasable package definition. | id, code, audience, name, price, duration_days, listing_quota, featured_quota, lead_quota | 1:N SUBSCRIPTION | code (unique) | No | FUTURE (v1.3) | NOT STARTED | OBSERVED FROM RESEARCH
SUBSCRIPTION | A user's active plan. | id, user_id, plan_id, status, starts_at, ends_at, auto_renew, payment_id | N:1 USER, PLAN | (user_id, status), (ends_at) | No | FUTURE (v1.3) | NOT STARTED | OBSERVED FROM RESEARCH
PAYMENT | A payment attempt and its outcome. | id, user_id, subscription_id, amount, currency, gateway, gateway_ref, status, invoice_number, gst_amount | N:1 USER, SUBSCRIPTION | (user_id), gateway_ref (unique) | No | FUTURE (v1.3) | NOT STARTED | OBSERVED FROM RESEARCH
QUOTA_LEDGER | Append-only record of quota consumption. Never a mutable counter. | id, subscription_id, quota_type, delta, balance_after, reason, ref_id, created_at | N:1 SUBSCRIPTION | (subscription_id, created_at) | No | MVP (free quota) / extended in v1.3 | NOT STARTED | OBSERVED FROM RESEARCH
PROMOTION | A paid placement applied to a listing. | id, property_id, subscription_id, kind, starts_at, ends_at, placement_scope, priority | N:1 PROPERTY, SUBSCRIPTION | (property_id, ends_at), (kind, placement_scope) | No | FUTURE (v1.3) | NOT STARTED | OBSERVED FROM RESEARCH
PLACE_SUGGEST | Denormalised autocomplete table. Never run typeahead against PROPERTY. | id, location_id, type, label, parent_path, popularity, listing_count | N:1 LOCATION | trigram index on label, (popularity DESC) | No | MVP | NOT STARTED | OBSERVED FROM RESEARCH
OUTBOX | Transactional outbox so events are published reliably. | id, aggregate_type, aggregate_id, event_type, payload, published_at, created_at | — | (published_at NULLS FIRST, created_at) | No | MVP | NOT STARTED | OBSERVED FROM RESEARCH

## API CHECKLIST
API CHECKLIST — the planned endpoints (do NOT build these yet)
This is the plan, not an instruction to start coding. 'Error Cases' matter as much as the success path — they are what makes an API feel reliable.
API ID | Module | Method | Endpoint | Purpose | Authentication | Request | Response | Error Cases | Database Tables | MVP/Future | Status
API-01 | Auth | POST | /auth/otp/request | Send a one-time code to a phone number. | Public | {phone, purpose} | {challenge_id, expires_in} | 429 rate limited; 400 invalid phone; 503 SMS provider down | OTP_CHALLENGE | MVP | NOT STARTED
API-02 | Auth | POST | /auth/otp/verify | Verify the code and issue a session. | Public | {challenge_id, code} | {access_token, refresh_token, user} | 400 wrong code; 410 expired; 429 too many attempts | OTP_CHALLENGE, USER, SESSION | MVP | NOT STARTED
API-03 | Auth | POST | /auth/refresh | Exchange a refresh token for a new access token. | Refresh token | {refresh_token} | {access_token, refresh_token} | 401 invalid; 403 reuse detected (revoke all) | SESSION | MVP | NOT STARTED
API-04 | Auth | POST | /auth/logout | End the current session. | Bearer | {} | 204 | 401 unauthenticated | SESSION | MVP | NOT STARTED
API-05 | User | GET | /me | Return the signed-in user's profile. | Bearer | — | {user} | 401 | USER | MVP | NOT STARTED
API-06 | User | PATCH | /me | Update profile details. | Bearer | {name, email} | {user} | 400 validation; 409 email taken | USER | MVP | NOT STARTED
API-07 | User | POST | /me/phone/change | Change phone number with re-verification. | Bearer | {new_phone, challenge_id, code} | {user} | 400; 409 number in use | USER, OTP_CHALLENGE, SESSION | MVP | NOT STARTED
API-08 | User | POST | /me/delete | Request account deletion (data-protection right). | Bearer | {reason} | {request_id, effective_at} | 401; 409 active obligations | USER | MVP | NOT STARTED
API-09 | Places | GET | /places/suggest | Autocomplete cities, localities and societies. | Public | ?q=&limit=&city_id= | [{id, type, label, path, listing_count}] | 400 query too short | PLACE_SUGGEST | MVP | NOT STARTED
API-10 | Places | GET | /places/{id} | Return a place and its ancestors. | Public | — | {place, ancestors[]} | 404 | LOCATION | MVP | NOT STARTED
API-11 | Search | GET | /search | Return filtered, sorted, paginated listings. | Public | Normalised filter params + sort + page | {results[], total, page, facets_summary} | 400 invalid filter; 422 unknown place | PROPERTY, LOCATION | MVP | NOT STARTED
API-12 | Search | GET | /search/facets | Return option counts for the current filter set. | Public | Same filter params | {facets: {field: [{value, count}]}} | 400 invalid filter | PROPERTY | MVP | NOT STARTED
API-13 | Search | GET | /search/count | Fast count only, for the Apply button and titles. | Public | Same filter params | {total} | 400 | PROPERTY | MVP | NOT STARTED
API-14 | Search | GET | /search/map | Listings within a map bounding box, clustered. | Public | ?bbox=&zoom=&filters | {clusters[], listings[]} | 400 bbox too large | PROPERTY (PostGIS) | FUTURE (v1.1) | NOT STARTED
API-15 | Property | GET | /properties/{public_id} | Full detail for one listing. | Public | — | {property, media[], amenities[], seller_summary} | 404; 410 expired | PROPERTY, PROPERTY_MEDIA, AMENITY | MVP | NOT STARTED
API-16 | Property | GET | /properties/{public_id}/similar | Comparable listings. | Public | ?limit= | {results[]} | 404 | PROPERTY | MVP (see D-14) | NOT STARTED
API-17 | Listing | POST | /listings | Create a draft listing. | Bearer (seller) | {intent, segment, property_type_id} | {listing_id, status: DRAFT} | 401; 403 role; 429 quota | PROPERTY | MVP | NOT STARTED
API-18 | Listing | PATCH | /listings/{id} | Save a wizard step (autosave). | Bearer (owner) | Partial listing fields | {listing} | 403 not owner; 400 validation | PROPERTY | MVP | NOT STARTED
API-19 | Listing | GET | /listings/{id} | Read own listing including draft state. | Bearer (owner) | — | {listing} | 403; 404 | PROPERTY | MVP | NOT STARTED
API-20 | Listing | POST | /listings/{id}/publish | Submit the listing for screening. | Bearer (owner) | {} | {status: UNDER_SCREENING} | 403; 409 incomplete; 429 quota exceeded | PROPERTY, QUOTA_LEDGER, MODERATION_TASK | MVP | NOT STARTED
API-21 | Listing | DELETE | /listings/{id} | Delete or withdraw a listing. | Bearer (owner) | — | 204 | 403; 404 | PROPERTY | MVP | NOT STARTED
API-22 | Listing | POST | /listings/{id}/renew | Extend a listing before expiry. | Bearer (owner) | {} | {expires_at} | 403; 409 not renewable | PROPERTY | MVP | NOT STARTED
API-23 | Listing | GET | /listings/mine | List the seller's own listings by state. | Bearer (seller) | ?status=&page= | {results[], counts_by_status} | 401 | PROPERTY | MVP | NOT STARTED
API-24 | Media | POST | /media/presign | Get a presigned URL for direct upload. | Bearer (owner) | {listing_id, filename, content_type, bytes} | {upload_url, storage_key, expires_in} | 403; 413 too large; 415 wrong type | PROPERTY_MEDIA | MVP | NOT STARTED
API-25 | Media | POST | /media/confirm | Confirm an upload and queue processing. | Bearer (owner) | {listing_id, storage_key} | {media_id, status: PROCESSING} | 403; 404 | PROPERTY_MEDIA, OUTBOX | MVP | NOT STARTED
API-26 | Media | PATCH | /media/{id} | Reorder, caption or set the primary image. | Bearer (owner) | {sort_order, is_primary, caption} | {media} | 403 | PROPERTY_MEDIA | MVP | NOT STARTED
API-27 | Media | DELETE | /media/{id} | Remove a photo. | Bearer (owner) | — | 204 | 403; 409 last remaining photo | PROPERTY_MEDIA | MVP | NOT STARTED
API-28 | Favorites | POST | /favorites | Save a listing. | Bearer | {property_id} | {saved: true} | 401; 409 already saved | FAVORITE | MVP | NOT STARTED
API-29 | Favorites | DELETE | /favorites/{property_id} | Remove a saved listing. | Bearer | — | 204 | 401; 404 | FAVORITE | MVP | NOT STARTED
API-30 | Favorites | GET | /favorites | List saved listings. | Bearer | ?page= | {results[]} | 401 | FAVORITE, PROPERTY | MVP | NOT STARTED
API-31 | Leads | POST | /inquiries | Send a written enquiry to a seller. | Bearer | {property_id, message, contact} | {inquiry_id} | 401; 429 rate limited; 409 duplicate | INQUIRY | MVP | NOT STARTED
API-32 | Leads | POST | /inquiries/reveal | Record the lead and return seller contact details. | Bearer + verified phone | {property_id} | {seller_contact, inquiry_id} | 401; 403 phone unverified; 429 daily limit | INQUIRY, USER | MVP | NOT STARTED
API-33 | Leads | GET | /leads | Seller's lead inbox. | Bearer (seller) | ?type=&status=&page= | {results[], counts} | 401; 403 | INQUIRY | MVP | NOT STARTED
API-34 | Leads | PATCH | /leads/{id} | Update lead status or notes. | Bearer (seller) | {seller_status, seller_notes} | {lead} | 403; 404 | INQUIRY | MVP | NOT STARTED
API-35 | Stats | GET | /listings/{id}/stats | Views, saves and contacts for one listing. | Bearer (owner) | ?period= | {views, saves, inquiries, reveals, series[]} | 403; 404 | SEARCH_EVENT, INQUIRY | MVP | NOT STARTED
API-36 | Events | POST | /events | Record client-side analytics events. | Public/Bearer | {events[]} | 202 | 400 malformed; 429 | SEARCH_EVENT | MVP | NOT STARTED
API-37 | Moderation | GET | /admin/moderation | List listings awaiting review. | Admin | ?status=&page= | {results[], queue_depth} | 401; 403 | MODERATION_TASK | MVP | NOT STARTED
API-38 | Moderation | POST | /admin/moderation/{id}/decision | Approve or reject a listing with a reason. | Admin | {decision, reason_code, notes} | {status} | 403; 409 already decided | MODERATION_TASK, PROPERTY, AUDIT_LOG | MVP | NOT STARTED
API-39 | Moderation | POST | /reports | Report a listing. | Bearer | {property_id, reason_code, details} | {report_id} | 401; 429 | REPORT | MVP | NOT STARTED
API-40 | Moderation | GET | /admin/reports | List abuse reports by SLA urgency. | Admin | ?status=&page= | {results[]} | 403 | REPORT | MVP | NOT STARTED
API-41 | Verification | POST | /verification | Submit captured evidence for listing verification. | Bearer (owner) | {listing_id, media_ids[], captured_geo, captured_at} | {request_id, status} | 403; 422 location mismatch | VERIFICATION_REQUEST | MVP | NOT STARTED
API-42 | Admin | GET | /admin/users | Search and inspect accounts. | Admin | ?q=&page= | {results[]} | 403 | USER | MVP | NOT STARTED
API-43 | Admin | PATCH | /admin/users/{id} | Suspend or restore an account. | Admin | {status, reason} | {user} | 403 | USER, AUDIT_LOG | MVP | NOT STARTED
API-44 | Admin | GET | /admin/audit | Read the audit trail. | Admin | ?entity=&actor=&page= | {results[]} | 403 | AUDIT_LOG | MVP | NOT STARTED
API-45 | Admin | POST | /admin/locations | Add or correct a place. | Admin | {parent_id, type, name, centroid} | {location} | 403; 409 duplicate | LOCATION, AUDIT_LOG | MVP | NOT STARTED
API-46 | SEO | GET | /sitemap.xml | Sitemap index for crawlers. | Public | — | XML | — | PROPERTY, LOCATION | MVP | NOT STARTED
API-47 | Saved search | POST | /saved-searches | Store a search and subscribe to alerts. | Bearer | {name, filter_json, alert_frequency} | {saved_search} | 401 | SAVED_SEARCH | FUTURE (v1.1) | NOT STARTED
API-48 | Billing | POST | /subscriptions | Purchase a seller plan. | Bearer (seller) | {plan_code} | {subscription, payment_url} | 403; 402 payment required | SUBSCRIPTION, PAYMENT | FUTURE (v1.3) | NOT STARTED
API-49 | Billing | POST | /webhooks/payments | Receive payment status from the gateway. | Signature-verified | Gateway payload | 200 | 401 bad signature; 409 replay | PAYMENT, SUBSCRIPTION | FUTURE (v1.3) | NOT STARTED
API-50 | Health | GET | /health | Liveness and dependency check for monitoring. | Public | — | {status, db, cache, version} | 503 dependency down | — | MVP | NOT STARTED

## UI-UX CHECKLIST
UI/UX CHECKLIST — design system and interface work
The design system must be ORIGINAL. Extract principles from the research, never the competitor's colours, fonts or visual identity.
Area | Item | What To Build | Why It Matters | MVP/Future | Status | Source
Design system | Design tokens | Define colour, spacing, radius and elevation as named variables. | Stops the interface drifting into inconsistency; makes dark mode cheap later. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Design system | Original visual identity | Create a colour palette and identity that is entirely your own. | Copying a competitor's trade dress is the one part of this project with real legal exposure. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Typography | Font family | Choose one UI font with Indic script coverage if localisation is ever planned. | Font changes late are disruptive and affect performance. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Typography | Type scale | Adopt a consistent scale (e.g. 12/14/16/18/20/25/31/39/49). | Arbitrary font sizes make a UI look amateur. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Typography | Tabular numerals | Enable tabular figures for price, area and statistics. | Numbers in lists must align to be comparable at a glance. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Colour | Semantic tokens | Name colours by role (primary, trust, danger) not by hue. | Lets you change the palette without touching components. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Colour | Contrast compliance | Meet WCAG AA contrast on all text. | Legal requirement and readability on phones in daylight. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Colour | Never colour alone | Pair every colour-coded meaning with an icon or text. | Colour-blind users cannot decode colour-only signals. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Colour | Dark mode tokens | Define the dark palette from the start, even if shipped later. | Retrofitting dark mode is far harder than planning for it. | FUTURE | NOT STARTED | OBSERVED FROM RESEARCH
Spacing | 4px spacing scale | Use 4/8/12/16/24/32/48/64 only. | Consistent rhythm is most of what makes a UI feel designed. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Spacing | Grid and containers | Define container widths and column counts per breakpoint. | Keeps layouts predictable across pages. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Components | Buttons | Primary, secondary, tertiary and danger variants in three sizes with all states. | Every screen needs them; inconsistency here is highly visible. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Components | Inputs | Text, number, select, date, textarea with label, helper and error slots. | Reserved error space prevents layout jumping during validation. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Components | Chips | Filter chips (toggle) and applied chips (removable). | The main way users see and undo their filters. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Components | Badges | Verified, RERA, New, Price Reduced. | Trust signals must be instantly recognisable. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Components | Cards | Base card container with border and elevation rules. | Prefer borders over shadows in long lists for paint performance. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Property card | Media area | Fixed 4:3 ratio, carousel, image counter, media-type badge. | Fixed ratio prevents layout shift; 4:3 shows interiors better than 16:9. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Property card | Price hierarchy | Price is the largest element, with price-per-area secondary. | Price is the primary comparison field. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Property card | Explicit area basis | Always label whether area is carpet, built-up or super. | The most misleading field in Indian real estate if left ambiguous. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Property card | Single primary action | Exactly one filled button per card. | Two competing filled buttons reduce clicks on both. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Property card | Seller type + freshness | Show owner/agent/builder and how recently it was posted. | Both are top-three trust signals for buyers. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Property card | Responsive variants | Horizontal card on phones, vertical in grids. | Vertical cards show only ~1.5 results per phone screen. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Search | Search entry point | Full-screen sheet on mobile, inline bar on desktop. | Multi-field inline entry does not work on a phone. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Search | Multi-select location chips | Allow several localities in one search. | Real users search 'Salt Lake OR New Town', not one locality. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Search | Typeahead grouping | Group suggestions by city, locality, society, with counts. | Users type all of these interchangeably. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Search | Recent searches | Persist and re-offer recent searches. | Property search runs over weeks, across many sessions. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Filters | Desktop filter rail | Sticky left rail, collapsible groups, counts per option. | Familiar, persistent and fast to scan. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Filters | Mobile filter sheet | Full-screen sheet with a live count on the Apply button. | Lets users tune before committing to a reload. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Filters | Disabled zero-count options | Show options with zero results as disabled, never hidden. | Hiding options makes the filter look broken. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Filters | Non-linear range sliders | Denser resolution where most inventory sits, plus numeric inputs. | A linear budget slider makes the common range unselectable. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Filters | State preservation | Filter and sort changes never lose scroll, state or results. | The incumbent's single most-complained-about failure. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Navigation | Header | Logo left, intent links, distinct Post Property action, account. | Logo-left is an escape-hatch convention; breaking it costs task success. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Navigation | Mobile bottom navigation | Search, Saved, Post, Leads, Account. | App-like convention expected by a mobile-majority audience. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Navigation | Breadcrumbs | Visible breadcrumb reflecting the location hierarchy. | Orientation for users and structure for search engines. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Navigation | SEO footer | Grouped links by city, intent and type. | Distributes crawl authority into the long tail. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Modals | Modal and sheet behaviour | Focus trap, Escape to close, scroll lock, focus restored on close. | Without these, keyboard and screen-reader users become trapped. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Toasts | Toast notifications | Non-blocking confirmations for save, copy and alert actions. | Confirms an action without interrupting the task. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
States | Empty states | Every list has a designed empty state with a next action. | An empty screen with no guidance reads as a broken screen. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
States | Zero-result recovery | Name the blocking filter, offer radius expansion and alerts. | Property searches are over-constrained constantly. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
States | Loading skeletons | Skeletons matching final dimensions exactly, not spinners. | Prevents layout shift and feels faster than a spinner. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
States | Error states | Inline retry that preserves filters and context. | Never dump the user back to the homepage on an error. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
States | Offline state | Tell the user when they are offline and what still works. | Mobile connectivity is unreliable. | FUTURE | NOT STARTED | OBSERVED FROM RESEARCH
Gallery | Photo gallery | Swipe on touch, arrows on pointer, keyboard arrows, counter, lightbox. | Photos are the most-used element on the detail page. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Gallery | Lazy loading | Only the first image loads eagerly. | Images are the dominant byte cost of the page. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Gallery | No autoplay | Carousels never advance on their own. | Auto-advancing carousels are disorienting and hurt accessibility. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Contact CTA | Sticky contact module | Sticky right rail on desktop, sticky bottom bar on mobile. | The user must never scroll to a position with no way to contact. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Contact CTA | Two-tier contact | Enquire (low friction) and View Number (verified). | Captures both lower-intent and higher-intent buyers. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Posting wizard | Step indicator | Show progress and let users move between completed steps. | Long forms need a visible sense of progress. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Posting wizard | Autosave indicator | Visibly confirm that progress is saved. | Reassurance directly reduces abandonment. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Posting wizard | Completeness score | Live score naming the highest-value missing field. | The cheapest available lever on listing quality. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Posting wizard | Mobile-first upload | Camera capture, compression, progress, retry. | Most sellers will post from a phone with poor connectivity. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Dashboard | Role-aware layout | Show buyer or seller tools according to the account's roles. | One account may be both; the interface must adapt. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Dashboard | Listing state clarity | Explain lifecycle states in plain language. | 'Under screening' means nothing to a first-time seller. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Dashboard | Lead inbox | Scannable list with status controls and notes. | Where sellers perceive the platform's value. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Admin UI | Density over beauty | Optimise admin screens for speed and information density. | Admin users are repetitive power users, not first-time visitors. | MVP | NOT STARTED | PROPOSED
Admin UI | Destructive action guards | Confirmation and undo for removals and suspensions. | Admin mistakes affect real users' listings and income. | MVP | NOT STARTED | PROPOSED
Responsive | Breakpoint specification | Define behaviour at 390, 412, 768, 1024, 1280+. | Most traffic will be mobile; desktop cannot be the default. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Responsive | Map behaviour | Exclusive toggle below 1024px; split view above. | A split map on a phone is unusable. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Responsive | Touch targets | Minimum 44x44px for every interactive element. | Smaller targets cause mis-taps and frustration. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Responsive | Thumb zone | Primary actions in the lower third on phones. | The most important button on a phone belongs at the bottom. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Accessibility | Visible focus ring | 2px ring with offset on every interactive element. | Never remove focus outlines without a replacement. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Accessibility | Keyboard navigation | Every journey completable by keyboard alone. | Legal requirement and a genuine usability improvement. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Accessibility | Form labels | Real labels, never placeholder-as-label. | Placeholders vanish on focus and are invisible to screen readers. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Accessibility | Meaningful alt text | Describe the image content, not 'image1'. | Accessibility requirement and an image-SEO benefit. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Accessibility | Live regions | Announce result-count changes to screen readers. | Otherwise filtering appears to do nothing. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Motion | Duration limits | 120ms micro, 200ms standard, 300ms maximum. | Slow animation makes a fast site feel slow. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Motion | Reduced motion | Honour prefers-reduced-motion by disabling transforms. | Motion can cause genuine physical discomfort. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Motion | No hover dependencies | Nothing reachable only by hover. | Touch devices have no hover. | MVP | NOT STARTED | OBSERVED FROM RESEARCH

## SEO CHECKLIST
SEO CHECKLIST — how people will find the site
Read this BEFORE building any page. URL structure and rendering decisions cannot be retrofitted cheaply. 'LATER' items are the programmatic scale-up after launch.
Area | Item | What To Do | Why It Matters | MVP/Later | Status | Source
URL architecture | Design routes before building | Agree every public URL pattern in Phase 2. | Retrofitting SEO-grade URLs onto a finished app is effectively a rewrite. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
URL architecture | Keyword-rich readable slugs | Put intent, config, type and place into the URL. | Observed on the incumbent; the slug carries the query terms users type. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
URL architecture | Typed ID suffix | Append a short typed ID to detail URLs (e.g. -p12345). | Guarantees uniqueness so slugs can be regenerated without breaking links. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
URL architecture | Two separate surfaces | Pretty SSR URLs are indexable; /search query URLs are not. | Keeps indexation controlled while still offering an app-like experience. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
URL architecture | Avoid subdomains | Keep builders, projects and agents on the main domain as paths. | Subdomains split authority and complicate analytics and sessions. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Canonical URLs | Canonical on every page | Point each filtered variant to its cleanest indexable form. | Prevents duplicate-content dilution across thousands of combinations. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Canonical URLs | Self-canonical on detail pages | Each listing canonicalises to itself. | Avoids accidental consolidation onto the wrong URL. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Index strategy | Allowlist indexable facets | Only named filter combinations may be indexed. | Uncontrolled facet indexation is the classic cause of portal demotion. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Index strategy | noindex the app surface | The interactive /search route must not be indexed. | It duplicates the landing pages with unstable parameters. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Thin content | Minimum inventory gate | Only index a page above an inventory threshold. | Thousands of near-empty pages are a liability, not an asset. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Thin content | Redirect below-threshold pages | Send them to the parent page with nearby inventory shown. | Preserves the user experience without indexing an empty page. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Metadata | Title templates per page type | Define one template per archetype. | Consistency at scale; hand-written titles do not scale to thousands of pages. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Metadata | Live counts in titles | Inject current inventory counts (e.g. '1,240+ flats'). | Confirmed technique on the incumbent; raises click-through and signals freshness. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Metadata | Count fallback | Never render '0+' if the count service fails. | A broken title is worse than a generic one. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Metadata | Dynamic freshness tokens | Include month/year on data pages that regenerate. | Observed on the incumbent's trend pages; wins 'now' queries without new content. | LATER | NOT STARTED | OBSERVED FROM RESEARCH
Metadata | Meta descriptions | Template descriptions including sub-inventory counts. | Observed technique; doubles as a value proposition in results. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Metadata | Open Graph / social cards | Add OG and Twitter card tags. | Listings are shared in messaging apps constantly in this market. | MVP | NOT STARTED | PROPOSED
Structured data | RealEstateListing JSON-LD | Mark up detail pages with offer, price and geo data. | Enables rich results and machine understanding. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Structured data | BreadcrumbList | Mark up breadcrumbs on every page. | Improves how results display in search. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Structured data | ItemList on results pages | Mark up result collections. | Helps engines interpret listing pages. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Structured data | FAQPage on FAQ blocks | Mark up templated question blocks. | Can win additional search real estate. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Structured data | Organization / WebSite | Site-level markup including a SearchAction. | Establishes entity identity for the brand. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Structured data | Validate markup | Test with Google's Rich Results Test. | Invalid markup is silently ignored. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Sitemap | Segmented sitemap index | Split by content type, max 50,000 URLs per file. | Required at scale and makes indexation problems diagnosable. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Sitemap | Accurate lastmod | Reflect genuine content changes. | False freshness signals erode crawler trust. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Sitemap | Remove expired listings | Drop removed listings promptly. | Leaving them in wastes crawl budget. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Sitemap | Nightly regeneration | Automate sitemap rebuilds. | Manual sitemaps go stale immediately. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Robots | robots.txt | Allow crawling of indexable areas; point to the sitemap index. | Controls crawl budget and discovery. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Robots | Do not block sitemap URLs | Ensure nothing in the sitemap is disallowed. | A very common and damaging misconfiguration. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Pagination | Path-based page URLs | Use /page/2 rather than ?page=2 for indexable pages. | Observed on the incumbent; path pages are independently indexable. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Pagination | Self-canonical paginated pages | Page 2 canonicalises to page 2, not page 1. | Canonicalising to page 1 hides deep inventory from the index. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Expired content | HTTP 410 for removed listings | Return 410 with a useful page offering alternatives. | Signals permanent removal and recovers the visit. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Expired content | Automatic expiry | Expire stale listings on a schedule. | Dead listings are both an SEO and a trust problem. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Internal linking | Generated link clusters | Nearby localities, budget bands, configurations, parent city. | Distributes authority into the long tail automatically. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Internal linking | Generate from the gazetteer | Never hand-author link clusters. | Hand-authored links cannot scale and go stale. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Locality pages | Locality hub pages | A page per locality with summary and inventory rails. | Captures research intent that listings alone cannot. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Locality pages | City hub pages | Top-level geographic entry points. | Crawl distribution and user orientation. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Image SEO | Descriptive alt text | Generate alt text from listing attributes. | Image search traffic plus accessibility. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Image SEO | Descriptive filenames | Use meaningful storage filenames where practical. | Minor but cheap ranking signal. | LATER | NOT STARTED | PROPOSED
Core Web Vitals | Performance as a ranking factor | Meet the budgets in the PERFORMANCE sheet. | Speed is a confirmed ranking input and a conversion factor. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Search Console | Verify the property | Set up Google Search Console before launch. | How you discover indexation problems. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Search Console | Submit sitemaps | Submit the sitemap index and monitor coverage. | Coverage errors are invisible otherwise. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Search Console | Weekly coverage review | Check indexation, errors and Core Web Vitals weekly. | Problems compound silently if unmonitored. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Programmatic SEO | Landing matrix generation | Generate city x type x budget x config pages from data. | The incumbent's core acquisition machine. | LATER | NOT STARTED | OBSERVED FROM RESEARCH
Programmatic SEO | Governance rules | Every generated page must pass the thin-content gate. | Generate the matrix, but govern it. | LATER | NOT STARTED | OBSERVED FROM RESEARCH
Programmatic SEO | Monitor index bloat | Watch indexed-page count against intended count. | Early warning of uncontrolled generation. | LATER | NOT STARTED | OBSERVED FROM RESEARCH
Hreflang | Multi-language tags | Only if multi-language is ever built. | Not applicable to a single-language launch. | FUTURE | NOT STARTED | PROPOSED

## SECURITY CHECKLIST
SECURITY CHECKLIST — protecting users, data and the business model
Every CRITICAL item must be DONE before launch. Nothing here involves bypassing anyone else's security — these are controls for YOUR system.
Area | Control | What To Do | Why It Matters | Priority | Status | Source
Authentication | OTP as primary login | Phone-based one-time codes as the main login method. | Appropriate for the Indian market where phone is the primary identity. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Authentication | Hash OTP codes at rest | Store a hash of the code, never the code itself. | A database leak must not expose live codes. | CRITICAL | NOT STARTED | PROPOSED
Authentication | Single-use codes | Consume the code on first successful use. | Prevents replay of an intercepted code. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Authentication | Short expiry | Expire codes within a few minutes. | Limits the window for interception. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Authentication | Attempt limits | Lock the challenge after a small number of wrong attempts. | Prevents brute-forcing a 6-digit code. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
OTP security | Per-number rate limits | Cap OTP requests per phone number per hour. | Without this your SMS bill becomes the attack surface. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
OTP security | Per-IP rate limits | Cap OTP requests per IP address. | Stops distributed abuse from one source. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
OTP security | Exponential backoff | Increase the delay after each repeated request. | Makes automated abuse uneconomic. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
OTP security | Monitor spend | Alert on abnormal SMS volume. | Detects abuse before the bill arrives. | HIGH | NOT STARTED | PROPOSED
Authorization | Server-side checks on every endpoint | Never rely on the client hiding a button. | Client-side role checks are decoration, not security. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Authorization | Object-level ownership checks | Verify the requester owns the listing or lead they are acting on. | Broken object-level access control is the most common serious API flaw. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Authorization | Role permission matrix | Document which role may perform which action. | You cannot test what you have not specified. | CRITICAL | NOT STARTED | PROPOSED
Authorization | Automated authorization tests | Test cross-role access attempts in CI. | Regressions here are silent and severe. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Input validation | Validate every input server-side | Use a schema validator on all request bodies and parameters. | Client validation is a convenience feature only. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Input validation | Reject unknown fields | Do not silently accept unexpected properties. | Prevents mass-assignment style attacks. | HIGH | NOT STARTED | PROPOSED
Input validation | Bound numeric ranges | Reject absurd prices, areas and page numbers. | Prevents both abuse and accidental data corruption. | HIGH | NOT STARTED | PROPOSED
File upload | Validate real content type | Inspect actual file content, not the declared type or extension. | Renaming a script to .jpg is a classic bypass. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
File upload | Enforce size limits | Enforce limits on the presigned URL, not just in the browser. | Client-side limits are trivially bypassed. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
File upload | Strip EXIF metadata | Remove metadata from uploaded photos. | Photo GPS data can reveal a person's home address. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
File upload | Serve media from a separate origin | Host user media on a distinct domain or subdomain. | Contains the damage if a malicious file is ever served. | HIGH | NOT STARTED | PROPOSED
File upload | Scan for embedded contact details | OCR images to detect phone numbers and emails. | Protects the lead model and prevents off-platform scams. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
Rate limiting | Search endpoint limits | Rate-limit search and facet endpoints. | Prevents cheap denial of service and bulk scraping. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Rate limiting | Contact reveal limits | Cap reveals per account per day. | Prevents bulk harvesting of seller phone numbers. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Rate limiting | Write endpoint limits | Rate-limit listing creation and media uploads. | Prevents spam flooding. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
API protection | Consistent error responses | Never leak stack traces or internal details to clients. | Error detail is reconnaissance for an attacker. | CRITICAL | NOT STARTED | PROPOSED
API protection | Request size limits | Cap request body size. | Prevents memory-exhaustion attacks. | HIGH | NOT STARTED | PROPOSED
API protection | CORS policy | Allow only your own origins. | Prevents other sites calling your API as your users. | HIGH | NOT STARTED | PROPOSED
XSS | Escape all user content | Never render user text as HTML. | Listing descriptions are user-supplied and shown publicly. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
XSS | Content-Security-Policy | Restrict which scripts may execute. | Strong defence in depth if an escaping bug slips through. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
XSS | Sanitise rich text | If rich text is ever allowed, allowlist tags strictly. | Blocklists are always incomplete. | HIGH | NOT STARTED | PROPOSED
CSRF | Protect cookie-based state changes | Use anti-CSRF tokens wherever cookies authenticate requests. | Not needed for pure bearer-token APIs, but essential if cookies are used. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
CSRF | SameSite cookie attributes | Set SameSite on any session cookie. | Cheap and effective mitigation. | HIGH | NOT STARTED | PROPOSED
SQL injection | Parameterised queries only | Use an ORM or bound parameters; never concatenate SQL. | Still among the most damaging vulnerabilities. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
SQL injection | Review raw SQL | Audit every hand-written query, especially in search. | Search code is where raw SQL usually appears. | CRITICAL | NOT STARTED | PROPOSED
Secrets | No secrets in Git | Keep credentials out of the repository, including history. | Leaked credentials are among the most damaging incidents. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Secrets | Managed secret store | Store secrets in a proper secret manager. | Environment files on servers get copied and leaked. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Secrets | Rotation procedure | Document how to rotate every credential. | You need this ready before an incident, not during one. | HIGH | NOT STARTED | PROPOSED
Transport | HTTPS everywhere + HSTS | Force TLS and enable HSTS. | Protects credentials and OTPs in transit. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Transport | Security headers | Set CSP, X-Content-Type-Options, Referrer-Policy and frame protections. | Cheap, broad protection. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
Audit logs | Log administrative actions | Record actor, action, entity, before and after, immutably. | Accountability and dispute resolution. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Audit logs | Log lead data access | Record every read of buyer contact details. | This is your most sensitive data. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Audit logs | Protect log integrity | Make logs append-only and restrict deletion. | Logs an attacker can edit are worthless. | HIGH | NOT STARTED | PROPOSED
Admin security | Second factor for admins | Require a second authentication factor for admin accounts. | Admin accounts are the highest-value target. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Admin security | Separate admin surface | Keep admin on a distinct path with its own access rules. | Reduces exposure of administrative endpoints. | HIGH | NOT STARTED | PROPOSED
Admin security | Least privilege | Give staff the narrowest role that lets them work. | Limits the blast radius of a compromised account. | HIGH | NOT STARTED | PROPOSED
Abuse prevention | Duplicate listing detection | Perceptual image hashing plus text similarity. | Duplicates are the category's top user complaint. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Abuse prevention | Owner-vs-agent detection | Flag accounts claiming owner status while behaving like agents. | 'Posted by owner' carries a trust premium worth gaming. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
Abuse prevention | Report and review loop | Let users report, and resolve reports within an SLA. | Your users are your largest moderation workforce. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Abuse prevention | Account suspension | Ability to suspend abusive accounts quickly. | Needed the first time it happens, not after. | HIGH | NOT STARTED | PROPOSED
Contact protection | Never expose contact before reveal | Ensure contact fields are absent from API responses pre-reveal. | Hiding in the UI while sending in the payload is a real and common leak. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Contact protection | Record the lead before revealing | Write the inquiry first, then display the number. | If the write fails after display, you lose the lead and the revenue. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Contact protection | Number masking (future) | Route calls through a proxy number. | Protects sellers from long-term spam; a genuine differentiator. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
Duplicate prevention | Deduplicate repeat reveals | Use a dedupe key so repeat views are not billed twice. | Revenue integrity; double-charging destroys seller trust. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Duplicate prevention | Idempotent write endpoints | Support idempotency keys on create operations. | Prevents duplicates from retries and double-taps. | HIGH | NOT STARTED | PROPOSED
Data protection | Encrypt PII at rest | Encrypt personal data in the database. | Legal obligation and limits breach impact. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Data protection | Data retention policy | Define how long leads and accounts are kept. | Required under India's data-protection law. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
Data protection | Consent capture | Record consent for marketing communications. | Legal requirement; also reduces complaints. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
Data protection | Breach response plan | Write the plan before you need it. | Response time determines legal and reputational damage. | HIGH | NOT STARTED | PROPOSED
Review | Independent security review | Have someone other than the builder review before launch. | You cannot review your own blind spots. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Review | Dependency vulnerability scanning | Automate scanning of third-party packages. | Most vulnerabilities arrive through dependencies. | HIGH | NOT STARTED | PROPOSED

## TESTING & QA
TESTING & QA — what to test and what 'passing' means
Every row has a concrete acceptance criterion. If you cannot tell whether it passed, the criterion is not specific enough.
Test Area | Test Type | What To Test | Acceptance Criteria | MVP/Future | Status | Source
Strategy | Planning | Decide the mix of unit, integration and end-to-end tests. | A written test strategy exists and is followed in CI. | MVP | NOT STARTED | PROPOSED
Business logic | Unit | Quota calculation, price formatting, area conversion, completeness score. | All core calculations covered; edge cases (zero, negative, very large) included. | MVP | NOT STARTED | PROPOSED
Business logic | Unit | Listing state machine transitions. | Every legal transition passes; every illegal transition is rejected. | MVP | NOT STARTED | PROPOSED
Business logic | Unit | Filter object normalisation from both URL forms. | Pretty URL and query URL produce an identical filter object. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Business logic | Unit | Relevance ranking function. | Ranking is deterministic and reproducible for a fixed input set. | MVP | NOT STARTED | PROPOSED
Authentication | Integration | OTP request, verify, expiry, reuse and attempt limits. | Expired and reused codes are rejected; limits enforced. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Authentication | Integration | Token refresh and refresh-token reuse detection. | Reuse of a rotated refresh token revokes the session family. | MVP | NOT STARTED | PROPOSED
Authentication | Integration | Phone change invalidates other sessions. | Old sessions cannot act after a phone change. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Authorization | Integration | Cross-role access attempts on every endpoint. | A buyer token cannot read or modify another user's listings or leads. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Authorization | Integration | Object ownership checks. | User A cannot edit user B's listing by guessing an ID. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Property posting | E2E | Complete the wizard end to end on a mobile viewport. | Listing created, screened and published successfully. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Property posting | E2E | Draft autosave and resume after a browser refresh. | No entered data is lost after refresh or navigation away. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Property posting | Integration | Photo upload, processing, EXIF strip and variant generation. | Variants exist; EXIF removed; fingerprint computed. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Property posting | Integration | Contact-detail sanitisation in descriptions. | Obfuscated phone numbers and emails are removed or flagged. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Property posting | Integration | Quota enforcement on publish. | Publishing beyond quota is blocked with a clear message. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Search | Integration | Each filter individually and in combination. | Results match the filter criteria exactly, verified against seeded data. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Search | Integration | Facet counts exclude their own facet selection. | Counts match a manually computed expectation. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Search | Integration | Sort purity. | Explicit sorts are strictly ordered with no promoted interleaving. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Search | E2E | Filter state preservation. | CRITICAL: no filter or sort change loses scroll, state or results, even when the API errors. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Search | E2E | Browser back and forward behaviour. | Back returns to the previous filter state, not the homepage. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Search | Integration | Zero-result relaxation ladder. | Relaxation triggers in order and the user is told what changed. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Search | Integration | Pagination on both surfaces. | Path pages and infinite scroll return consistent, non-overlapping results. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Search | Performance | Search latency under realistic data volume. | p95 within the PERFORMANCE sheet budget. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Leads | E2E | Enquiry submission end to end. | Enquiry reaches the seller inbox and notifies them. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Leads | E2E | OTP-gated contact reveal. | Lead is recorded before the number is displayed. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Leads | Integration | Duplicate reveal deduplication. | A repeat reveal within the window creates no new billable lead. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Leads | Integration | Reveal rate limiting. | Daily cap enforced server-side and clearly explained to the user. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Leads | Security | Contact details absent from API payloads before reveal. | Inspecting the raw network response shows no seller phone number. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Admin | E2E | Moderation approve and reject with reason. | Decision applied, seller notified, audit entry written. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Admin | E2E | Report handling. | Report enters the queue, is actioned and closed with an audit entry. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Admin | Integration | Audit log completeness. | Every admin state change produces exactly one immutable log entry. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
API | Contract | Every endpoint's success and failure responses. | All documented error cases return the documented status and shape. | MVP | NOT STARTED | PROPOSED
API | Integration | Idempotency on create endpoints. | Repeated submission does not create duplicates. | MVP | NOT STARTED | PROPOSED
Mobile | Device | Core journeys on a real mid-range Android device. | Search, post and contact complete successfully on real hardware. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Mobile | Device | Photo upload on a slow mobile connection. | Upload completes or fails gracefully with retry. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Responsive | Visual | Layout at 390, 412, 768, 1024 and 1280px. | No horizontal scroll, no overlap, no clipped content at any width. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Responsive | Visual | Sticky elements at each breakpoint. | Contact bar and filter controls behave as specified. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Browser | Compatibility | Chrome, Safari, Firefox and Edge on current versions. | No blocking defect in any supported browser. | MVP | NOT STARTED | PROPOSED
Browser | Compatibility | iOS Safari specifically. | Sticky elements, viewport height and date inputs behave correctly. | MVP | NOT STARTED | PROPOSED
Accessibility | Automated | Automated accessibility scan on key pages. | No critical violations reported. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Accessibility | Manual | Keyboard-only completion of search and contact journeys. | Both journeys completable without a mouse. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Accessibility | Manual | Screen-reader review of results and detail pages. | Result count changes are announced; images have meaningful alt text. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Accessibility | Manual | Focus visibility audit. | Every interactive element shows a visible focus indicator. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
SEO | Automated | Metadata presence on every page type. | Title, description and canonical present and correctly templated. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
SEO | Automated | Structured data validity. | JSON-LD validates without errors. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
SEO | Automated | Indexation directives. | App surface is noindex; below-threshold pages are noindex. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
SEO | Automated | Sitemap correctness. | All sitemap URLs return 200 and none are disallowed by robots.txt. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
SEO | Manual | Server-rendered content check. | Viewing page source shows listing content without JavaScript. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Performance | Synthetic | Lighthouse on five representative routes in CI. | All budgets in the PERFORMANCE sheet met; build fails otherwise. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Performance | Load | Search and detail pages under projected peak traffic. | Latency budgets held at peak; no error-rate increase. | MVP | NOT STARTED | PROPOSED
Performance | Field | Real user monitoring after launch. | Field p75 Core Web Vitals within budget. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Security | Automated | Dependency vulnerability scan. | No unresolved critical or high vulnerabilities. | MVP | NOT STARTED | PROPOSED
Security | Manual | Authorization and access-control review. | No endpoint allows cross-user access. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Security | Manual | File upload abuse testing. | Non-image content is rejected even when renamed. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Security | Review | Independent pre-launch security review. | All critical and high findings resolved. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
User acceptance | Manual | Five external users post a property unaided. | At least 4 of 5 complete it; median time within 8 minutes. | MVP | NOT STARTED | OBSERVED FROM RESEARCH
User acceptance | Manual | Five external users find and contact a listing unaided. | At least 4 of 5 complete it without assistance. | MVP | NOT STARTED | PROPOSED
Production | Smoke | Critical journeys against the live site after deploy. | Post, search, contact and OTP all verified on production. | MVP | NOT STARTED | PROPOSED
Production | Monitoring | Alerts fire correctly for a simulated failure. | A real person receives the alert within the target time. | MVP | NOT STARTED | PROPOSED
Regression | Automated | Full suite runs on every main-branch build. | Suite is green before any production deploy. | MVP | NOT STARTED | PROPOSED

## PERFORMANCE
PERFORMANCE — hard speed targets
These budgets come from the research document. Measure on a throttled mid-range Android on simulated 4G, never on a developer laptop. Being measurably faster than the incumbent is this product's clearest differentiator.
Metric | What It Means (plain English) | Target | Hard Fail | How To Measure | Status | Source
LCP — Largest Contentful Paint (mobile, p75) | How long until the biggest thing on screen appears. The main 'does this feel fast' number. | <= 2.0 s | > 2.5 s | Lighthouse in CI + real user monitoring, throttled mid-range Android on simulated 4G | NOT STARTED | OBSERVED FROM RESEARCH
CLS — Cumulative Layout Shift | How much the page jumps around while loading. Zero is ideal. | <= 0.05 | > 0.1 | Lighthouse + RUM; check result cards and the image gallery specifically | NOT STARTED | OBSERVED FROM RESEARCH
INP — Interaction to Next Paint | How quickly the page responds when you tap or click something. | <= 150 ms | > 200 ms | RUM in the field; test filter and sort interactions specifically | NOT STARTED | OBSERVED FROM RESEARCH
TTFB — Time To First Byte (SSR, p75) | How long the server takes to start sending the page. | <= 400 ms | > 800 ms | Server timing headers + RUM; measure landing pages and detail pages | NOT STARTED | OBSERVED FROM RESEARCH
JavaScript transferred (search route) | How much code the browser downloads for the search page. | <= 180 KB gzip | > 250 KB | Bundle analyser in CI; fail the build on breach | NOT STARTED | OBSERVED FROM RESEARCH
CSS transferred | How much styling code is downloaded. | <= 40 KB gzip | > 60 KB | Bundle analyser in CI | NOT STARTED | OBSERVED FROM RESEARCH
Image bytes above the fold | Weight of images visible before scrolling. Usually the biggest cost. | <= 150 KB | > 250 KB | Lighthouse network audit on results and detail pages | NOT STARTED | OBSERVED FROM RESEARCH
Requests to first render | How many separate network calls are needed before the page is usable. | <= 25 | > 40 | Lighthouse network panel audit | NOT STARTED | OBSERVED FROM RESEARCH
Search API latency (p95) | How long the slowest 5% of searches take on the server. | <= 300 ms | > 600 ms | Application performance monitoring at realistic data volume | NOT STARTED | OBSERVED FROM RESEARCH
Typeahead latency (p95) | How long autocomplete suggestions take to appear. | <= 120 ms | > 250 ms | APM; must be measured against the dedicated suggest table | NOT STARTED | OBSERVED FROM RESEARCH
Filter/sort error rate | How often a filter or sort action fails. | < 0.1 % | > 0.5 % | Error monitoring with a dedicated alert on these actions | NOT STARTED | OBSERVED FROM RESEARCH
Test conditions | The device and network profile all budgets are measured on. | Throttled mid-range Android, simulated 4G | Developer laptop on office wifi | Configure Lighthouse and device testing to this profile | NOT STARTED | OBSERVED FROM RESEARCH

## DEVOPS & DEPLOYMENT
DEVOPS & DEPLOYMENT — running the system safely
The backup RESTORE DRILL is the item most often assumed and never verified. An untested backup is not a backup.
Area | Item | What To Do | Why It Matters | Phase | Status | Source
Repository | Create the repository | Set up Git hosting with a README, licence and .gitignore. | Single source of truth for code and history. | Phase 1 | NOT STARTED | PROPOSED
Repository | Protect the main branch | Require pull requests and passing checks before merge. | Prevents broken code reaching production. | Phase 1 | NOT STARTED | PROPOSED
Repository | CODEOWNERS | Define who reviews which parts of the codebase. | Useful the moment more than one person contributes. | Phase 1 | NOT STARTED | PROPOSED
Branch strategy | Define branching rules | Short-lived feature branches merged into main via pull request. | Long-lived branches cause painful merges. | Phase 1 | NOT STARTED | PROPOSED
Branch strategy | Commit conventions | Adopt a consistent commit message format. | Makes history readable and enables automated changelogs. | Phase 1 | NOT STARTED | PROPOSED
Environment variables | Document every variable | Maintain a .env.example listing every variable with a description. | New environments are otherwise impossible to reproduce. | Phase 1 | NOT STARTED | PROPOSED
Environment variables | Never commit real values | Keep actual secrets out of the repository entirely. | Secrets in Git history are extremely hard to remove. | Phase 1 | NOT STARTED | OBSERVED FROM RESEARCH
Environments | Development environment | Local setup running with one command via Docker Compose. | Everyone develops against identical dependency versions. | Phase 1 | NOT STARTED | PROPOSED
Environments | Staging environment | A production-like environment with separate data. | Never test against production data. | Phase 19 | NOT STARTED | PROPOSED
Environments | Production environment | The live environment, isolated from all others. | Isolation prevents accidental data loss. | Phase 19 | NOT STARTED | PROPOSED
CI/CD | Continuous integration | Run lint, typecheck and tests on every pull request. | Catches problems before merge, while they are cheap. | Phase 1 | NOT STARTED | PROPOSED
CI/CD | Performance gate | Fail the build when a performance budget is breached. | Performance debt compounds and is expensive to repay. | Phase 16 | NOT STARTED | OBSERVED FROM RESEARCH
CI/CD | Automated deployment to staging | Merging to main deploys to staging automatically. | Manual deploys are where mistakes happen. | Phase 19 | NOT STARTED | PROPOSED
CI/CD | Controlled production deployment | Deploy to production on an explicit, logged action. | Production changes should be deliberate. | Phase 19 | NOT STARTED | PROPOSED
Database | Versioned migrations | All schema changes go through migration files. | Manual production schema edits cause outages. | Phase 4 | NOT STARTED | OBSERVED FROM RESEARCH
Database | Reversible migrations | Every migration has a tested rollback path. | You will need to undo one eventually. | Phase 19 | NOT STARTED | PROPOSED
Database | Zero-downtime migration practice | Add columns before using them; remove only after deploy. | Avoids breaking the running application mid-deploy. | Phase 19 | NOT STARTED | PROPOSED
Database | Connection pooling | Configure a connection pool sized to the workload. | Exhausted connections take the whole site down. | Phase 4 | NOT STARTED | PROPOSED
Backups | Automated daily backups | Schedule automated database backups with retention. | Data loss is the one truly unrecoverable failure. | Phase 19 | NOT STARTED | OBSERVED FROM RESEARCH
Backups | Point-in-time recovery | Enable transaction-log based recovery if available. | Lets you recover to just before a mistake. | Phase 19 | NOT STARTED | PROPOSED
Backups | Restore drill | Actually restore a backup into a clean environment. | An untested backup is not a backup. Do not skip this. | Phase 19 | NOT STARTED | OBSERVED FROM RESEARCH
Backups | Offsite copy | Keep at least one backup copy in a separate location. | Protects against a provider-level failure. | Phase 19 | NOT STARTED | PROPOSED
Monitoring | Uptime monitoring | External checks on the site and key endpoints. | Tells you the site is down before users do. | Phase 19 | NOT STARTED | PROPOSED
Monitoring | Application performance monitoring | Track endpoint latency and throughput. | Finds slow endpoints before they become outages. | Phase 19 | NOT STARTED | PROPOSED
Monitoring | Alerting with a recipient | Route alerts to a person who will actually see them. | Alerts nobody receives are decoration. | Phase 19 | NOT STARTED | OBSERVED FROM RESEARCH
Monitoring | Business metric alerts | Alert if leads or listings drop sharply. | Catches silent failures that technical monitoring misses. | Phase 20 | NOT STARTED | PROPOSED
Error tracking | Frontend and backend error capture | Install error tracking on both sides with release tagging. | You cannot fix errors you never hear about. | Phase 15 | NOT STARTED | OBSERVED FROM RESEARCH
Error tracking | Filter/sort error alert | A dedicated alert on search interaction failures. | The specific failure the incumbent's users complain about. | Phase 15 | NOT STARTED | OBSERVED FROM RESEARCH
Logging | Structured logs | Log as structured data with a request ID on every entry. | Lets you trace one request across services. | Phase 4 | NOT STARTED | PROPOSED
Logging | Centralised aggregation | Ship logs to one searchable place. | Debugging production without logs is guesswork. | Phase 19 | NOT STARTED | PROPOSED
Logging | Never log secrets or PII | Redact tokens, OTPs and personal data from logs. | Logs are widely accessible and frequently exported. | Phase 4 | NOT STARTED | OBSERVED FROM RESEARCH
Logging | Retention policy | Define how long logs are kept. | Cost control and data-protection compliance. | Phase 19 | NOT STARTED | PROPOSED
CDN | Static asset delivery | Serve assets from a CDN with long cache lifetimes. | The cheapest performance win available. | Phase 19 | NOT STARTED | OBSERVED FROM RESEARCH
CDN | HTML edge caching | Cache landing pages at the edge with stale-while-revalidate. | Large latency reduction for the highest-traffic pages. | Phase 19 | NOT STARTED | OBSERVED FROM RESEARCH
CDN | Image transformation | Resize and convert images at the edge. | Avoids storing dozens of variants per photo. | Phase 16 | NOT STARTED | PROPOSED
Object storage | Media bucket | Create a bucket for user-uploaded media. | Databases are the wrong place for images. | Phase 4 | NOT STARTED | OBSERVED FROM RESEARCH
Object storage | Presigned uploads | Upload directly from the browser to storage. | Keeps large uploads off the application server. | Phase 4 | NOT STARTED | OBSERVED FROM RESEARCH
Object storage | Lifecycle rules | Automatically clean up orphaned and abandoned uploads. | Storage cost grows silently otherwise. | Phase 19 | NOT STARTED | PROPOSED
Domain | Register the domain | Secure the domain and relevant variants. | Required before anything is publicly usable. | Phase 0 | NOT STARTED | DECISION REQUIRED
DNS | Configure DNS | Set up records with a reliable DNS provider. | DNS misconfiguration is a common launch-day failure. | Phase 19 | NOT STARTED | PROPOSED
SSL | TLS certificates | Enable HTTPS with automatic renewal. | Required for security and for search ranking. | Phase 19 | NOT STARTED | OBSERVED FROM RESEARCH
SSL | Force HTTPS | Redirect all HTTP traffic to HTTPS. | Prevents credentials travelling unencrypted. | Phase 19 | NOT STARTED | PROPOSED
Deployment | Health checks | Expose a health endpoint used by the deployment system. | Enables safe rolling deploys. | Phase 4 | NOT STARTED | PROPOSED
Deployment | Rolling or blue-green deploys | Deploy without dropping live traffic. | Users should not see errors during a release. | Phase 19 | NOT STARTED | PROPOSED
Rollback | Documented rollback procedure | Write down exactly how to revert a bad release. | Speed of recovery matters more than avoiding every failure. | Phase 19 | NOT STARTED | OBSERVED FROM RESEARCH
Rollback | Practise a rollback | Perform a rollback on staging at least once. | An untested procedure fails when you need it. | Phase 19 | NOT STARTED | PROPOSED
Disaster recovery | Define RTO and RPO | Decide acceptable downtime and acceptable data loss. | Decide this calmly now, not during an incident. | Phase 19 | NOT STARTED | OBSERVED FROM RESEARCH
Disaster recovery | Written DR runbook | Step-by-step recovery instructions with named owners. | Incidents are not the time to improvise. | Phase 19 | NOT STARTED | PROPOSED
Infrastructure as code | Define infrastructure in code | Use Terraform or equivalent rather than console clicks. | Makes environments reproducible and auditable. | Phase 19 | NOT STARTED | PROPOSED
Cost | Cost monitoring and alerts | Set budget alerts on cloud spend. | Cloud bills surprise people, especially with image traffic. | Phase 19 | NOT STARTED | PROPOSED

## THIRD-PARTY SERVICES
THIRD-PARTY SERVICES — what you must buy or sign up for
Do NOT sign up for everything at once. Only the MVP rows are needed for launch. Note that DLT registration for Indian SMS has a lead time — start that early.
Service | Purpose | MVP/Future | Why Needed | Alternative | Estimated Cost | Integration Phase | Status | Source
SMS / OTP provider | Deliver one-time codes and lead alerts by SMS. | MVP | OTP is the primary login method and the gate on contact reveal. Nothing works without it. | MSG91, Twilio, AWS SNS, Gupshup | Per-message; budget for OTP volume plus abuse margin. DLT registration required in India. | Phase 5 | NOT STARTED | DECISION REQUIRED
Email provider | Transactional email: verification, lead alerts, notifications. | MVP | Secondary notification channel and account recovery. | Resend, AWS SES, Postmark, SendGrid | Low at launch volume; usually per-thousand emails. | Phase 10 | NOT STARTED | DECISION REQUIRED
Object storage | Store listing photos and documents. | MVP | Images cannot live in the database; you need durable blob storage. | AWS S3, Cloudflare R2, Google Cloud Storage | Storage plus egress. R2 has no egress fee — relevant for an image-heavy product. | Phase 4 | NOT STARTED | OBSERVED FROM RESEARCH
CDN | Serve assets and cache HTML at the edge. | MVP | The single cheapest performance improvement available. | Cloudflare, Fastly, AWS CloudFront | Free tier often sufficient at launch. | Phase 19 | NOT STARTED | OBSERVED FROM RESEARCH
Maps / geocoding | Show property locations; geocode addresses. | MVP (static map only) | Location is the primary decision factor on the detail page. | MapLibre + MapTiler/Protomaps, Google Maps, Mapbox | MapLibre with open tiles can be near-free; Google bills per load and grows fast. | Phase 6 | NOT STARTED | DECISION REQUIRED
Error monitoring | Capture and alert on application errors. | MVP | You cannot fix errors you never hear about. | Sentry, Rollbar, Bugsnag | Free tier usually sufficient at launch. | Phase 15 | NOT STARTED | OBSERVED FROM RESEARCH
Web analytics | Understand traffic sources and page performance. | MVP | Tells you which acquisition channels actually work. | GA4, Plausible, Fathom, PostHog | Free to low. | Phase 15 | NOT STARTED | DECISION REQUIRED
Event analytics / product analytics | Own the lead funnel data end to end. | MVP | The lead funnel is the business; owning this data is non-negotiable. | PostHog (self-hosted or cloud), own pipeline to a warehouse | Self-hosting trades money for operational effort. | Phase 15 | NOT STARTED | OBSERVED FROM RESEARCH
Hosting — frontend | Run the server-rendered web application. | MVP | Required to serve the site. | Vercel, Netlify, self-managed containers | Scales with traffic; watch bandwidth on image-heavy pages. | Phase 19 | NOT STARTED | DECISION REQUIRED
Hosting — backend & database | Run the API, workers and database. | MVP | Required to serve the site. | AWS, GCP, Railway, Render, Fly.io, DigitalOcean | Managed database is worth the premium at this stage. | Phase 19 | NOT STARTED | DECISION REQUIRED
Uptime monitoring | External checks that the site is up. | MVP | Tells you about outages before users do. | BetterStack, UptimeRobot, Pingdom | Free tier usually sufficient. | Phase 19 | NOT STARTED | OBSERVED FROM RESEARCH
Domain registrar | Own the domain name. | MVP | Required before anything is public. | Any reputable registrar | Annual, small. | Phase 0 | NOT STARTED | DECISION REQUIRED
Payment gateway | Take payment for seller plans. | FUTURE (v1.3) | Not needed until monetisation begins. Do not integrate early. | Razorpay, Cashfree, PayU, Stripe | Percentage per transaction. Indian gateways handle UPI and GST invoicing. | Phase 19+ | NOT STARTED | DECISION REQUIRED
Telephony / number masking | Route calls through proxy numbers. | FUTURE (v1.2) | Protects sellers from long-term spam; a genuine differentiator. | Exotel, Knowlarity, Twilio Proxy | Per-minute plus number rental. Meaningful ongoing cost. | Post-MVP | NOT STARTED | OBSERVED FROM RESEARCH
Push notification service | Deliver push notifications to devices. | FUTURE (v1.2) | Lead response speed is the seller's core value. | Firebase Cloud Messaging, OneSignal | Usually free at this scale. | Phase 22 | NOT STARTED | OBSERVED FROM RESEARCH
Search engine service | Dedicated search cluster. | FUTURE (v2.0) | Only when PostgreSQL search stops meeting latency budgets. | OpenSearch, Elasticsearch, Typesense, Algolia | Significant. Deliberately deferred — see the research's phased search plan. | Post-MVP | NOT STARTED | OBSERVED FROM RESEARCH
Image moderation / OCR | Detect contact details and unsuitable content in photos. | MVP (basic) | Protects the lead model; manual review alone does not scale. | AWS Rekognition, Google Vision, self-hosted OCR | Per-image. Start with cheap OCR for text detection only. | Phase 13 | NOT STARTED | OBSERVED FROM RESEARCH
Feature flags | Roll out changes safely to a subset of users. | FUTURE | Useful once there is enough traffic for staged rollout. | PostHog, Unleash, LaunchDarkly | Free tiers available. | Post-MVP | NOT STARTED | OBSERVED FROM RESEARCH
Customer support tooling | Handle user queries and complaints. | MVP (basic) | A support channel is a legal and practical necessity from day one. | Email inbox at launch; Crisp, Freshdesk later | Start with a monitored email address. | Phase 20 | NOT STARTED | PROPOSED
Secrets manager | Store credentials securely. | MVP | Environment files on servers get copied and leaked. | AWS Secrets Manager, Doppler, Infisical, 1Password | Low. | Phase 17 | NOT STARTED | OBSERVED FROM RESEARCH

## MONETIZATION ROADMAP
MONETIZATION ROADMAP — how the product makes money, and when
Nothing is charged at launch, deliberately. The research's central finding is that the monetisable event is the contact reveal: instrument it from day one, charge for it later.
Item | Type | MVP/Future | Description | Rationale | Dependencies | Target Release | Status | Source
Free listings for everyone | Free | MVP | All sellers can list at no cost during the first phase. | You cannot charge before proving liquidity and lead quality. Charging on thin supply kills marketplaces. | Phase 7 | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Free listing quota | Quota | MVP | Limit the number of free active listings per account. | Creates the scarcity that later plans relieve. Build the accounting even while everything is free. | Phase 7 | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Quota ledger (append-only) | Infrastructure | MVP | Record every quota consumption as an immutable ledger entry. | Quota disputes are common; an append-only ledger is the only defensible answer. | Phase 7 | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Lead instrumentation | Infrastructure | MVP | Record every enquiry and contact reveal as a first-class object. | You cannot price what you cannot measure. This is the monetisable event. | Phase 10 | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Lead quality measurement | Analytics | MVP | Track which leads sellers mark as qualified or closed. | Lead quality — not volume — is what sellers will pay for. | Phase 10, 15 | MVP | NOT STARTED | OBSERVED FROM RESEARCH
Buyer side stays free | Policy | MVP | Buyers and tenants never pay. | Standard for the category; charging buyers destroys the demand side that sellers are paying to reach. | — | Permanent | NOT STARTED | OBSERVED FROM RESEARCH
Owner paid plan | Subscription | FUTURE | More listings, longer duration, verified badge, featured days, analytics. | The individual-owner cohort is underserved by sales-assisted enterprise pricing. | Payments | v1.3 | NOT STARTED | OBSERVED FROM RESEARCH
Agent starter plan | Subscription | FUTURE | Listing allowance, lead inbox, bulk upload, public profile. | Agents are the recurring-revenue cohort. | Payments, agent tools | v1.3 | NOT STARTED | OBSERVED FROM RESEARCH
Agent pro plan | Subscription | FUTURE | Higher allowances, featured credits, priority placement, CRM export. | Upgrade path for high-volume agents. | Agent starter | v1.4 | NOT STARTED | OBSERVED FROM RESEARCH
Builder package | Subscription | FUTURE | Project microsite, unlimited configurations, brand placement, campaign reporting. | Builders have the largest marketing budgets in this category. | Projects module | v1.5 | NOT STARTED | OBSERVED FROM RESEARCH
Payments and GST invoicing | Infrastructure | FUTURE | Take payment and issue compliant invoices. | Required before any money can be collected in India. | Payment gateway | v1.3 | NOT STARTED | OBSERVED FROM RESEARCH
Featured listing placement | Advertising | FUTURE | Paid, clearly-labelled ranking boost with a bounded multiplier. | Sells visibility without destroying the relevance that makes visibility valuable. | Payments, ranking | v1.3 | NOT STARTED | OBSERVED FROM RESEARCH
Top-slot placement by locality | Advertising | FUTURE | Fixed premium slots on specific locality result pages. | High-value inventory because intent is unambiguous. | Featured listings | v1.3 | NOT STARTED | OBSERVED FROM RESEARCH
Promotion caps and labelling | Policy | FUTURE | Never more than 2 promoted results in the first 10; always visibly labelled. | Unbounded paid ranking destroys result quality and users detect it quickly. | Featured listings | v1.3 | NOT STARTED | OBSERVED FROM RESEARCH
Homepage and city banners | Advertising | FUTURE | Display advertising placements. | Additional inventory once traffic justifies it. | Traffic volume | v2.0 | NOT STARTED | PROPOSED
Lead packages | Lead monetization | FUTURE | Sell blocks of leads rather than listing slots. | Aligns price with value delivered rather than promises made. | Lead quality data | v1.4 | NOT STARTED | OBSERVED FROM RESEARCH
Verification as a paid add-on | Service | FUTURE | Charge for assisted or higher-tier verification. | Verification has a real operational cost; charging funds the quality. | Verification tiers | v1.4 | NOT STARTED | PROPOSED
Home loan referral | Adjacent revenue | FUTURE | Refer qualified buyers to lenders. | A mortgage lead is worth far more than a listing lead; an EMI calculator qualifies users for free. | Finance partners | v2.2 | NOT STARTED | OBSERVED FROM RESEARCH
Rent agreement and tenant verification | Adjacent revenue | FUTURE | Offer paid transactional services around renting. | Converts an event-driven business into a recurring one. | Partners | v2.2 | NOT STARTED | OBSERVED FROM RESEARCH
Self-serve pricing page | Policy | FUTURE | Publish prices publicly rather than quoting by phone. | Sales-assisted-only pricing excludes the long tail of individual owners — the cohort a new entrant can win. | Plans | v1.3 | NOT STARTED | OBSERVED FROM RESEARCH
Never sell undisclosed ranking | Policy | FUTURE | All paid placement is labelled and bounded. | Trust is the only durable advantage against an incumbent with more inventory. | — | Permanent | NOT STARTED | OBSERVED FROM RESEARCH

## LAUNCH CHECKLIST
LAUNCH CHECKLIST — the final gate before going live
Every item must be DONE or consciously DEFERRED. Work through this top to bottom in Phase 20. If an item is not true, you are not ready.
Category | Item | What Must Be True | Status | Owner | Notes
Product | MVP scope complete | Every item marked MVP in the MVP CHECKLIST is DONE or consciously DEFERRED. | NOT STARTED | UNASSIGNED
Product | Success metrics defined | Targets agreed and measurable in the analytics dashboard. | NOT STARTED | UNASSIGNED
Product | Launch cities confirmed | Cities are named, and the gazetteer covers them fully. | NOT STARTED | UNASSIGNED
Product | Minimum inventory reached | Enough active listings exist that search is useful in every launch city. | NOT STARTED | UNASSIGNED | Research proposes 2,000+ across 3 cities.
UI/UX | All MVP screens built | Every page marked MVP in WEBSITE PAGES exists and is reachable. | NOT STARTED | UNASSIGNED
UI/UX | Empty, loading and error states | Every list and form has all three states designed and implemented. | NOT STARTED | UNASSIGNED
UI/UX | Mobile responsiveness verified | Tested at 390, 412, 768, 1024 and 1280px with no layout defects. | NOT STARTED | UNASSIGNED
UI/UX | Accessibility pass | Keyboard navigation works; focus visible; contrast meets AA. | NOT STARTED | UNASSIGNED
UI/UX | Original branding confirmed | No competitor branding, wording, imagery or visual identity anywhere. | NOT STARTED | UNASSIGNED | Legal requirement, not a preference.
Database | Schema finalised for MVP | All MVP tables exist with indexes and constraints. | NOT STARTED | UNASSIGNED
Database | Migrations tested | Migrations run forward and roll back cleanly on a copy of production. | NOT STARTED | UNASSIGNED
Database | Seed and reference data loaded | Property types, amenities and the gazetteer are populated. | NOT STARTED | UNASSIGNED
Database | Backups running and restored once | A real restore has been performed into a clean environment. | NOT STARTED | UNASSIGNED | Do not accept an untested backup.
Backend | All MVP APIs implemented | Every API marked MVP responds correctly including error cases. | NOT STARTED | UNASSIGNED
Backend | Health endpoint live | Monitoring can confirm application and dependency health. | NOT STARTED | UNASSIGNED
Backend | Background workers running | Image processing, moderation, notifications and indexing all process jobs. | NOT STARTED | UNASSIGNED
Backend | Rate limits active | Search, OTP, reveal and upload endpoints are rate-limited. | NOT STARTED | UNASSIGNED
Frontend | Server-side rendering verified | Page source contains listing content without JavaScript enabled. | NOT STARTED | UNASSIGNED
Frontend | No console errors | No errors in the browser console on any core journey. | NOT STARTED | UNASSIGNED
Frontend | Images optimised | Modern formats, responsive sizes, correct lazy loading, reserved space. | NOT STARTED | UNASSIGNED
Authentication | OTP delivery reliable | Codes arrive within seconds on all major Indian networks. | NOT STARTED | UNASSIGNED | Verify DLT template approval is complete.
Authentication | Session handling correct | Login persists; refresh works; logout revokes. | NOT STARTED | UNASSIGNED
Authentication | Role permissions enforced | Cross-role access attempts fail, verified by automated tests. | NOT STARTED | UNASSIGNED
Search | All filters correct | Every filter returns exactly the right results against seeded data. | NOT STARTED | UNASSIGNED
Search | Facet counts correct | Counts verified against manual expectation. | NOT STARTED | UNASSIGNED
Search | Filter state never lost | No filter or sort action loses state, even when the API errors. | NOT STARTED | UNASSIGNED | The single most important quality bar for this product.
Search | Zero-result recovery works | Relaxation ladder triggers and explains itself. | NOT STARTED | UNASSIGNED
Search | Search latency within budget | p95 within the PERFORMANCE sheet target at realistic volume. | NOT STARTED | UNASSIGNED
Property posting | Wizard completes on mobile | Five external users completed posting unaided; median under 8 minutes. | NOT STARTED | UNASSIGNED
Property posting | Autosave verified | Refreshing mid-form loses nothing. | NOT STARTED | UNASSIGNED
Property posting | Photo upload reliable | Works on a slow mobile connection with retry on failure. | NOT STARTED | UNASSIGNED
Property posting | Quota enforced | Over-quota publishing is blocked with a clear message. | NOT STARTED | UNASSIGNED
Leads | Enquiry delivered end to end | Enquiry reaches the seller inbox and notifies them. | NOT STARTED | UNASSIGNED
Leads | Contact reveal records before revealing | Inquiry is written before the number is displayed. | NOT STARTED | UNASSIGNED
Leads | Duplicate reveals deduplicated | Repeat reveal creates no second billable lead. | NOT STARTED | UNASSIGNED
Leads | Contact details not leaked in API | Raw network responses contain no seller phone number before reveal. | NOT STARTED | UNASSIGNED
Admin | Moderation queue operational | Listings can be approved and rejected with reasons. | NOT STARTED | UNASSIGNED
Admin | Reports handled | Reporting works and reports reach the queue with an SLA timer. | NOT STARTED | UNASSIGNED
Admin | Audit log recording | Every admin action writes an immutable entry. | NOT STARTED | UNASSIGNED
Admin | Staff trained | Whoever moderates knows the policy and the tools. | NOT STARTED | UNASSIGNED | Often forgotten; moderation quality depends on it.
SEO | URLs final | No indexable URL will change after launch. | NOT STARTED | UNASSIGNED | Changing URLs post-indexing costs ranking.
SEO | Canonicals correct | Every page declares the intended canonical URL. | NOT STARTED | UNASSIGNED
SEO | Indexation rules applied | App surface noindex; thin pages noindex; allowlist enforced. | NOT STARTED | UNASSIGNED
SEO | Sitemaps live and submitted | Sitemap index generated, valid and submitted to Search Console. | NOT STARTED | UNASSIGNED
SEO | robots.txt correct | Nothing in the sitemap is disallowed. | NOT STARTED | UNASSIGNED
SEO | Structured data valid | JSON-LD validates on every page type. | NOT STARTED | UNASSIGNED
SEO | Search Console verified | Property verified and coverage monitoring in place. | NOT STARTED | UNASSIGNED
Security | Independent security review passed | All critical and high findings resolved. | NOT STARTED | UNASSIGNED
Security | No secrets in the repository | Git history verified clean. | NOT STARTED | UNASSIGNED
Security | HTTPS enforced with HSTS | HTTP redirects; certificate auto-renews. | NOT STARTED | UNASSIGNED
Security | Security headers set | CSP and related headers verified by an external scanner. | NOT STARTED | UNASSIGNED
Security | PII protected | Personal data encrypted at rest; lead access logged. | NOT STARTED | UNASSIGNED
Performance | All budgets met | Every target in the PERFORMANCE sheet is green on five representative routes. | NOT STARTED | UNASSIGNED
Performance | CI performance gate active | Builds fail on budget breach. | NOT STARTED | UNASSIGNED
Performance | Tested on a real mid-range phone | Not only on a developer machine. | NOT STARTED | UNASSIGNED
Analytics | Event tracking live | Every funnel step is recorded and queryable. | NOT STARTED | UNASSIGNED
Analytics | Funnel dashboard built | Each success metric is visible as a number. | NOT STARTED | UNASSIGNED
Analytics | Error monitoring live | Errors alert a real person with full context. | NOT STARTED | UNASSIGNED
Legal | Terms and Conditions published | Reviewed by a lawyer and linked from every page. | NOT STARTED | UNASSIGNED
Legal | Privacy policy published | Describes data collected, retention and user rights. | NOT STARTED | UNASSIGNED
Legal | Verification scope disclaimer | States exactly what a verified badge does and does not prove. | NOT STARTED | UNASSIGNED | Copy the honesty of this scoping — it is legally protective.
Legal | Data-protection compliance | Consent capture, retention limits and deletion flow all working. | NOT STARTED | UNASSIGNED
Legal | Contact and grievance channel | A monitored support address and complaint process exist. | NOT STARTED | UNASSIGNED
Domain | Domain live | Domain resolves, HTTPS works, www and apex behave consistently. | NOT STARTED | UNASSIGNED
Domain | Email deliverability | SPF, DKIM and DMARC configured so transactional email is not spam-filed. | NOT STARTED | UNASSIGNED
Deployment | Production deploy tested | A full deploy has been performed successfully. | NOT STARTED | UNASSIGNED
Deployment | Rollback tested | A rollback has been performed on staging. | NOT STARTED | UNASSIGNED
Deployment | Monitoring and alerting live | A simulated outage produced an alert to a real person. | NOT STARTED | UNASSIGNED
Deployment | Disaster recovery plan written | RTO and RPO defined with named steps and owners. | NOT STARTED | UNASSIGNED
Testing | Full test suite green | All automated tests pass on the release build. | NOT STARTED | UNASSIGNED
Testing | User acceptance testing complete | External users completed both posting and search journeys. | NOT STARTED | UNASSIGNED
Testing | Production smoke tests pass | Post, search, contact and OTP verified on the live site. | NOT STARTED | UNASSIGNED
Testing | Cross-browser verified | No blocking defect in Chrome, Safari, Firefox or Edge. | NOT STARTED | UNASSIGNED
Launch ops | Support coverage arranged | Someone is available to answer users in the first week. | NOT STARTED | UNASSIGNED
Launch ops | 72-hour watch planned | A person is assigned to monitor errors, performance and leads after launch. | NOT STARTED | UNASSIGNED
Launch ops | Rollback decision criteria agreed | You know in advance what would make you roll back. | NOT STARTED | UNASSIGNED

## POST-LAUNCH ROADMAP
POST-LAUNCH ROADMAP — what comes after launch
Grouped into releases. Nothing here is invented: every item is either deferred from the MVP scope or recommended by the research document.
Release | Item | Category | Description | Why | Priority | Status | Source
Immediate (weeks 1–4) | Triage and fix critical defects | Stability | Fix anything blocking a core journey. | Broken core journeys destroy early word of mouth permanently. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Immediate (weeks 1–4) | Measure against launch targets | Analytics | Compare actual funnel numbers to the agreed targets. | Tells you whether to optimise or change direction. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Immediate (weeks 1–4) | Fix the weakest funnel step | Conversion | Focus entirely on whichever step is furthest from target. | Focused effort beats broad tinkering. | CRITICAL | NOT STARTED | OBSERVED FROM RESEARCH
Immediate (weeks 1–4) | Review SEO indexation | SEO | Check what actually got indexed and fix crawl errors. | Indexation problems are invisible unless checked. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
Immediate (weeks 1–4) | Tune duplicate detection | Quality | Adjust thresholds using real listing data. | Our stated differentiator; needs live data to calibrate. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
Immediate (weeks 1–4) | Reduce moderation backlog | Operations | Tune auto-approval so human review stays manageable. | Slow review frustrates sellers and slows supply growth. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
v1.1 — Discovery | Interactive map search | Search | Bounding-box search with clustered markers and list toggle. | Highly requested in this category; deferred from MVP for cost and complexity. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
v1.1 — Discovery | Saved searches with alerts | Retention | Let buyers save a search and be notified of new matches. | The single best retention mechanism for a months-long decision. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
v1.1 — Discovery | Comparison view | Buyer tools | Side-by-side comparison with normalised area basis and price per unit. | Buyers build these spreadsheets manually today — a real differentiator. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v1.1 — Discovery | Recent searches sync | Retention | Persist recent searches across devices for logged-in users. | Property search spans weeks and multiple devices. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v1.1 — Discovery | WhatsApp contact option | Leads | Offer WhatsApp as a contact channel. | Dominant communication channel in the Indian market. | HIGH | NOT STARTED | PROPOSED
v1.2 — Trust | Phone number masking | Trust | Route calls through proxy numbers by default for owner listings. | Not evidenced at the incumbent; protects sellers from long-term spam. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
v1.2 — Trust | Seller response-rate badges | Trust | Show how quickly and how often a seller responds. | Response speed is the strongest driver of lead conversion. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v1.2 — Trust | Last-verified date on listings | Trust | Show when a listing was last confirmed as available. | Directly attacks the category's biggest complaint: dead listings. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
v1.2 — Trust | Automatic stale-listing expiry tuning | Quality | Refine expiry windows using real availability data. | Keeps the catalogue honest without annoying active sellers. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
v1.2 — Trust | Web push notifications | Notifications | Push lead alerts to installed devices. | Lead response speed is the seller's core value. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v1.3 — Monetisation | Seller subscription plans | Revenue | Owner and agent plans with quotas and features. | Only after lead quality is proven. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
v1.3 — Monetisation | Payments and GST invoicing | Revenue | Integrate a payment gateway with compliant invoicing. | Required to collect money in India. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
v1.3 — Monetisation | Featured listings (bounded, labelled) | Revenue | Paid placement with a capped boost and visible labelling. | Sells visibility without destroying relevance. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
v1.3 — Monetisation | Self-serve pricing page | Revenue | Publish plan pricing publicly. | Captures the individual-owner long tail that phone-quoted pricing excludes. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v1.3 — Monetisation | Seller analytics upgrade | Revenue | Deeper performance data for paying sellers. | Creates the upgrade conversation. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v1.4 — Supply depth | Commercial property category | Catalogue | Add commercial with its own field schema and filters. | Expands addressable supply; deferred because it is a full second schema. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v1.4 — Supply depth | PG / co-living category | Catalogue | Add PG with gender, meals and sharing fields. | Different economics and a fast-moving rental segment. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v1.4 — Supply depth | Plots and land category | Catalogue | Add plots with dimensions and boundary fields. | Distinct buyer type with no BHK concept. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v1.4 — Supply depth | Agent public profiles | Agent tools | Public agent pages with listings and areas served. | Agents are the paying cohort; profiles are a retention feature. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
v1.4 — Supply depth | Agent bulk upload and feeds | Agent tools | Bulk listing creation by file or feed. | Power users cannot work listing by listing. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
v1.4 — Supply depth | Agent lead CRM | Agent tools | Assignment, follow-up reminders and export. | Retention mechanism for the paying cohort. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v1.5 — Projects | Project entity and configurations | Catalogue | New-construction projects with unit configurations and floor plans. | Different buyer psychology and the highest-value advertising inventory. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v1.5 — Projects | Builder profiles and microsites | Builder tools | Developer pages and project microsites. | Builders have the largest marketing budgets. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v1.5 — Projects | Brochure and payment-plan hosting | Builder tools | Gated document downloads. | The canonical builder lead magnet: high intent, low friction. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v1.5 — Projects | RERA cross-verification | Trust | Check declared RERA IDs against state registries where feasible. | Meaningful trust signal; complex because each state differs. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v2.0 — Data & content | Locality hub pages at scale | SEO | Rich locality pages across all covered cities. | Captures research intent that listings alone cannot. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v2.0 — Data & content | Locality reviews and ratings | Content | Resident reviews on environment, connectivity and safety. | Needs a user base first; an empty review section damages trust. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v2.0 — Data & content | Price trends | Content | Rate-per-area and appreciation data by locality. | Needs historical data and a minimum sample size to be credible. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v2.0 — Data & content | Programmatic landing matrix | SEO | Generate the full combinatorial page matrix with governance. | The incumbent's core acquisition machine. | HIGH | NOT STARTED | OBSERVED FROM RESEARCH
v2.0 — Data & content | OpenSearch migration | Search | Move search to a dedicated cluster. | Only when PostgreSQL stops meeting latency budgets — a measured trigger. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v2.0 — Data & content | Locality boundary polygons | Search | Acquire real boundary geometry city by city. | Enables true polygon search and accurate pin validation. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v2.1 — Intelligence | Learning-to-rank relevance | Search | Train ranking on click and contact signals. | Needs traffic volume before it can learn anything useful. | LOW | NOT STARTED | OBSERVED FROM RESEARCH
v2.1 — Intelligence | Personalised recommendations | Buyer tools | Recommend listings based on behaviour. | Improves engagement once there is behavioural data. | LOW | NOT STARTED | OBSERVED FROM RESEARCH
v2.1 — Intelligence | Semantic / natural-language search | Search | Support queries like 'near a good school with a park'. | Differentiating but only worthwhile at scale. | LOW | NOT STARTED | OBSERVED FROM RESEARCH
v2.1 — Intelligence | Lead scoring | Leads | Score lead quality to sell fewer, better leads. | Directly attacks the incumbent's weakest commercial point. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v2.1 — Intelligence | Price estimation | Content | Estimate a fair price range for a listing. | High-value trust feature; requires substantial data. | LOW | NOT STARTED | OBSERVED FROM RESEARCH
v2.2 — Adjacent revenue | Home loan marketplace | Revenue | Refer qualified buyers to lenders. | A mortgage lead is worth far more than a listing lead. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v2.2 — Adjacent revenue | EMI calculator | Content | Loan calculators as an SEO and qualification asset. | Cheap to build, high intent, strong SEO — could come earlier. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v2.2 — Adjacent revenue | Rent agreements and tenant verification | Revenue | Paid transactional services around renting. | Converts an event business into a recurring one. | LOW | NOT STARTED | OBSERVED FROM RESEARCH
v3.0 — Platform | Native mobile apps | Platform | iOS and Android applications. | Only if launch data justifies two more codebases. | MEDIUM | NOT STARTED | OBSERVED FROM RESEARCH
v3.0 — Platform | Partner API | Platform | Documented API for partners and feeds. | Enables agent software integrations and supply partnerships. | LOW | NOT STARTED | OBSERVED FROM RESEARCH
v3.0 — Platform | Multi-language support | Platform | Localise the interface and content. | Significant complexity across content, SEO and UI. | LOW | NOT STARTED | OBSERVED FROM RESEARCH
v3.0 — Platform | Additional cities and regions | Growth | Expand geographic coverage. | Growth lever once the model is proven in the launch cities. | HIGH | NOT STARTED | PROPOSED
Long-term | Microservice extraction | Platform | Split modules into services only if team size and load require it. | A solution to an organisational problem you do not yet have. | LOW | NOT STARTED | OBSERVED FROM RESEARCH

## DECISIONS LOG
DECISIONS LOG — questions only YOU can answer
THE MOST IMPORTANT SHEET FOR YOU. Nothing is decided automatically. Review weekly: write your answer in 'Final Decision', set the date, and change Decision Status to DECIDED.
Decision ID | Decision | Options | Recommended / Proposed Direction | Reason | Impact | Decision Status | Final Decision | Date
D-01 | Frontend framework and language | (a) Next.js + React + TypeScript (b) Remix (c) Nuxt/Vue (d) Plain React SPA | Next.js (App Router) + React + TypeScript | Server-side rendering is a hard requirement for the SEO architecture. Option (d) cannot deliver it without a rewrite. Research §22. | Very high — affects every frontend task, hiring, and whether SEO works at all. | OPEN — DECISION REQUIRED
D-02 | Backend framework and architecture style | (a) NestJS modular monolith (TypeScript) (b) Spring Boot (Java) (c) Django (Python) (d) Microservices from day one | NestJS modular monolith | Same language as the frontend means shared types and one skill set for a small team. Microservices solve an organisational problem you do not have yet. Research §21.1, §22. | Very high — affects hiring, libraries, deployment and delivery speed. | OPEN — DECISION REQUIRED
D-03 | Primary database | (a) PostgreSQL + PostGIS (b) MySQL (c) MongoDB | PostgreSQL 16 + PostGIS | One engine covers relational data, geospatial search, full-text search and JSON for the entire first phase. Research §22. | Very high — the data model constrains everything built on it. | OPEN — DECISION REQUIRED
D-04 | Search engine approach | (a) PostgreSQL only, migrate later (b) OpenSearch/Elasticsearch from day one (c) Hosted search (Algolia/Typesense) | PostgreSQL first; add OpenSearch at a measured trigger | Running a search cluster before there is data to justify it adds operational burden for no benefit. Set an explicit migration trigger (listing count or facet latency). Research §13.3. | High — but reversible if the index is kept as a derived, rebuildable projection. | OPEN — DECISION REQUIRED
D-05 | Image and object storage | (a) Cloudflare R2 (b) AWS S3 (c) Google Cloud Storage | R2 or S3, decided together with hosting (D-07) | This is an image-heavy product, so egress cost matters. R2 charges no egress; S3 does. Compare against where the rest of the stack lives. | Medium — migration is possible but tedious once there are many files. | OPEN — DECISION REQUIRED
D-06 | Maps and geocoding provider | (a) MapLibre + open vector tiles (b) Google Maps Platform (c) Mapbox | Decide with a cost model before Phase 6 | MapLibre avoids per-load billing; Google has better Indian place data and autocomplete. This is a genuine trade-off between cost and data quality. Research §22. | Medium-high — affects cost at scale and the quality of location search. | OPEN — DECISION REQUIRED
D-07 | Hosting and cloud provider | (a) Vercel (frontend) + managed containers (backend) (b) Single cloud — AWS/GCP (c) Simplified platform — Railway/Render/Fly | Start managed; avoid Kubernetes until the team needs it | Operational simplicity is worth more than theoretical flexibility at launch. Research §22 explicitly defers Kubernetes. | High — affects cost, deployment complexity and every DevOps task. | OPEN — DECISION REQUIRED
D-08 | Authentication and session strategy | (a) Own OTP flow + JWT access with rotating refresh (b) Managed auth provider (c) Session cookies only | Own OTP flow with rotating refresh tokens | Authentication is core to this product (roles, quotas, contact-reveal gating), and OTP-first is the right pattern for India. Research §22. | High — security-critical and hard to change after launch. | OPEN — DECISION REQUIRED
D-09 | OTP / SMS provider | (a) MSG91 (b) Twilio (c) AWS SNS (d) Gupshup | Choose an India-focused provider and start DLT registration EARLY | DLT template registration is legally required in India and has a lead time that can delay launch. Decide before Phase 5. | High — nothing in the product works without reliable OTP delivery. | OPEN — DECISION REQUIRED
D-10 | Analytics stack | (a) PostHog (events + flags + replay) (b) Own pipeline to a warehouse + GA4 (c) GA4 only | PostHog or an owned pipeline; GA4 alone is not enough | The lead funnel is the business. GA4 cannot answer lead-level questions. Research §22 calls owning event data non-negotiable. | Medium-high — retrofitting event tracking loses all historical data. | OPEN — DECISION REQUIRED
D-11 | MVP launch cities | (a) One city (b) Three cities (c) One metro plus its satellite towns | Research proposes three cities — YOU MUST NAME THEM | Cities determine the gazetteer work, the supply plan and the inventory target. This is a business decision only you can make. Research §24. | Very high — determines scope, effort and whether launch inventory is achievable. | OPEN — DECISION REQUIRED
D-12 | Property categories in MVP | (a) Residential Buy + Rent only (b) Add Commercial (c) Add PG (d) Add Plots | Residential Buy + Rent only | Each additional category is a full field schema, filter set and landing-page family. Research §24 defers all three. | High — each category added roughly extends the posting and search work. | OPEN — DECISION REQUIRED
D-13 | User roles at launch | (a) Buyer + Owner only (b) Buyer + Owner + Agent (c) All including Builder | Buyer + Owner, with Agent as a flagged role but no agent tooling | Agent tooling (bulk upload, CRM) is a v1.4 item. But you must decide now whether agents may post at all, because it affects moderation and quota policy. | High — affects moderation load, quota design and supply volume. | OPEN — DECISION REQUIRED
D-14 | 'Similar properties' in MVP — research conflict | (a) Include in MVP (b) Defer to v1.1 | Confirm one way | The research document is internally inconsistent: §24 lists similar properties in MVP scope, while §23 places it in the post-MVP discovery phase. Flagged rather than silently resolved. | Low-medium — a contained feature, but it should be consciously decided. | OPEN — DECISION REQUIRED
D-15 | Mobile strategy: PWA or native | (a) PWA only (b) PWA then native (c) Native immediately (d) React Native / Flutter | PWA first; decide on native only after launch data | Native means two more codebases, release cycles and store reviews. Research §20.3 suggests a PWA covers v1. Do not decide before you have real usage data. | Very high — native development is one of the largest cost items available. | OPEN — DECISION REQUIRED
D-16 | Monetisation model and timing | (a) Free until liquidity proven, then subscriptions (b) Charge from launch (c) Commission per transaction | Free first; subscriptions at v1.3 | Charging before proving lead quality kills marketplaces. The research's core finding is that the monetisable event is the contact reveal — instrument it now, charge later. | High — affects supply growth, pricing credibility and cash flow. | OPEN — DECISION REQUIRED
D-17 | Brand name and domain | Open | Must be original and trademark-checked | Needed before design, SEO and any public artefact. Must not resemble any competitor's branding. | Very high — effectively irreversible once indexed. | OPEN — DECISION REQUIRED
D-18 | Free listing quota per owner | (a) 1 (b) 2 (c) 3 (d) Unlimited during launch | Research observed the incumbent offering 1–2; consider unlimited during the supply-building phase | Too tight a quota starves you of launch supply. Too loose makes later monetisation harder. Revisit after launch. | Medium — adjustable, but changing it later annoys existing sellers. | OPEN — DECISION REQUIRED
D-19 | Thin-content indexation threshold | (a) 3 listings (b) 5 listings (c) 10 listings | Research proposes at least 5 active listings | Too low and you index near-empty pages, risking demotion. Too high and you forgo long-tail traffic. Research §16.5. | Medium — tunable, but mistakes here damage domain-level SEO. | OPEN — DECISION REQUIRED
D-20 | Locality data source | (a) Open data (b) Commercial dataset (c) Manual compilation (d) Hybrid | Decide before Phase 6 — this blocks a lot of work | The gazetteer is the most important table in the system and cannot be generated. Boundary polygons in particular are a genuine acquisition project. Research §20.4. | Very high — blocks search, SEO, posting and statistics. | OPEN — DECISION REQUIRED
D-21 | Listing expiry period | (a) 30 days (b) 60 days (c) 90 days | Choose deliberately and prompt before expiry | Stale listings are the category's biggest trust problem and our stated differentiator. Shorter expiry means fresher catalogue but more seller friction. | Medium — directly affects perceived catalogue quality. | OPEN — DECISION REQUIRED
D-22 | Photo limit per listing | (a) 20 (b) 30 (c) 50 | Research proposes 30 for MVP (the incumbent allows 50) | Higher limits increase storage, processing and moderation cost. Start conservative and raise it if sellers ask. | Low — easily adjusted later. | OPEN — DECISION REQUIRED
D-23 | Who builds this | (a) Solo with AI assistance (b) Hire developers (c) Agency (d) Technical co-founder | Open — affects every effort estimate in this workbook | The effort estimates assume competent full-time development. Adjust all timelines to your actual capacity. Be honest about this. | Very high — determines whether the roadmap timeline is realistic at all. | OPEN — DECISION REQUIRED
D-24 | Payment gateway (future) | (a) Razorpay (b) Cashfree (c) PayU (d) Stripe | Defer until v1.3; Indian gateways handle UPI and GST invoicing | Do not integrate payments before monetisation begins. Research §22. | Medium — deferred, so low cost to decide late. | OPEN — DECISION REQUIRED
D-25 | ORM / database access layer | (a) Prisma (b) Drizzle (c) TypeORM (d) Raw SQL with a query builder | Prisma, dropping to raw SQL for hot search paths | Type-safe with good migrations, but search queries usually need hand-written SQL anyway. Research §22. | Medium — changing it later is a large refactor. | OPEN — DECISION REQUIRED

## GLOSSARY
GLOSSARY — every technical term in plain English
If a word anywhere in this workbook is unfamiliar, look here first. No prior technical knowledge is assumed.
Term | Plain-English Meaning | Why It Matters For This Project | Where You Will See It
API | A way for one program to ask another program for data or to do something. Like a waiter carrying orders between you and the kitchen. | Your website (frontend) talks to your server (backend) through APIs. Every button that loads data calls one. | API CHECKLIST sheet; Phases 4–12
Frontend | Everything the user sees and clicks in their browser or app. | This is where your design system, pages and interactions live. | UI/UX CHECKLIST; WEBSITE PAGES; Phase 3
Backend | The part that runs on your servers: business rules, database access, security. Users never see it directly. | Where listings are stored, leads are recorded and permissions are enforced. | Phases 4–13; API CHECKLIST
Database | An organised store of your data — users, listings, leads — that can be searched and updated reliably. | The single most important technical asset you own. Everything else can be rebuilt. | DATABASE sheet; Phase 4
PostgreSQL | A specific, free, very reliable database system. Often shortened to 'Postgres'. | Recommended as your main database because it handles text search, location search and normal data in one system. | DECISIONS LOG D-03; Phase 4
PostGIS | An add-on for PostgreSQL that understands maps and locations — distances, areas, 'what is inside this boundary'. | Property search is fundamentally about location. This is what makes 'within 5 km' work. | DATABASE sheet; Phase 6
Redis | A very fast temporary store kept in memory. Used to remember answers so you do not recalculate them. | Makes filter counts and autocomplete fast, and enforces rate limits. | Phase 4; PERFORMANCE
OpenSearch / Elasticsearch | Specialised software built purely for searching and filtering large amounts of data quickly. | You will NOT use this at first. It is deliberately deferred until PostgreSQL stops keeping up. | DECISIONS LOG D-04; POST-LAUNCH v2.0
CDN (Content Delivery Network) | A network of servers worldwide that keeps copies of your images and files close to users. | Images are the heaviest part of a property site. A CDN is the cheapest speed improvement available. | DEVOPS; PERFORMANCE
SSR (Server-Side Rendering) | The server builds the complete page and sends finished HTML to the browser. | Essential for SEO. Search engines see your listings properly, and pages appear faster. | Phase 2; SEO CHECKLIST
SSG (Static Site Generation) | Pages are built once in advance and served as ready-made files. | Extremely fast, but only suitable for pages whose content rarely changes. | Phase 2; WEBSITE PAGES
ISR (Incremental Static Regeneration) | Pre-built pages that quietly refresh themselves on a schedule. | Ideal for locality and landing pages: fast like static, but the content stays current. | Phase 2; WEBSITE PAGES
PWA (Progressive Web App) | A website that can be installed on a phone and behaves much like a real app. | Gives you most app benefits without building and maintaining two separate mobile apps. | Phase 22; DECISIONS LOG D-15
OTP (One-Time Password) | A short code sent by SMS that proves someone controls a phone number. | Your main login method, and the gate before a buyer sees a seller's number. | Phase 5, 10; SECURITY
JWT (JSON Web Token) | A signed digital pass that proves who a user is without checking the database every time. | How your site remembers a user is logged in across requests. | DECISIONS LOG D-08; Phase 5
RBAC (Role-Based Access Control) | Deciding what someone may do based on their role — buyer, seller, admin. | Stops a buyer editing someone else's listing or reading someone else's leads. | Phase 5; SECURITY
CRUD | Create, Read, Update, Delete — the four basic things you do with data. | Most of your APIs are CRUD operations on listings, users and leads. | API CHECKLIST
SEO (Search Engine Optimisation) | Making your pages findable and attractive in Google results. | The research found this is the incumbent's main customer-acquisition channel. Your URL design decides whether it can work. | SEO CHECKLIST; Phase 14
JSON-LD | A hidden, machine-readable summary of a page, written for search engines. | Lets Google understand that a page describes a property with a price and a location. | SEO CHECKLIST; Phase 14
Sitemap | An XML file listing every page you want search engines to find. | How Google discovers thousands of listing pages it would otherwise miss. | SEO CHECKLIST; Phase 14
Canonical URL | A tag saying 'this is the official address for this content'. | Property sites generate many near-identical filtered pages. Canonicals stop them competing with each other. | SEO CHECKLIST; Phase 14
Thin content | A page with too little useful content to deserve indexing — for example a search page with two results. | Publishing thousands of near-empty pages can get your whole site downgraded by Google. | SEO CHECKLIST; DECISIONS LOG D-19
LCP (Largest Contentful Paint) | How long until the biggest visible thing appears on screen. | Google's main 'does this feel fast' measure, and a ranking factor. Target: under 2 seconds. | PERFORMANCE sheet
CLS (Cumulative Layout Shift) | How much the page jumps around while it loads. | Jumping pages make people tap the wrong thing. Usually caused by images without reserved space. | PERFORMANCE sheet
INP (Interaction to Next Paint) | How quickly the page reacts when you tap or click. | Directly measures whether filters feel responsive — the incumbent's weakest area. | PERFORMANCE sheet
TTFB (Time To First Byte) | How long the server takes to begin responding. | Slow TTFB makes everything after it slow, no matter how well the frontend is built. | PERFORMANCE sheet
CI/CD | Automation that checks your code and deploys it. CI = continuous integration (testing), CD = continuous deployment (releasing). | Stops broken code reaching users and removes error-prone manual deploys. | DEVOPS; Phase 1, 19
Docker | A way to package software with everything it needs so it runs identically everywhere. | Means the app behaves the same on your laptop and on the server. | Phase 1; DEVOPS
Queue | A waiting line of background jobs to be done later, outside the user's request. | Image processing and notifications must not make the user wait. | Phase 4; DATABASE (OUTBOX)
Worker | A background program that takes jobs off the queue and does them. | Processes photos, runs moderation checks and sends alerts. | Phase 4; DEVOPS
Cache | A temporary saved copy of an answer, so you do not recompute it every time. | Filter counts are expensive to calculate and change slowly — ideal to cache. | PERFORMANCE; Phase 16
Microservice | An architecture where the system is split into many small, independently deployed programs. | Deliberately NOT recommended for you. It solves a large-team problem and adds heavy complexity. | DECISIONS LOG D-02
Modular monolith | One deployable application, internally divided into clear modules with strict boundaries. | The recommended approach: simple to run now, cheap to split into services later if ever needed. | Phase 2; DECISIONS LOG D-02
Webhook | A way for another service to notify your server when something happens, by calling your URL. | Your payment provider will use one to tell you a payment succeeded. | API CHECKLIST (API-49)
Object storage | A service for storing files such as photos, separate from your database. | Databases are the wrong place for images. Object storage is cheap, durable and fast to serve. | Phase 4; THIRD-PARTY SERVICES
Presigned URL | A temporary, permission-limited link that lets a browser upload a file directly to storage. | Keeps large photo uploads off your server entirely. | API-24; Phase 4
Migration | A versioned, repeatable script that changes the database structure. | Lets you change the database safely and undo it if something breaks. | Phase 4; DEVOPS
Index (database) | A lookup structure that makes searching a table dramatically faster. | Without the right indexes, search becomes unusably slow as listings grow. | DATABASE sheet
Facet | A filter category with a count next to each option, like 'Ready to move (412)'. | The counts must be correct or the filters feel broken. Harder to build than it looks. | Phase 8; API-12
Gazetteer | A structured list of places — cities, localities, societies — with their relationships and coordinates. | The research calls this the most important table in the system. Everything depends on it. | Phase 6; DATABASE (LOCATION)
Slug | The human-readable part of a URL, such as 'flats-in-new-town'. | Carries the words users search for, which is why it matters for SEO. | Phase 2; SEO CHECKLIST
Carpet / built-up / super area | Three different legal ways of measuring an Indian property's size. | Mixing them up produces wrong prices per square foot and destroys user trust. Store all three separately. | DATABASE (PROPERTY); Phase 4
Lead | A potential customer's contact details, delivered to a seller. | This IS your business. The monetisable event is a buyer revealing a seller's number. | Phase 10; MONETIZATION
Contact reveal | The moment a verified buyer is shown a seller's phone number. | The single most important event in the product. Record it before displaying the number. | Phase 10; API-32
Rate limiting | Capping how often someone can call an endpoint. | Stops people harvesting seller phone numbers or running up your SMS bill. | SECURITY; Phase 17
EXIF | Hidden data inside a photo, which can include the exact GPS location where it was taken. | Must be stripped from uploads, or you publish sellers' home coordinates. | Phase 7; SECURITY
Perceptual hash (phash) | A fingerprint of an image that stays similar even if the image is resized or slightly edited. | How you detect the same property photographed and re-listed multiple times. | Phase 7; DATABASE
Audit log | An unchangeable record of who did what and when. | Needed to resolve disputes and to know what an admin or attacker actually did. | Phase 12; SECURITY
WCAG AA | The common international standard for making websites usable by people with disabilities. | A legal expectation in many markets, and it genuinely improves usability for everyone. | UI/UX CHECKLIST; Phase 3
RERA | India's Real Estate Regulatory Authority. Projects must be registered and display a registration number. | Displaying RERA information is both a trust signal and an advertising compliance matter. | Phase 13; SECURITY
DPDP Act | India's Digital Personal Data Protection law, covering consent, retention and deletion of personal data. | You store phone numbers and leads. Compliance is a legal requirement, not optional. | Phase 0, 5, 17
MVP (Minimum Viable Product) | The smallest version that is genuinely useful to real users. | Everything in this workbook is organised around protecting the MVP boundary from scope creep. | MVP CHECKLIST
Technical debt | Shortcuts taken now that cost more to fix later. | Performance and URL structure are the two kinds of debt this project must not take on. | Phase 14, 16